## PEDL Original Status
|  | Extant Licences | [6 empty] | Terminated June 2020 | [5 empty] | Relinquished - June 2016
| Licence | EXL203 | PEDL014 | PEDL100 | PEDL147 | PEDL148 | PEDL149 | PEDL157 | PEDL184 | PEDL214 | PEDL215 | PEDL216 | PEDL217 | PEDL224 | PEDL185 | PEDL186 | PEDL187 | PEDL188 | PEDL219 | PEDL220
STATUS | Status | Extant | Extant | Extant | Extant | Extant | Extant | Extant | Terminated | Terminated | Terminated | Terminated | Terminated | Terminated | Relinquished | Relinquished | Relinquished | Relinquished | Relinquished | Relinquished
| Model Clauses | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 2 (SI 2014 No 1686) | Schedule 2 (SI 2014 No 1686) | Schedule 2 (SI 2014 No 1686) | Schedule 2 (SI 2014 No 1686) | Schedule 2 (SI 2014 No 1686) | Schedule 2 (SI 2014 No 1686) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436) | Schedule 2 (SI 2014 No 1686) | Schedule 3 (SI 1995 No 1436) | Schedule 3 (SI 1995 No 1436)
LOCATION | Local Authority | Wrexham | Bridgend | Neath Port Talbot | Flintshire | Neath Port Talbot | Bridgend | Newport | Flintshire | Swansea | Neath Port Talbot | Bridgend | Vale of Glamorgan | Newport/Monmouth | Wrexham | Wrexham | Wrexham | Wrexham | Vale of Glamorgan | Rhondda Cynon Taf
| Block Number | SJ35a | SN90a, SS99a,b,c | SS78, SS88, SS98 | SJ36a | SN80 | SS89 | ST38a,b | SJ27, SJ28, SJ37 | SS69a | SS79a | SS87a | SS97a | ST48a
TERM DATES | Licence Start Date | 1991-10-01 | 1996-04-04 | 2000-09-08 | 2004-10-01 | 2004-10-01 | 2004-10-01 | 2004-10-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01 | 2008-07-01
| Original Initial Term End Date | 1997-09-30 | 2002-04-03 | 2008-09-07 | 2011-09-30 | 2011-09-30 | 2011-09-30 | 2010-09-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
| 1st Initial Terms Extension End Date | 2008-07-01: 2018-06-30; 2008-07-01: 2018-06-30; 2008-07-01: 2018-06-30; 2008-07-01: 2018-06-30; 2008-07-01: 2018-06-30
| 2nd Initial Terms Extension End Date | 2008-07-01: 2020-06-30; 2008-07-01: 2020-06-30; 2008-07-01: 2020-06-30; 2008-07-01: 2020-06-30; 2008-07-01: 2020-06-30
| Second Term End Date | 2002-09-30 | 2008-04-03 | 2011-09-07 | 2017-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30 | 2019-06-30
| 1st Second Term End Date Extensions | 2008-07-01: 2020-06-30; 2008-07-01: 2022-06-30; 2008-07-01: 2022-06-30; 2008-07-01: 2022-06-30; 2008-07-01: 2022-06-30; 2008-07-01: 2022-06-30
| Licence End Date | 2022-09-30 | 03/04/2027 ) | 2031-09-07 | 2035-09-30 | 2035-09-30 | 2035-09-30 | 2035-09-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30 | 2039-06-30
LICENSEE | Licence Administrator Registered No | 5146688 | 3128509 | 6252743 | 7240286 | 3452019 | 3452019 | 4309298 | 4962079 | 3452019 | 3452019 | 3440732 | 3440732 | 4309298 | 6760557 | 7240286 | 7240286 | 6760557 | 3440732 | 3440732
| Licence Administrator Name | BIOGAS TECHNOLOGY (SAWTRY) LIMITED | ALKANE ENERGY UK LIMITED | ADAMO ENERGY (UK) LIMITED | IGAS ENERGY DEVELOPMENT LIMITED | U.K. METHANE LIMITED | U.K. METHANE LIMITED | SONOREX OIL AND GAS LIMITED | ISLAND GAS LIMITED | U.K. METHANE LIMITED | U.K. METHANE LIMITED | COASTAL OIL AND GAS LIMITED | COASTAL OIL AND GAS LIMITED | SONOREX OIL AND GAS LIMITED | DART ENERGY (WEST ENGLAND) LIMITED | GP ENERGY LIMITED | GP ENERGY LIMITED | DART ENERGY (WEST ENGLAND) LIMITED | COASTAL OIL AND GAS LIMITED | COASTAL OIL AND GAS LIMITED
| Licensee Name | BIOGAS TECHNOLOGY (SAWTRY) LIMITED | ALKANE ENERGY UK LIMITED | ADAMO ENERGY (UK) LIMITED & COASTAL OIL AND GAS LIMITED | IGAS ENERGY DEVELOPMENT LIMITED & INEOS UPSTREAM LIMITED | U.K. METHANE LIMITED | U.K. METHANE LIMITED | SONOREX OIL AND GAS LIMITED | INEOS UPSTREAM LIMITED & ISLAND GAS LIMITED | ADAMO ENERGY (UK) LIMITED & U.K. METHANE LIMITED | ADAMO ENERGY (UK) LIMITED & U.K. METHANE LIMITED | ADAMO ENERGY (UK) LIMITED & COASTAL OIL AND GAS LIMITED | ADAMO ENERGY (UK) LIMITED & COASTAL OIL AND GAS LIMITED | SONOREX OIL AND GAS LIMITED | GDF SUEZ E&P UK LTD | GP ENERGY LIMITED | GP ENERGY LIMITED | DART ENERGY (WEST ENGLAND) LIMITED & INEOS UPSTREAM LIMITED | COASTAL OIL AND GAS LIMITED | COASTAL OIL AND GAS LIMITED

## PEDL Changes June 2016 WALES
Licence Ammendments
|  |  |  | Oil and Gas Authority |  | Welsh Government as Licensing Authority
|  |  |  | 2016-07-01 | 2018-07-09 | 06/02/2019 | 01/07/2019 | 2020-06-30 | 2020-10-08 | 2020-03-24
Current Licence Status | Licnece Number | Operator | Work Programme at Issue | Conversion to 2014 Model Clauses, extension of time or Retention Area Ammendments | Retention Area Ammendments and Term Extensions | Retention Area Ammendments | Term Extensions | Licence Terminations | Retention Area Terminations | Well Abandonment
Extant | EXL203 | BIOGAS TECHNOLOGY (SAWTRY) LIMITED | The Licensee shall in respect of Blocks SJ35, SJ36a, SJ37, SJ47b, SJ48c and SJ46: i) By the 30th September 1998 complete a remote sensing study by means of High Altitude Aerial Photography and Landsat Infrared Satellite Imagery to identify geological and geomorphological features indicative of areas of enhanced permeability, and ii) By December 31 1999 drill not less than one exploration well to a depth not less than the deepest prospective coal seam in the licence area. | [6 empty] | 24/03/2020 Consent granted for well-abandonment
Extant | PEDL014 | ALKANE ENERGY UK LIMITED | The licensee shall in respect of blocks SN90, SO00, SO10, SS99 and ST09: i) Analyses and test gas vents which are present in the licence area within 2 years of the award of the licence; ii) Drill not less than one exploration well in block SS99 and not less than one exploration well in block ST09 within 4 years of the award of the licence. These wells shall be drilled to not less than the depth of the deepest prospective coal seam, and iii) Drill not less than one further exploration well within 6 years of the award of the licence, if the licensee is satisfied that the results obtain from drilling the exploration wells in blocks SS99 and ST09 are adequate for the well to proceed. If the licensee considers that the results are not adequate for the well to proceed, it shall inform the Secretary of State of its reasons for reaching this conclusion.
Extant | PEDL100 | UK Onshore | The licensee shall in respect of Block SS78: i) Drill one gob gas well to 300m within 2 years of the date of commencement of the licence, provided that the licensee shall not be required to drill the said well if the licensee satisfies the Minister that the drilling of the well is not justifiable having regard to the technical information available at the time: ii) Drill one coal bed methane well to 850m within 2 years of the date of commencement of the licence, provided that the licensee shall not be required to drill the said well if the licensee satisfies the Minister that the drilling of the well is not justifiable having regard to the technical information available at the time: The licensee shall in respect of Block SS88: iii) Drill one coal bed methane well to 650m within 3 years of the date of commencement of the licence, provided that the licensee shall not be required to drill the said well if the licensee satisfies the Minister that the drilling of the well is not justifiable having regard to the technical information available at the time: iv) Drill one coal bed methane well to 750m within 3 years of the date of commencement of the licence, provided that the licensee shall not be required to drill the said well if the licensee satisfies the Minister that the drilling of the well is not justifiable having regard to the technical information available at the time: The licensee shall in respect of Block SS98: v) Drill two coal bed methane wells to 550m within 2 years of the commencement of the licence; vi) Drill one coal bed methane well to 350m within 2 years of the date of commencement of the licence, provided that the licensee shall not be required to drill the said well if the licensee satisfies the Minister that the drilling of the well is not justifiable having regard to the technical information available at the time. | Conversion to 2014 Model Clause and Retention Area work plan agreed: two retention areas: RA1 Llangeinor Area - East- submit a planning application for field development activity by 30 Sept 2017 and submit an updated Field Development Plan by 30 September 2019 and RA2 Margam Area - West - re-process British Coal seismic data by 30 June 2017, submit a planning application for field development activity by 30 Sept 2017 and submit a Field Development Plan by 30 June 2019. | Retension Area Ammended: two retention areas: RA1 Llangeinor Area - East- submit a planning application for field development activity by 30 Sept 2019 and submit an updated Field Development Plan by 30 September 2021 and RA2 Margam Area - West - re-process British Coal seismic data by 30 June 2019, submit a planning application for field development activity by 30 Sept 2019 and submit a Field Development Plan by 30 June 2021. |  |  |  | Retention Area Ammended
Extant | PEDL147 | IGAS | DRILL-OR-DROP WORK PROGRAMME Part 1 No commitment Part 2: The Licensee shall drill one vertical and three deviated horizontal wells. | Conversion to 2014 Model Clause and Retention Area work plan agreed: acquire new 3D seismic data by 30 June 2020 and drill a well by 30 June 2021. |  | 30/01/2019 • Geographical Location: The whole of the licence area which is located in Wales • Proposed Expiry Date: June 2023 • Proposed Work programme: 3D Seismic Acquisition by June 2022 Commitment to drill removed.
Extant | PEDL148 | UK Onshore | DRILL-OR-DROP WORK PROGRAMME Part 1 No commitment Part 2: The Licensee shall drill one well. | Conversion to 2014 Model Clause and Retention Area work plan agreed: two retention areas: RA1 Seven Sisters Area - West - submit planning permission for field development activity by 30 Sept 2017 and submit a Field Development Plan by 30 September 2019 and RA2 Banwen Area - East - submit planning permission for field development activity by 30 Sept 2017 and submit Field Development Plan by 30 September 2019 | Retension Area Ammended: two retention areas: RA1 Seven Sisters Area - West - submit planning permission for field development activity by 30 Sept 2019 and submit a Field Development Plan by 30 September 2021 and RA2 Banwen Area - East - to submit planning permission for field development activity by 30 Sept 2019 and submit Field Development Plan by 30 September 2021 |  |  |  | Retention Area Ammended
Extant | PEDL149 | UK Onshore | DRILL-OR-DROP WORK PROGRAMME Part 1 No commitment Part 2: The Licensee shall drill one well. | Conversion to 2014 Model Clause and Retention Area work plan agreed: two retention areas: RA1 Bryn Area - West - submit a planning application for field development activity by 30 Sept 2017 and to submit a Field Development Plan by 30 September 2019 and RA2 St Johns Area - East - submit a further planning application for field development activity by 30 Sept 2017 and to submit a Field Development Plan by 30 June 2018 | Retension Area Ammended: two retention areas: RA1 Bryn Area - West - submit a planning application for field development activity by 30 Sept 2019 and to submit a Field Development Plan by 30 September 2021 and RA2 St Johns Area - East - submit a further planning application for field development activity by 30 Sept 2019 and to submit a Field Development Plan by 30 June 2020 |  |  |  | Retention Area Ammended
Extant | PEDL157 | Sonorex | Firm commitment The Licensee shall obtain 50km of 2D seismic data. | Conversion to 2014 Model Clause and Retention Area work plan agreed: drill one well by 30 Sept 2017 and submit a Field Development Plan by 30 September 2019 EXTRA ONE YEAR EXTENSION for drilling | Retension Area Ammended: drill one well by 30 Sept 2019 and submit a Field Development Plan by 30 September 2021 |  |  |  | Retention Area Ammended
Terminated | PEDL184 | IGas | Firm commitments The Licensee shall: obtain 56km of 2D seismic data on Blocks SJ28 and SJ27; obtain 35km of 2D seismic data on Block SJ37; and drill one well to a depth of 580m. | Conversion to 2014 Model Clause and Retention Area work plan agreed: reprocess regional geomagnetic data by 30 June 2017, sample and reinterpret Namurian shale from Gronant borehole by 30 March 2018, acquire new seismic data by 30 June 2019 and drill a well by 30 June 2021 |  | Geographical Location: The whole of the licence area which is located in Wales • Proposed Expiry Date: June 2023 • Proposed Work programme: 3D Seismic Acquisition by June 2022 Commitment to drill removed. | Licence Terms extensions: Second Term - 30 June 2020 | Licence Terminated
Terminated | PEDL188 | IGas | Firm commitments The Licensee shall: obtain 20km of 2D seismic data; reprocess 10km of 2D seismic data; and drill two wells to a depth of 750m. | Conversion to 2014 Model Clause and Retention Area work plan agreed: acquire new 2D seismic data by 30 June 2020 and drill a well by 30 June 2021
Terminated | PEDL214 | U.K. Onshore | Firm commitments The Licensee shall: obtain 22km of 2D seismic data; and drill one well to a depth of 800m. | Two year extension to Initial Term, partial relinquishment of 74 km2 was made | Licence Terms extensions: Initial Term- 30 June 2020 Second Term – 30 June 2022 |  |  | Licence Terminated
Terminated | PEDL215 | U.K. Onshore | Firm commitments The Licensee shall: obtain 9km of 2D seismic data; and drill one well to a depth of 800m. | Two year extension to Initial Term, partial relinquishment of 60 km2 was made | Licence Terms extensions: Initial Term- 30 June 2020 Second Term – 30 June 2022 |  |  | Licence Terminated
Terminated | PEDL216 | U.K. Onshore | PART I Firm commitment The Licensee shall obtain 5km of 2D seismic data. PART II Drill-or-drop commitment The Licensee shall either: drill one well to a depth of 1500m, or elect to allow the licence to automatically cease and determine pursuant to Clause 3. | Two year extension to Initial Term, partial relinquishment of 22 km2 was made | Licence Terms extensions: Initial Term- 30 June 2020 Second Term – 30 June 2022 |  |  | Licence Terminated
Terminated | PEDL217 | U.K. Onshore | PART I Firm commitment The Licensee shall obtain 7.5km of 2D seismic data. PART II Drill-or-drop commitment The Licensee shall either: drill one well to a depth of 1500m, or elect to allow the licence to automatically cease and determine pursuant to Clause 3. | Two year extension to Initial Term, partial relinquishment of 41 km2 was made | Licence Terms extensions: Initial Term- 30 June 2020 Second Term – 30 June 2022 |  |  | Licence Terminated
Terminated | PEDL224 | Sonorex | PART I Firm commitment The Licensee shall reprocess 12km of 2D seismic data. PART II Drill-or-drop commitment The Licensee shall either: drill one well, or elect to allow the licence to automatically cease and determine pursuant to Clause 3. | One year extension to Initial Term, Partial relinquishment of 39 km2 was made | Licence Terms extensions: Initial Term- 30 June 2020 Second Term – 30 June 2022 |  |  | Licence Terminated
Relinquished | PEDL185 | IGas | Firm commitments The Licensee shall: obtain 40km of 2D seismic data; reprocess 20km of 2D seismic data. drill one well on Block SJ33 to a depth of 600m; and drill one well on Block SJ44 to a depth of 800m. | Licence Ended
Relinquished | PEDL186 | IGas | Firm commitment The Licensee shall: obtain and reprocess 140km of 2D seismic data; and drill two wells to a depth of 1300m. | Licence Ended
Relinquished | PEDL187 | IGas | Firm commitments The Licensee shall: obtain and reprocess 75km of 2D seismic data; and drill two wells to a depth of 1100m. | Licence Ended
Relinquished | PEDL219 | U.K. Onshore | Obtain 7.5km of 2D Seismic Drill one well to a depth of 1500m | Licence Ended
Relinquished | PEDL220 | U.K. Onshore | Drill one well to a depth of 800m | Licence Ended

## Plan and Permit Status
2021-06-21
|  | Planning Application | [8 empty] | Permit Application
PEDL | Operator | Local Authority | Planning Application Number | Proposed Location | Proposed Activity | Application Type | Application Status | Decision Details | Expiry Date | Committee | Issue Date | Permit Number | License/Activity Type
PEDL157 | SONOREX OIL AND GAS LTD | Newport | 17/1215 | West Nash Road, Nash | Variation of conditions 01 (implementation time) and 19 (buffer zones) of planning permission 11/1351 for the construction of temporary oil/gas exploration drilling site and associated works, the creation of perimeter bund, vehicular access, and the siting of drilling rig | Renewals and Variation of Conditions | Granted with Conditions | 5 year extension. The development to which this permission relates must be begun not later than the expiration of FIVE YEARS from the date of this permission. | 2023-03-29 | Delegated decision | 2015-06-30 | EPR/NB3593HJ/A001 (CONVENTIONAL) | A1- Mining Waste Operation A2- Flaring Activity Discharge of integral site drainage
PEDL216 | COASTAL OIL AND GAS LIMITED | Bridgend | P/19/862/RLX | Field to the west of unnamed road between A48 Bypass and Merthyr Mawr off Tyla Lane Merthyr Mawr Bridgend CF32 0LT | Vary the standard time condition on P/13/322/FUL (drill an exploration borehole to test for Devonian strata) to extend the consent for a further 5 years | Remove/vary condition/s | Granted with Conditions | 5 year extension. | 2025-01-14 | Officer | 2015-07-15 | EPR/JB3993HS/A001 | A1- Mining Waste Operation without a Mining Waste Facilityy
PEDL214 | UK Methane Limited | Swan | 2015/1515 | Bryntywod Road, near Llangyfelach, north-east of Morriston. | Drilling of an appraisal borehole for the purpose of coal bed methane exploration with associated equipment, drilling rig, site cabins and offices. | Full - no ES | Approved | 5 year planning permmision | 2020-12-14 | Committee
PEDL157 | SONOREX OIL AND GAS LTD | Newport | 11/1351 | West Nash Road, Nash | Construction of temporary oil/gas exploration drilling site and associated works, the creation of perimeter bund, vehicular access, and including the siting of drilling rig | Full+Env Statement | Granted with Conditions | 5 year planning permmision | 2017-09-07 | Committee decision | 2015-06-30 | EPR/NB3593HJ/A001 (CONVENTIONAL) | A1- Mining Waste Operation A2- Flaring Activity Discharge of integral site drainage
PEDL215 | UK Methane Limited | NPT | P2015/0031 | Land within Foel Fynyddau Forest Near Pontrhydyfen Cwmavon | Temporary permission for the drilling of an exploratory borehole to test the Westphalian and Namurian strata for coal bed methane and shale gases. | Full - no ES | Full Plans Approved | 5 yearplanning permmision | 2020-03-18 | Committee Decision | 2016-01-27 |  | A30: Mining Waste Operation without a Mining Waste Facility.
PEDL216 | COASTAL OIL AND GAS LIMITED | Bridgend | P/13/322/FUL | Field to the west of unnamed road between A48 Bypass and Merthyr Mawr off Tyla Lane Merthyr Mawr Bridgend CF32 0LT | Drill an exploration borehole to test the devonian strata | Full - no ES | APPROVED +conditions | 5 year planning permmision | 2019-12-12 | Committee Decision | 2015-07-15 | EPR/JB3993HS/A001 | A1- Mining Waste Operation without a Mining Waste Facilityy
PEDL217 | Coastal Oil and Gas Limited, | VOG | 2013/00334/FUL | LANDOW (2) Unit 20, Sutton Spring Road, Llandow (2)Trading Estate | To drill a single vertical exploration borehole | Full - no ES | Approved | 5 yearplanning permmision | 2018-10-04 | Committee | 2015-07-15 | EPR/RB3593HS/A001 | A1- Mining Waste Operation without a Mining Waste Facility
PEDL187 | GP Energy ltd | Wrexham | P/2013/0660 | Part Of Field West Of Commonwood Farm And South Of Borras Road | Drilling Of Exploration Borehole (Requiring 24 Hour Operations) To Remove A Core Of Coal For Sampling And Site Restoration Following Cessation Of Drilling Operations. Drilling Operations To Take Approximately 60 Days And A Maximum Of 75 Days |  | Approved on APPEAL - Inspector appointed by Welsh Government | 5 year planning permmision | 2019-10-08 |  | 2014-06-05 | EA/EPR/MB3993HU/A001 | A30: Mining Waste Operations
PEDL219 | Coastal Oil and Gas Limited, | VOG | 2013/00333/FUL | ST NICHOLAS Site located in field 400m along an unnamed road between the A4266 and Duffryn (grid ref 308215 : 171623) | Drill a single vertical exploration borehole | Full - no ES | Approved | 5 year planning permmision | 2018-10-04 | Committee | 2015-09-04 | EPR/JB3593HA/A001 | A1- Mining Waste Operation without a Mining Waste Facility
PEDL149 | UK METHANE LIMITED | Bridgend | P/12/718/FUL | St johns colliery Maesteg Bridgend CF34 0DH | Drill 3 boreholes to abandoned workings at st johns colliery & generate electricity | Full - no ES | APPROVED temporarily | 5 year planning permmision | 2018-01-10 | Committee
PEDL220 | Coastal Oil and Gas | RCT | 15/0147/10 | Land next to farm access track at Hendre Owen Farm, Llanharan | Drill an exploratory borehole to test for unconventional gas reserves in the Westphalian and Namurian strata | Full - no ES | Pending Decision / Committee minded to refuse - APPEAL submitted 07/03/16 APEEAL WITHDRAWN | REFUSED - the proposal is out of accord with LDP Policies AW5, AW8 and AW12 insofar as there is an unacceptable effect on the interest of residential amenity, cultural heritage and landscape importance. |  | Committee
PEDL100 | COASTAL OIL AND GAS | Bridgend | P/11/503/FUL | Cwmcedfyw Farm Pontrhydycyf Bridgend cf34 0eb | Capture of coal bed methane utilising a portable generator & connecting to overhead lines | Full - no ES | APPROVED +conditions | 5 year planning permission | 2018-10-26 | Committee
PEDL149 | UK METHANE LIMITED | Bridgend | P/11/12/FUL | Former St Johns colliery Maesteg Bridgend cf34 0dh | Drill and test the insitu namurian shale and associated strata | Full - no ES | APPROVED +conditions | 5 year planning permission | 2016-04-08 | Committee
PEDL014 | ALKANE ENERGY UK LTD | Bridgend | P/11/187/FUL | PLOT 1A Ffaldau industrial estate Victoria street Pontycymmer | Retain exploratory borehole, erect containerised units, associated plant & equipment & ancillary operations | Full - no ES | APPROVED +conditions | 5 year planning permission | 2016-07-01 | Committee
PEDL148 | UK METHANE LIMITED | NPT | P2010/1183 | Land east of Banwen adjacent intervalley road Neath | Construction of a compound for gas exploration including, offices, toilets, fuel store, generators, parking area drilling rig and associated drilling equipment for a temporary period of 12 weeks. (Additional Information Received 6/6/11) | Full - no ES | Full Plans Approved | 5 year planning permission | 2016-07-19 | Delegated decision
PEDL220 | Coastal Oil and Gas | RCT | 12/1253/10 | Field on the left hand side of Pantybrad road, north of Llantrisant | Drill an exploration borehole to test for unconventional gas reserves in the Westphalian and Namurian strata | Full - no ES | Decided | 5 year planning permission | 2013-10-10 | Committee
PEDL219 | Coastal Oil and Gas | VOG | 2013/00335/FUL | Llantrithyd Land on the west side of the road leading from Llancarfan to Bonvilston (Grid ref. 305209:172962) | Drill an exploration borehole to test for gas reserves | Full - no ES | Approved | 5 yearplanning permmision | 2018-10-04 | Committee
PEDL217 | Coastal Oil and Gas | VOG | 2011/00812/FUL | Unit 1, Llandow Industrial Estate, Llandow | Drill and test the insitu lower limestone and associated strata for the presence of gas | Full - no ES | Refused | 5 year planning permission | 2016-10-21 | Committee
PEDL217 | Coastal Oil and Gas | VOG | 11/2167112 | Unit 1, Llandow Industrial Estate, Llandow | Drill and test the insitu lower limestone and associated strata for the presence of gas | appeal | allowed | 5 year planning permission | 2017-07-06 | Planning Inspector
PEDL214 | UK Methane Limited | Swan | 2012/1427 | Llys Nini Animal Centre Pontarddulais Road Penllergaer Swansea SA4 9WB | Drilling of an appraisal borehole for the purpose of coal bed methane exploration | Full - no ES | Grant Permission Conditional | 5 year planning permmision | 2018-02-01 | Committee