## Commitment & Spend
Table 1: Allocation, Spend & Commitment
£ Millions
Allocation |  | Committed1 |  |  |  | Spend
TOTAL | EAFRD | TOTAL |  | EAFRD |  | TOTAL |  | EAFRD
842 | 562 | 873.8381 | 103.8% | 582 | 103.6% | 750.28 | 89.11% | 509.1149 | 90.59%
Source: RD&S, 30-04-2023
1The Wales Rural Development Programme 2014-2020 is fully committed; as part of the contingency planning ,an element of over-programming has been factored into the overall financial budgeting to achieve a successful programme delivery.

## Priority 1
Priority 1: Fostering knowledge transfer and innovation in agriculture, forestry, and rural areas
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 1a | 1 | Total public expenditure | 91.29 | 92.14 | 85.2207
| 2 | Total public expenditure | 14.3224 | 14.0363 | 14.0363
| 16 | Total public expenditure | 108.4594 | 89.8448 | 89.3901
FA 1b | 16.1 | Number of EIP operational groups supported | 45 | 46 | 46
| 16.2 - 16.9 | Number of cooperation operations supported (non EIP) | 433 | 235 | 143
FA 1c | 1.1 | Number of participants in trainings | 33716 | 97527 | 97527
Source: RD&S, 30-04-2023

## Priority 2
Priority 2: Enhancing competitiveness and farm viability of all types of agriculture, promoting innovative farm technologies and the sustainable management of forests
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 2a | 1.1 | Number of participants in trainings | 10010 | 17262.63 | 17262.63
| 1.1 | Number of training days given | 8008 | 13069.4651 | 13069.4651
| 1.1 | Total public expenditure for training / skills | 3.8307 | 4.6777 | 4.6777
| 1.2 | Number of demonstration operations / information actions supported | 1395.24 | 5025.02 | 5025.02
| 1.3 | Number of farm exchanges operations supported | 39 | 87.01 | 87.01
| 1.1 -1.3 | Total public expenditure | 30.4023 | 42.65 | 30.2054
| 2.1 | Number of beneficiaries advised | 2963 | 5946.2991 | 5946.2991
| 2.1 - 2.2 | Total public expenditure | 7.6042 | 7.5016 | 7.5016
| 4.1 | Number of holdings supported | 2431 | 4248 | 3616
| 4.1 | Total public expenditure | 36.7456 | 39.399 | 24.8227
| 4 | Total investment | 91.9139 | 98.4976 | 62.0567
| 4 | Total public expenditure | 36.7956 | 39.399 | 24.8227
| 16 | Total public expenditure | 13.8664 | 0.49871 | 0.43457
Source: RD&S, 30-04-2023

## Priority 3
Priority 3: Promoting food chain organisation and risk management in agriculture
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 3a | 1.1 | Number of participants in trainings | 16996 | 75304.95 | 75304.95
| 1.1 | Number of training days given | 11211 | 26922.4866 | 26922.4866
| 1.1 | Total public expenditure for training / skills | 48.2084 | 42.7105 | 42.7105
| 1.2 | Number of demonstration operations / information actions supported | 90.6 | 326.3 | 326.3
| 1.1 -1.3 | Total public expenditure | 49.9338 | 44.3681 | 44.3681
| 2.1 | Number of beneficiaries advised | 303 | 608.94 | 608.94
| 2.1 - 2.2 | Total public expenditure | 0.77872 | 0.86 | 0.76822
| 4.2 | Number of operations supported | 120 | 111 | 111
| 4 | Total investment | 125.1543 | 183.3374 | 145.0705
| 4 | Total public expenditure | 50.0617 | 53.2031 | 45.7502
| 16.4 | Number of agricultural holdings supported | 165 | 184 | 184
| 16 | Number of cooperation operations supported (non EIP) | 165 | 15 | 15
| 16 | Total public expenditure | 32.0634 | 9.8969 | 3.0098
Source: RD&S, 30-04-2023

## Priority 4
Priority 4: Restoring, preserving and enhancing ecosystems dependent on agriculture and forestry
Priority | Measure | Outputs | Target | Forecast | Achieved to Date
Priority 4 Agricultural Land | 1.1 | Number of participants in trainings | 1376 | 1793.52 | 1793.52
| 1.1 | Number of training days given | 2092 | 1357.8665 | 1357.8665
| 1.1 | Total public expenditure for training / skills | 0.83786 | 3.5008 | 3.5008
| 1.2 | Number of demonstration operations / information actions supported | 144.96 | 522.08 | 522.08
| 1.3 | Number of farm exchanges operations supported | 4 | 9.04 | 9.04
| 1.1 -1.3 | Total public expenditure | 3.5985 | 6.1531 | 6.1531
| 2.1 | Number of beneficiaries advised | 1684 | 1522.35 | 1522.35
| 2.1 - 2.2 | Total public expenditure | 2.0123 | 2.6697 | 2.6697
| 4.4 | Number of operations supported | 11120 | 11120 | 9794
| 4 | Total investment | 47.6834 | 58.0565 | 47.6358
| 4 | Total public expenditure | 47.6834 | 58.0565 | 47.6358
| 8.1 | Total area (ha) supported | 2498 | 8424.82 | 1971.55
| 8.1 | Total public expenditure | 21.1713 | 12.251 | 9.3613
| 8.2 | Total area (ha) supported | 50 | 45 | 1.47
| 8.2 | Total public expenditure | 0.01 | 0.002502 | 0.002532
| 10.1 | Total area (ha) supported | 635399 | 1819280.52 | 691801.43
| 10.1 | Physical area (ha) supported | 635399 | 1264835.92 | 752849.05
| 10.1 | Number of contracts supported | 7337.55 | 5362 | 4829
| 10.1 | Total public expenditure | 274.9168 | 251.9249 | 251.9249
| 11.1 | Number of holdings supported | 201 | 175 | 131
| 11.1 | Total area (ha) supported | 11153 | 15018 | 9915.36
| 11.2 | Number of holdings supported | 341 | 561 | 536
| 11.2 | Total area (ha) supported | 57287 | 128023.87 | 64353.38
| 11 | Total public expenditure | 33.192 | 28.9997 | 28.9997
| 16 | Number of cooperation operations supported (non EIP) | 25 | 32.8578 | 32.8578
| 16 | Total public expenditure | 14.9947 | 17.3727 | 12.1376
Priority 4 Forest Area | 1.1 | Number of participants in trainings | 274 | 224.19 | 224.19
| 1.1 | Number of training days given | 644 | 169.7333 | 169.7333
| 1.1 | Total public expenditure for training / skills | 0.23826 | 0.43755 | 0.43755
| 1.2 | Number of demonstration operations / information actions supported | 18.12 | 65.26 | 65.26
| 1.3 | Number of farm exchanges operations supported | 0.5 | 1.13 | 1.13
| 1.1 -1.3 | Total public expenditure | 0.58335 | 0.76905 | 0.76905
| 2.1 | Number of beneficiaries supported | 851 | 101.49 | 101.49
| 2.1 - 2.2 | Total public expenditure | 1.1037 | 0.33367 | 0.33367
| 8.3 | Number of beneficiaries supported | 1 | 1 | 1
| 8.3 | Total area (ha) supported | 76000 | 306000 | 306000
| 8.3 | Total public expenditure | 0.040982 | 0.18128 | 0.16393
| 8.5 | Number of operations supported | 403 | 1101 | 561
| 8.5 | Total area (ha) supported | 8400 | 7875 | 3647.95
| 8.5 | Total public expenditure | 2.9957 | 4.3573 | 4.3468
| 16 | Number of cooperation operations supported (non EIP) | 12 | 13.1422 | 3.7547
| 16 | Total public expenditure | 5.9639 | 7.1882 | 4.8547
Source: RD&S, 30-04-2023

## Priority 5
Priority 5: Promoting resource efficiency and supporting the shift towards a low carbon and climate resilient economy in agriculture, food and forestry sectors
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 5b | 1.1 | Number of participants in trainings | 260 | 448.38 | 448.38
| 1.1 | Number of training days given | 208 | 339.4666 | 339.4666
| 1.1 | Total public expenditure for training / skills | 0.099498 | 0.12291 | 0.12291
| 1.2 | Number of demonstration operations / information actions supported | 36.24 | 130.52 | 130.52
| 1.3 | Number of farm exchanges operations supported | 1 | 2.26 | 2.26
| 1.1 -1.3 | Total public expenditure | 0.78967 | 1.11 | 0.78597
| 2.1 | Number of beneficiaries advised | 83 | 167.4585 | 167.4585
| 2.1 - 2.2 | Total public expenditure | 0.21415 | 0.24 | 0.21126
| 4.1 - 4.3 | Number of operations supported | 286 | 1699 | 1669
| 4 | Total investment | 20.3145 | 13.3188 | 13.3188
| 4 | Total public expenditure | 6.6198 | 5.3275 | 5.3275
| 16 | Total public expenditure | 0.2471 | 0.24701 | 0.21729
FA 5c | 1.1 | Number of participants in trainings | 260 | 448.38 | 448.38
| 1.1 | Number of training days given | 208 | 339.4666 | 339.4666
| 1.1 | Total public expenditure for training / skills | 0.099498 | 0.12291 | 0.12291
| 1.2 | Number of demonstration operations / information actions supported | 36.24 | 130.52 | 130.52
| 1.3 | Number of farm exchanges operations supported | 1 | 2.26 | 2.26
| 1.1 -1.3 | Total public expenditure | 0.78967 | 1.11 | 0.78597
| 2.1 | Number of beneficiaries advised | 66 | 131.937 | 131.937
| 2.1 - 2.2 | Total public expenditure | 0.16872 | 0.19 | 0.16645
| 7.2 | Number of operations supported | 197 | 5 | 4
| 7 | Total investment | 6.2158 | 9.8963 | 0.35908
| 7 | Total public expenditure | 5.1799 | 3.9585 | 0.27741
| 8.6 | Number of operations supported | 100 | 18 | 18
| 8.6 | Total investment | 14.6171 | 14.5 | 2.6568
| 8.6 | Total public expenditure | 5.8469 | 5.8 | 1.1003
| 16 | Number of cooperation operations supported (non EIP) | 1 | 0 | 0
| 16 | Total public expenditure | 1.0873 | 0.55666 | 0.21729
FA 5d | 1.1 | Number of participants in trainings | 260 | 448.38 | 448.38
| 1.1 | Number of training days given | 208 | 339.4666 | 339.4666
| 1.1 | Total public expenditure for training / skills | 0.099498 | 0.12291 | 0.12291
| 1.2 | Number of demonstration operations / information actions supported | 36.24 | 130.52 | 130.52
| 1.3 | Number of farm exchanges operations supported | 1 | 2.26 | 2.26
| 1.1 -1.3 | Total public expenditure | 0.78967 | 1.11 | 0.78597
| 2.1 | Number of beneficiaries advised | 588 | 1179.3138 | 1179.3138
| 2.1 - 2.2 | Total public expenditure | 1.5081 | 1.67 | 1.4878
| 4.1, 4.3 + 4.4 | Number of operations supported | 4893 | 2218 | 1644
| 4 | Total investment | 19.941 | 30.7896 | 30.7896
| 4 | Total public expenditure | 8.0116 | 12.3159 | 12.3159
| 10.1 | Total area (ha) supported | 59807.08 | 148731.06 | 90364.11
| 10.1 | Total public expenditure | 11.9369 | 12.3322 | 10.891
| 16 | Total public expenditure | 1.4478 | 0.24701 | 0.21729
FA 5e | 1.1 | Number of participants in trainings | 260 | 448.38 | 448.38
| 1.1 | Number of training days given | 208 | 339.4666 | 339.4666
| 1.1 | Total public expenditure for training / skills | 0.099498 | 0.12291 | 0.12291
| 1.2 | Number of demonstration operations / information actions supported | 36.24 | 130.52 | 130.52
| 1.3 | Number of farm exchanges operations supported | 1 | 2.26 | 2.26
| 1.1 -1.3 | Total public expenditure | 0.78967 | 1.11 | 0.78597
| 2.1 | Number of beneficiaries advised | 326 | 153.2499 | 153.2499
| 2.1 - 2.2 | Total public expenditure | 0.50034 | 0.47127 | 0.47127
| 4.4 | Number of operations supported | 7857 | 2880 | 2077
| 4 | Total investment | 4.7767 | 2.9063 | 2.9063
| 4 | Total public expenditure | 4.7767 | 2.9063 | 2.9063
| 8.1 | Total area (ha) supported | 832 | 2237.3 | 565.17
| 8.1 | Total public expenditure | 4.9938 | 6.4266 | 6.4266
| 8.2 | Total area (ha) supported | 50 | 0 | 0
| 8.2 | Total public expenditure | 0.007 | 0.03 | 0
| 8.3 | Number of beneficiaries supported | 0.75 | 0 | 0
| 8.3 | Total area (ha) supported | 225000 | 0 | 0
| 8.3 | Total public expenditure | 0.12295 | 0.36459 | 0
| 8.4 | Number of beneficiaries supported | 159 | 369 | 197
| 8.4 | Total area (ha) supported | 848 | 2051 | 1202.82
| 8.4 | Total public expenditure | 5.0039 | 3.7889 | 3.7889
| 8.5 | Number of operations supported | 393 | 176 | 176
| 8.5 | Total area (ha) supported | 4900 | 1351 | 663.52
| 8.5 | Total public expenditure | 2.3647 | 0.1936 | 0.1936
| 10.1 | Physical area (ha) supported | 3021.6 | 2211.03 | 2211.03
| 10.1 | Total public expenditure (£'m) | 0.68125 | 1.7672 | 1.7672
| 16 | Number of cooperation operations supported (non EIP) | 2 | 1 | 1
| 16 | Total public expenditure | 0.28006 | 0.497 | 0.28122
Source: RD&S, 30-04-2023

## Priority 6
Priority 6: Promoting social inclusion poverty reduction and economic development in rural areas
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 6a | 2.1 | Number of beneficiaries advised | 168 | 337.9617 | 337.9617
| 2.1 - 2.2 | Total public expenditure | 0.43219 | 0.48 | 0.42636
| 6.4 | Number of beneficiaries supported | 340 | 41 | 41
| 6 | Total investment | 19.3558 | 43.7719 | 4.9505
| 6 | Total public expenditure | 7.7423 | 17.5088 | 5.176
| 8.6 | Number of operations supported | 20 | 56 | 55
| 8.6 | Total investment | 2.922 | 15.5227 | 13.8289
| 8.6 | Total public expenditure | 1.1688 | 5.4155 | 5.4155
| 16 | Number of cooperation operations supported (non EIP) | 1 | 2 | 2
| 16 | Total public expenditure | 0.19898 | 2.0989 | 2.0989
| 6.4 + 8.6 | Number of jobs created | 765 | 377.8 | 377.8
FA 6b | 1.1 | Number of participants in trainings | 3890 | 1798 | 924
| 1.1 | Total public expenditure for training / skills | 3.0379 | 0.86393 | 0.18813
| 1.1 -1.3 | Total public expenditure | 3.2186 | 0.86393 | 0.18813
| 7.1 | Number of operations supported | 18 | 11 | 7
| 7.2 | Number of operations supported | 56 | 2 | 2
| 7.4 | Number of operations supported | 116 | 97 | 95
| 7.5 | Number of operations supported | 150 | 31 | 31
| 7.6 | Number of operations supported | 35 | 15 | 15
| 7.7 | Number of operations supported | 25 | 7 | 7
| 7 (exc 7.3) | Population benefiting from improved services / infrastructures | 1381745 | 639362 | 639362
| 7 (exc 7.3) | Total public expenditure | 12.115 | 18.056 | 18.056
| 19 | Number of LAGs selected | 18 | 18 | 18
| 19 | Number of projects supported | 54 | 75 | 75
| 19 | Number of cooperation projects supported | 27 | 56 | 50
| 19 | Population covered by LAG | 1381745 | 1381745 | 1381745
| 19.1 | Total public expenditure | 0.041833 | 0.051185 | 0.051185
| 19.2 | Total public expenditure | 32.3599 | 32.3 | 27.9003
| 19.3 | Total public expenditure | 3.2444 | 3.4 | 2.0198
| 19.4 | Total public expenditure | 10.8347 | 11.8 | 11.2843
| 16 | Number of cooperation operations supported (non EIP) | 214 | 133 | 125
| 16 | Total public expenditure | 38.3098 | 65.9215 | 65.9215
| 7 + 19 | Number of jobs created | 100 | 13 | 13
FA 6c | 1.1 | Number of participants in trainings | 130 | 224.19 | 224.19
| 1.1 | Number of training days given | 104 | 169.7333 | 169.7333
| 1.1 | Total public expenditure for training / skills | 0.049749 | 0.061454 | 0.061454
| 1.1 -1.3 | Total public expenditure | 0.39483 | 0.55 | 0.39298
| 7.3 | Number of operations supported | 16 | 12 | 12
| 7.3 | Population benefiting from new or improved IT infrastructures | 500000 | 18880 | 18880
| 7.3 | Total public expenditure | 1.036 | 0.75913 | 0.75913
Source: RD&S, 30-04-2023

## Technical Assistance
Technical Assistance
Measure | Outputs | Target | Forecast | Achieved to Date
20.1 | Total public expenditure | 31.3339 | 31.1637 | 31.1637
20.2 | Total public expenditure | 5.6661 | 2.3669 | 1.8044
20.2 | Number of thematic and analytical exchanges set up | 25 | 62 | 62
20.2 | Number of NRN communication tools | 230 | 2997 | 2997
20.2 | Number of ENRD activities in which the NRN has participated | 10 | 28 | 28
Source: RD&S, 30-04-2023

## EOIs
Scheme | Number of Scheme Rounds | Scheme Allocation | Applications Recieved | Appraisals Complete | Applications Approved | Total committed to projects | Total Spend
Cooperation & Supply Chain Development Scheme* | 15 | 54712137 | 120 | 120 | 101 | 74483944 | 57359460.27
Co-operative Forest Planning Scheme | 2 | 109891.7628 | 0 | 0 | 0 | 63931.7 | 63931.7
Enabling Wales's Natural Resources Scheme | 2 | 31000000 | 0 | 0 | 0 | 29572994 | 13453402.86
European Innovation Partnership | N/A | 2475000 | 7 | 7 | 1 | 2474679.7 | 2172851.05
Farm & Forestry Infrastructure | N/A | 50000 | 0 | 0 | 0 | 0 | 0
Farm Business Grant Scheme | 9 | 23607843 | 2919 | 2919 | 2359 | 21150754.47 | 20697180.19
Food Business Investment Scheme* | 9 | 50061706 | 152 | 151 | 136 | 56159698.64 | 45750205.15
Knowledge Transfer & Innovation* | N/A | 91290028 | 15 | 15 | 15 | 94373814.31 | 85220677.14
LEADER | N/A | 46480799 | 75 | 75 | 75 | 47424024.62 | 41255635.35
Rural Business Advisory Service* | N/A | 14322407 | 5 | 5 | 5 | 14211326.38 | 14036314.92
Rural Business Investment Scheme* | N/A | 7742314.72 | 2 | 2 | 2 | 6845603.09 | 5175967.76
Rural Community Development Fund* | 7 | 18330781.89 | 225 | 225 | 188 | 19939819.55 | 19092590.64
Sustainable Management Scheme | 5 | 20162336.278 | 52 | 52 | 50 | 23595536.6 | 16340496.85
Sustainable Production Grant | 7 | 27710459 | 73 | 73 | 72 | 27774818.81 | 20758147.22
Technical Assistance | N/A | 37000000 | 8 | 8 | 8 | 36913175 | 32968145.11
Timber Business Investment Scheme | 5 | 7015662.6 | 90 | 90 | 80 | 6942040.56 | 6515820.57
Socio-Economic Total | 61 | 432071366.2508 | 3743 | 3742 | 3092 | 461926161.43 | 380860826.78
Source: RD&S, 30-04-2023
*Figures include Direct Applications
Scheme | Number of Scheme Rounds | Scheme Allocation | Total committed to projects | Total Spend
Forest Monitoring and Risk Management Scheme | N/A | 163927 | 298851.07 | 163927
Glastir Advanced | 4 | 192133026 | 198644126.16 | 171882546.8
Glastir Commons | N/A | 37490097.02 | 39003039.59 | 33247384.12
Glastir Entry | N/A | 99822830.01 | 100147729.01 | 100131977.38
Glastir Organics | 3 | 33192041 | 32387454.11 | 28999686.93
Glastir Small Grants | 9 | 10607802 | 10342410.59 | 10343257.67
Glastir Woodland Creation | 11 | 22480615 | 17271476.97 | 12361627.19
Glastir Woodland Management | N/A | 959900 | 630500 | 653396.71
Glastir Woodland Restoration | 9 | 5003946 | 4976114.4 | 3788859.83
Legacy Schemes | N/A | 8101923 | 8210216.23 | 7846536.27
Agri-Environment Total | 36 | 409956107.03 | 411911918.13 | 369419199.9
Source: RD&S, 30-04-2023