## Annex B
Local Transport Fund - 2022-23 - Financial Report (Annex B)
Local Authority: | Isle of Anglesey County Council
For the period (quarter): | October 2022 to December 2022
Scheme | LTF Funding Allocation | LTF Forecast Outturn | Actual Spend on ledger (include any spend from match funding) | LTF Claimed To Date | LTF Sp | LTF Cl | LTF Sp | LTF Cl | LTF Sp | LTF Cl | LTF Sp | LTF Cl | LTF Sp | LTF Cl
[5 empty] | Quarter 1 | Quarter 1 | Quarter 2 | Quarter 2 | Quarter 3 | Quarter 3 | Quarter 4 | Quarter 4 | Total | Total
Bus Interchange Project | 630000 | 630000 | 30355.56 | 8926 | 0 | 0 | 8926 | 8926 | 21429.56 | 21429.56 | 462293.04 | 462293.04 | 492648.6 | 492648.6
[13 empty] | 0 | 0 | Please select from drop down list
[13 empty] | 0 | 0 | January 2023 to March 2023
[13 empty] | 0 | 0 | April 2022 to June 2022
[13 empty] | 0 | 0 | July 2022 to September 2022
[13 empty] | 0 | 0 | October 2022 to December 2022
[13 empty] | 0 | 0
Total | 630000 | 630000 | 30355.56 | 8926 | 0 | 0 | 8926 | 8926 | 21429.56 | 21429.56 | 462293.04 | 462293.04 | 492648.6 | 492648.6
To be completed by the Project Manager:
Completed By: | [redacted personal information] |  | Date: | 2023-01-15
Signature: | [redacted personal information] |  | Job Title: | Group Engineer - Sustainable & Strategic Transport
How to complete this form
The Project Manager shall complete one form per quarter for all Local Transport Fund schemes for which you received funding in 2022-23
For the Period Ending: please select period from the drop down menu
Scheme Name - name of the scheme the claim relates to
LTF Funding allocation - please refer to the award letter
LTF Claimed to Date - amount of LTF claimed in FY22-23 up to but not including this quarter's claim
LTF SP = Spend, i.e. paid, on ledger charged to LTF
Actual spend on ledger (Col. E) to relate to the current financial year and include spend from LTF AND match funding (where applicable) to end of period indicated in Line 6
Spend up to the period ending to which the report applies to be actual, with the remainder being forecast.
LTF Cl = Claim, i.e. actual or forecast LTF claim made or to be submitted to WG. For columns H to P claim figure to be actual up to previous quarter with remainder being forecast.