## Guidance
How to use the Risk Register Template
As part of your application, you’re asked to complete and upload a Risk Register. This helps you—and us—understand the potential challenges your project might face and how you plan to manage them.
Even if you're not used to risk registers this simple guide will walk you through how to complete the template step by step.
What is a Risk Register?
A risk register is a document that helps you identify and manage things that could go wrong during your project. It’s not a sign you’re expecting failure—it’s a sign that you’re thinking ahead and being realistic and responsible.
1. Risk Category
Before describing each risk, start by selecting a Risk Category. This helps group your risks and shows where challenges might arise in your project.
Here are the main categories to choose from:
1. Project Design / Definition / Planning Risks | [5 empty] | 6. Partners & Subcontractors – Suitability & Reliability
Risks related to unclear goals, poor planning, or unrealistic timelines. | [5 empty] | Risks tied to the quality, experience, or dependability of subcontractors.
Examples: Vague objectives, underestimated delivery time, missing key milestones. | [5 empty] | Examples: Incomplete work, quality concerns, delayed handover.
2. Partner Risks | [5 empty] | 7. Costing Risks
Risks involving your delivery partners or collaborators. | [5 empty] | Risks that arise from cost misestimation or scope creep.
Examples: Partners withdrawing, delays in agreements, unclear roles. | [5 empty] | Examples: Underestimated material costs, unexpected inflation.
3. Resource Risks | [5 empty] | 8. Finance & Tax Risks
Risks related to staffing, equipment, or materials. | [5 empty] | Risks related to funding sources, cash flow, or tax obligations.
Examples: Not enough team capacity, staff turnover, supply chain delays. | [5 empty] | Examples: Delayed funding disbursement, exchange rate changes, VAT issues.
4. Client / Beneficiary Risks | [5 empty] | 9. Environmental Risks
Risks related to the people or communities you serve. | [5 empty] | Risks from environmental factors or sustainability issues.
Examples: Low engagement, difficulty recruiting participants, changing needs. | [5 empty] | Examples: Extreme weather, environmental damage, waste disposal issues.
5. Project Environment (Political / Legal / Regulatory) | [5 empty] | 10. Other / Non-Identified Risks
External risks from changes in laws, politics, or compliance requirements. | [5 empty] | Risks that don’t fit into the categories above but are still important to flag.
Examples: New regulations, visa delays, legal disputes | [5 empty] | Examples: IT failures, cyber threats, reputation risks.
2. Risk Description
Write a short, clear description of a potential risk to your project.
Examples:
Delays in supplier delivery
Key staff member leaving the team
Difficulty recruiting participants
supply chain delays
Budget overruns
Think about risks related to time, budget, resources, delivery, stakeholders, environment, technology, and compliance.
3. Likelihood
Rate how likely it is that this risk will happen. You can use a simple scale:
Low (1) – Unlikely to occur
Medium (3) – Could occur occasionally
High (5) – Likely to occur
4. Impact
Rate how serious it would be if the risk did happen:
Low (1) – Small delays or inconvenience
Medium (3) – Noticeable impact on project delivery or quality
High (5) – Major impact; could threaten project success
5. Mitigation / Response Plan
Explain how you’ll reduce the chance of the risk happening or what you’ll do if it does.
Examples:
Identify backup suppliers
Cross-train staff to cover absences
Begin procurement early
Monitor budget monthly
This shows you’ve thought ahead and have a plan.
6. Further Action (Optional)
If the template has a space for extra comments, you can include things like:
Trigger events (what might signal this risk is about to happen)
Status updates
Related risks
Tips for Filling it Out
Focus on risks that could genuinely affect the delivery or success of your project.
Be honest: we’re not looking for “perfect” projects with zero risk—we’re looking for smart planning.
Register Template Description
Organisation Name | Risk Category | Risk Description | Likely causes of risk | Impact of Risk [1 to 5] | Likelihood of Risk [1 to 5] | Overall Risk [Calculated] | Control/Mitigation Measures | Mitigated Impact [1 to 5] | Mitigated Likelihood [1 to 5] | Mitigated Overall Risk [Calculated] | Further Actions Needed
[Name of you organisation] | [Categorisation of risk] | [Briefly describe the risk—what could go wrong?] | [List the possible reasons this risk might happen.] | [Rate the impact if this risk occurs (1 = Low, 5 = High).] | [Rate how likely this risk is to happen (1 = Unlikely, 5 = Very Likely).] | [Automatic calculation multiplying Impact x Likelihood to get the overall risk score.] | [List the steps taken to reduce or manage the risk.] | [Rate the impact after applying control measures.] | [Rate the likelihood after applying control measures.] | [Automatic calculation multiplying Mitigated Impact x Mitigated Likelihood to get the overall risk score.] | [List any additional actions required to further reduce the risk.]
Common Terms to be Used for Risk Mitigation Strategies:
Decide not to take a risk – AVOID
Decide to accept the risk - ACCEPT
Decide to transfer the risk – SHARE*
Decide to reduce the risk - REDUCE
Note - to “share” a risk includes: transferring the risk, spreading the risk, insuring against the risk.
Risk Scoring Matrix
70%+ - event almost certain to occur in most circumstances | LIKELIHOOD | Probable | 5 | 10 | 15 | 20 | 25 |  | Level | Colour | Score Range
30-70% - event likely to occur in most circumstances |  | Likely | 4 | 8 | 12 | 16 | 20 |  | Low |  | 1 – 4
10-30% - event will possibly occur in some circumstances |  | Possible | 3 | 6 | 9 | 12 | 15 |  | Moderate |  | 5 – 12
1-10% - event unlikely but may occur at some time |  | Unlikely | 2 | 4 | 6 | 8 | 10 |  | High |  | 13 – 19
<1% - event rare and may only occur in exceptional circumstances |  | Rare | 1 | 2 | 3 | 4 | 5 |  | Very High |  | 20 – 25
|  |  | Negligible | Minor | Moderate | Major | Critical
IMPACT
|  |  | Insignificant increase to project time or cost. Barely noticeable impact on project scope or objectives. Minor errors or disruption Trust recoverable with little effort or cost Less than £50,000 | Less than 5% increase to project time or cost. Minor impact on project scope or objectives Some disruption to core activities / customers Trust recoverable at modest cost with resource allocation within budgets £50,000 to £350,000 | 5% to 20% increase to project time or cost. Major impact on project scope or objectives requiring sponsor approval. Disruption to core activities / customers Trust recovery demands cost authorisation beyond existing budgets. £350,000 to £1million | 20% to 50% increase to project time or cost. Impact on project scope or objectives unacceptable to sponsor. Significant disruption to core activities. Key targets missed. Trust recoverable at considerable cost and management attention. Financial cost: 1million to £5million | 50%+ increase to project time/cost. Strategic Aims compromised. Trust severely damaged. Financial cost >£5million

## Risk Register
Project Risk Register
Cells to be completed
Organisation Name | Risk Category | Risk Description | Likely causes of risk | Impact of Risk [1 to 5] | Likelihood of Risk [1 to 5] | Overall Risk [Calculated] | Control/Mitigation Measures | Mitigated Impact [1 to 5] | Mitigated Likelihood [1 to 5] | Mitigated Overall Risk [Calculated] | Further Actions Needed
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0
[6 empty] | 0 |  |  |  | 0