2025 Annual Update Report:

National action plan to prevent the abuse of older people

Year One Progress

(February 2024 – February 2025)

Year Two Actions

(February 2025 – February 2026)

How we have achieved our year one actions and how we plan to continue to address and prevent the types of abuse which older people may be at increased risk.

Published: June 2025

Mae’r ddogfen hon ar gael yn Gymraeg hefyd / This document is also available in Welsh
Rydym yn croesawu gohebiaeth a galwadau ffôn yn Gymraeg / We welcome correspondence and telephone calls in Welsh

© Crown copyright        Digital ISBN 978-1-83715-835-5		WG52189

# Contents Page

Contents Page	2

Ministerial foreword	4

Background and Context	6

Objectives	8

Section 1 Priority areas for action year one update	9

1.1 Self-Neglect Practitioner Guidance	10

1.2 Violence against Women, Domestic Abuse and Sexual Violence (VAWDASV)	11

1.3 Financial abuse	13

1.4 Loneliness, social isolation and older people	14

1.5 Mental capacity - Deprivation of Liberty Safeguards (DoLS)	15

1.6 Dementia	16

Section 2 Priority areas for action year one update Key settings	18

2.1	Care homes	18

2.2	Domiciliary care	19

Section 3 Priority areas for action year one update Key enablers	22

3.1 Unpaid care	22

3.2 Voice	23

3.3 Older people’s rights	25

3.4 Role of LLAIS	27

3.5 Better information sharing	29

3.6 Better digital access	30

3.7 Learning and improving: the impact of our Single Unified Safeguarding Review (SUSR) process	31

3.8 Better data	34

3.9 Training and registering our workforce – Social Care Wales	36

3.10 Awareness raising and communication	38

Section 4 Year Two Actions	39

Year Two and beyond Actions	40

Key Objective 1 Actions	40

Key Objective 2 - Year Two Actions	48

Key Objective 3 – Year Two Actions	50

# Ministerial foreword

Wales stands proudly at the forefront of tackling abuse of older people with our groundbreaking National Plan—the first of its kind in the UK. One year into this vital work, we've laid strong foundations while recognising the significant journey still ahead.

This first annual report showcases our initial achievements and unveils our reshaped strategy for year two. We've strengthened our approach through collaborative partnerships and refined our methodology to drive measurable impact.

Work has commenced on the successor to the Dementia Action Plan, guided by evaluation findings and stakeholder engagement. A Resident Wellbeing Toolkit has been developed in partnership with Age Cymru to ensure that care home residents can express their needs throughout their care journey. The Carers Support Fund successfully delivered payments to 11,687 carers in 2024/25. To strengthen public engagement, the Code of Practice for Llais was published, enhancing access, involvement, and influence over service design. In terms of safeguarding, the Single Unified Safeguarding Review (SUSR) was officially launched in October 2024. Additionally, Social Care Wales, in collaboration with Regional Safeguarding Boards, has developed and implemented National Standards for Safeguarding Training in Wales.

Our evolved framework now emphasizes accountability through designated action owners from Welsh Government and partner organisations who take direct responsibility for progress. We've integrated robust monitoring mechanisms to assess effectiveness, learn, and adapt quickly.

The powerful insights from the Older People's Commissioner for Wales and key stakeholders continue to guide our path forward. Every person in Wales deserves to live with dignity, free from abuse of any kind. Age should never diminish this fundamental right. This Plan deliberately addresses the specific vulnerabilities older people may face without diminishing their individuality.

Our vision extends beyond safeguarding to creating a truly age-friendly Wales—a nation where everyone looks forward to growing older, where ageism does not limit potential or affect the quality of services older people receive, and where the independence, participation, care, self-fulfilment and dignity of older people are upheld at all times.

The progress detailed in this report represents our unwavering national commitment to protect and empower older people across Wales. Together, we are building a country where age brings respect rather than risk, celebration rather than concern, and where every older person can live without fear.

Dawn Bowden, MS, Minister for Children and Social Care.

# Background and Context

A National Commitment to Combat Abuse of Older People

The abuse of older people remains one of our society's most pressing challenges, with profound physical, emotional, and social consequences for victims. Our National Plan established Wales as a UK leader in addressing this complex issue through coordinated, preventative action. One year into implementation, we've made significant strides while identifying crucial areas for enhanced focus.

Our approach continues to build upon the robust legislative frameworks established through the Social Services and Well-being (Wales) Act 2014, the Regulation and Inspection of Social Care (Wales) Act 2016, and the Violence against Women, Domestic Abuse and Sexual Violence (Wales) Act 2015. What distinguishes this Plan is its cross-governmental scope and commitment to transforming strategic vision into tangible action.

The first year has reinforced our understanding that effective safeguarding demands proactive multi-agency collaboration. We've strengthened these partnerships while acknowledging that each older person's experience is unique. Our work remains guided by the principles outlined in Age friendly Wales: our strategy for an ageing society and the United Nations Principles for Older Persons.

Evidence continues to show that some older people face distinct barriers to accessing support, including limited awareness of available services, misconceptions that services primarily target younger demographics, and challenges navigating complex systems. These barriers are often compounded by longstanding issues like financial vulnerability, health conditions, and deeply embedded feelings of shame or helplessness that may have developed over years of abuse.

The Older People's Commissioner's groundbreaking research—including "Leaving No One Behind," "Support Services for Older People Experiencing Abuse in Wales," and studies highlighting barriers faced by older men—has been instrumental in shaping our approach.

Data published by the Welsh Government confirms that older people experience all forms of abuse, with vulnerability to neglect compared to the general adult population.

Throughout year one, we've intensified our efforts to identify and combat ageism—the underpinning of much older people abuse. By challenging negative stereotypes and implementing rigorous impact assessments across all policy areas, we're working toward a Wales where age never determines one's value, rights, or access to protection.

As we move into year two, our refined Plan introduces clear accountability measures, designated action owners across government and partner organisations, and enhanced monitoring frameworks to evaluate effectiveness. This evolved approach will help us better understand what works, identify gaps more quickly, and continuously improve our nationwide response to abuse of older people.

Our commitment remains unwavering: creating a Wales where every older person lives free from abuse, where services are accessible and responsive to individual needs, and where dignity and respect are guaranteed regardless of age or circumstance.

Contents page link

# Objectives

The National Action Plan to Prevent Abuse of Older People contains three key objectives:

- Older people are supported to live independently and with dignity and can access relevant support from safeguarding services where they are at risk of abuse or neglect.

- Older people experiencing domestic abuse or sexual violence can access relevant support from Violence against Women, Domestic Abuse and Sexual Violence (VAWDASV) services when required.

- Older people are protected from becoming at risk of abuse or neglect.

Contents page link

# Section 1 Priority areas for action year one update

Introduction

Section 1 Priority areas for action year one update, Section 2 Priority areas for action year one update Key settings and Section 3 Priority areas for action year one update Key enablers provides update on the progress of all actions for year one (Feb 2024-Feb 2025).

Below each year one action update there will be an indication of the action type as follows:

- Accomplished - this action is now completed.

- Year two action (Feb 2025 – Feb 2026) - This action will continue into year two action plan. This action will be listed in Section 4 Year Two Actions of the report.

- Continuous action - This action will be continuous therefore feature on every action plan year on year. (listed in in Section 4 Year Two Actions)

Year Two Plan

Year two and continuous actions can be found in section 4 of this report.

As we move into year two of our action plan, our refined plan introduces clear accountability measures, designated action owners across government and partner organisations, and enhanced monitoring frameworks to evaluate effectiveness.

This evolved approach will help us better understand what works, identify gaps more quickly, and continuously improve our nationwide response to the abuse of older people.

Contents page link

## 1.1 Self-Neglect Practitioner Guidance

Self-neglect is an issue that has been highlighted in several Adult Practice Reviews (APR’s).

Year One Action (wording taken from original action plan)

We will develop new practice guidance on self-neglect to support practice across relevant settings by mid-2024. This will enable practitioners to better identify and act upon signs of self-neglect and prevent the harm to self and others that may arise when it is not sensitively addressed.

This document will define self-neglect for the purposes of safeguarding practitioners, set it within the framework of the Social Services and Well-being (Wales) Act 2014 Act statutory framework and describes how it sits with the definitions of neglect used in that. It will give practitioners a clearer idea of the relationship between their obligations under 2014 Act and the issues of consent and capacity addressed in the Mental Capacity Act 2005, as amended, and the Mental Health Act 1983, when dealing with issues of self-neglect.

Year One Progress Update

We have experienced a delay in progressing this action in year one.

We have worked with partners to develop new practice guidance on self-neglect to support practice across relevant settings.

We aim to publish the ‘Self-Neglect Non-Statutory Supplementary Guidance’ on the Safeguarding Adults procedure board website late spring 2025.

This action will be reported on in the year two report following publication of the guidance.

Action type: Year two action

Contents page link

## 1.2 Violence against Women, Domestic Abuse and Sexual Violence (VAWDASV)

In our original action plan we documented that Welsh Government commissioned the Wales Violence Prevention Unit to carry out research to establish what approaches may have been successful in preventing Violence against Women, Domestic Abuse and Sexual Violence (VAWDASV), published in September 2021.

It concluded or recommendations included:

Further research is also urgently needed for the prevention of specific forms of VAWDASV including honour-based abuse, exploitation and trafficking, and how prevention programmes intersect with the needs of individuals and communities who are LGBT+, BAME, and older age groups.

- Year One - Action 1

We will continue to monitor VAWDASV Grants administered by the Welsh Government to regions and third sector organisations on an annual basis to ensure they are adhering to the statutory guidance for the commissioning of VAWDASV services in Wales. They will be asked to provide evidence of how they have considered and met the needs of older people.

Year One Progress Update

The VAWDASV policy and finance team monitor grant recipients on a quarterly and annual basis to ensure the needs of all victims of VAWDASV are considered when delivering specialist services across Wales.

An intersectional approach to supporting service users is taken to ensure all cohorts in Wales with protected characteristics are being considered, therefore this action will now continue into year two as is business as usual.

Action type: Accomplished action

- Year One - Action 2

We will ensure the Violence against Women, Domestic Abuse and Sexual Violence Strategy 2022 to 2026 adopts a blueprint approach under which there is a specific workstream to address the needs of older people. Specific actions will be achieved in accordance with a programme to be established under the strategy’s programme board, to highlight the qualities and characteristics of those services found to be effectively improving the lives of older people and how good practice can be encouraged and shared.

Year One Progress Update

The VAWDASV Blueprint was established to be the delivery mechanism for the National VAWDASV Strategy for 2022-26.  Older people’s needs have been identified as a priority and therefore the Older People’s Needs Workstream is a priority area within the Blueprint.

During 2024/25 the Older Pople’s Needs Workstream engaged with Welsh Women’s Aid regarding Act and Act ‘train the trainer’ programme. A spotlight session with the workstream members took place to learn how the materials are adapted to suit an older cohort and how they consider intersectional needs within their training.

A service engagement project took place to identify best practice when engaging with older people. This included a calendar of interviews with service providers who support older people, concluding in a report highlighting best practice. Workstream members then collaborated on translating the learning from these interviews into a non-statutory information leaflet to demonstrate best practice that has been disseminated to professional networks across Wales.

A research and evidence need sub-group was created to identify gaps in knowledge required to make informed policy decisions. During this, priority areas were highlighted such as adult family violence and abuse and identifying better working practice between social care services and VAWDASV services. This was fed into a broader evidence and research piece of work taking place across the Blueprint as a whole.

The workstream began work on reviewing opportunities to improve the risk assessment process for identifying those at risk of/ experiencing VAWDASV in Wales. Following concerns raised by professionals on the suitability of the assessment and its ability to appropriately capture risk for older people, a task and finish group was established, and data is being gathered regionally from MARACs to support this piece of work. The workstream aims to make a formal recommendation on opportunities to the National Partnership Board in the Summer of 2025.

Action type: Accomplished action

- Year One Action 3

We will work with the Older People’s Commissioner to review the information and guidance on domestic abuse: safeguarding older people in Wales by mid 2024.

Year One Progress Update

There was a delay in progressing this action in 2024. This guidance is currently under review by safeguarding and VAWDASV colleagues, once completed this will be shared with the Older People’s Needs workstream, including the representative from the Older People’s Commissioner’s office. It is expected this guidance will be delivered upon in year two of the national action plan.

Action type: Year two action

Contents page link

## 1.3 Financial abuse

Financial abuse can have a devastating impact on victims and their families. The Social Services and Well-being (Wales) Act 2014 included financial abuse within its definition of abuse and made clear that abuse is:

- having money or property stolen

- being defrauded

- being put under pressure in relation to money or property

- having money or property misused

Year One Action

We will work with partners to identify ways of recognising and avoiding financial abuse, including scams, raising awareness among older people particularly, and signposting sources of advice and assistance.

Year One Progress Update

We have experienced a delay in progressing this action.

As we move into year two, our refined plan introduces clear accountability measures, designated action owners across government and partner organisations, and enhanced monitoring frameworks to evaluate effectiveness. This evolved approach will help us better understand what works, identify gaps more quickly, and continuously improve our nationwide response to the abuse of older people.

This action will be continued and reflected in section 4 and reported on in the year two report.

Action type: Year two action

Contents page link

## 1.4 Loneliness, social isolation and older people

In our original action plan we documented that in recent years we have heard increasingly about the detrimental impact loneliness and social isolation can have on our physical and mental health and well-being.

Our strategy, connected communities published in February 2020, recognises that whereas anyone, of any age, can experience loneliness and social isolation, older people are particularly vulnerable. This can leave people at increased risk of abuse or neglect.

Year One Action

Continue to implement the Loneliness and Isolation strategy which will consider key issues such as: digital exclusion, overcoming barriers to re-engaging, types of ongoing support required and sustaining community-based support and the role social prescribing will play a key role in ensuring local, preventative support is available and responsive to people’s individual needs.

Year One Progress Update

The strategy continues to be embedded in the work of the Social Services and Integration Directorate and cuts across several other strategies and plans in other Directorates.

Several of the key objectives have been achieved including:

- Publication of the Competence Framework for Social Prescribing Practitioners in Wales in December 2023

- Launch of the Information and Advice Services that provide a single point of contact for health and social care in regions

- Funding from the Community Facilities Programme has helped community centres – as well as a range of other facilities - to make improvements, repairs and redevelopments across Wales

- Funding from the Sustainable Social Services Third Sector Grant has helped community support groups increase their capacity and activities for older people to maintain or re-engage with their local community and build social connections.

- Public Health Wales has published the Principles for Community Engagement for Empowerment

Currently progress towards the objectives of this strategy are being mapped and an oral statement will be made in 2025 to update stakeholders.

Action type: Continuous action

Contents page link

## 1.5 Mental capacity - Deprivation of Liberty Safeguards (DoLS)

In our original action plan we documented that The Deputy Minister for Mental Health and Well-being issued a written statement on 5 April 2023 in response to the announcement by the UK Government to step away from the introduction of the Liberty Protection Safeguards (the LPS) and the implementation of the Mental Capacity (Amendment) Act 2019 (the 2019 Act).

The statement confirmed the UK Government decision that the necessary legislation to implement the LPS will not be brought forward within this Parliament and confirmed the Welsh Government’s deep disappointment with this decision not to proceed with implementation at this time.

Year One Action

Continue to support partners in Health and Social Care to streamline processes and improve practice around Deprivation of Liberty assessments in the absence of the Liberty Protection Safeguards being brought into being by UK Government (info below)

Year One Progress Update

This action will be removed from year two action plan as the Deputy Minister for Mental Health and Well-being issued a written statement on 5 April 2023 in response to the announcement by the UK Government to step away from the introduction of the Liberty Protection Safeguards (the LPS) and the implementation of the Mental Capacity (Amendment) Act 2019 (the 2019 Act).

The statement confirmed the UK Government decision that the necessary legislation to implement the LPS will not be brought forward within that Parliament and confirmed the Welsh Government’s deep disappointment with this decision not to proceed with implementation, therefore this action will be removed from this action plan, however Welsh Government will continue to support partners in Health and Social Care to improve practice around Deprivation of Liberty assessments as required.

Action type: Accomplished action

Contents page link

## 1.6 Dementia

In our original action plan we documented that Welsh Government published Dementia action plan: strengthening provision in response to COVID-19 in September 2021.

- Year One Action 1

Of particular relevance to this action plan, the Dementia action plan identifies as one of the overall cross-cutting themes a ‘protecting rights / person centred approach’; support for care homes and support for unpaid carers.

The document states that Welsh Government will:

- Provide a summary of outcomes reported through the Intermediate Care Fund (ICF) funded projects, which are being matched to areas of the Dementia Action Plan. This will include developments supporting the ‘teams around the individual’ approach, enabling families and carers to access respite care that is able to meet the needs of the carer as well as those of the person living with dementia.

Year One Progress Update

Welsh Government provide £12m to Regional Partnership Boards annually to support the implementation of the Dementia Action Plan vision and develop a joint health and social care approach to dementia support.

We have commissioned an independent evaluation of the Dementia Action Plan which is continuing to assess its impact on dementia care and support in Wales. This evaluation will inform the successor arrangements to the current Dementia Action Plan, and the companion document published September 2021 is acting as a bridging plan whilst the priorities for the successor arrangements are identified. The interim evaluation of the current Dementia Action Plan was received in May with the final version due by the end of the year. The interim evaluation focuses on several recommendations around timely diagnosis and post-diagnostic needs assessment and support.

We are starting work on preparing for the successor strategy and will be using the evaluation findings, alongside our engagement with stakeholders, to inform this work.

Action type: Year two action

- Year One Action 2

Of particular relevance to this action plan, the Dementia action plan identifies as one of the overall cross-cutting themes a ‘protecting rights / person centred approach’, support for care homes and support for unpaid carers.

The document states that Welsh Government will:

- Continue to work with the care home sector to help support the rights-based approach to care for people living with dementia and their families and enabling access to the rehabilitation they require in response to COVID-19. This will include ongoing work supporting care home residents’ well-being, identified through the work of the Care Home Action Plan.

Year One Progress Update

The resident well-being project people living in care homes has continued to evolve.

The Resident Wellbeing toolkit -Age Cymru ¦ Resident wellbeing- brings together resources that have been developed as part of the above work and move with the person through their care home life, including resources to support care home staff to have conversations about moving to a care home, future care planning, what matters to them, meaningful activities they would like to take part in and their plan for the end of the their lives. The toolkit supports people living in care homes to have their voices heard.

We will continue to raise awareness of the Resident Wellbeing toolkit with care homes and continue to add resources to it throughout the year.

Action type: Year two action

Contents page link

# Section 2 Priority areas for action year one update Key settings

## Care homes

In our original action plan we documented that inquests into the deaths of 8 people whose cases were considered as part of Operation Jasmine shone a light on the impact poor leadership and management has on the culture of an organisation and how this in turn impacts on the safety and well-being of people receiving a service. A negative culture in care home services creates the environment in which the neglect, abuse and breaches of people’s human rights can occur.

CIW has changed its recording of safeguarding concerns raised. Once embedded, this will enable information to be shared. The Care Inspectorate Wales Strategic Plan for 2020 to 2025 commits to "publish ratings for care homes and domiciliary support services; and to further develop our approach to joint working and inspections to support improvement".

Year One Action

The CIW strategic plan for 2020 to 2025 commits to 'use the findings from our inspections and reviews to improve services locally and nationally' and, in doing so, to 'continue to develop our approach to securing improvement and enforcement to ensure people are safe and receive high quality services'. CIW will also 'publish ratings for care homes and domiciliary support services'.

Year One Progress Update

Regulations are required to enable the use of published ratings for care home services and domiciliary support services. We held a 12-week public consultation on the draft regulations from mid-July. There was a pilot of silent / unpublished ratings which has been independently evaluated, and the findings have been published.

The regulations to publish inspection ratings for care home services and domiciliary support services in Wales came into force on 31 March 2025.

Action type: Accomplished action

Contents page link

## Domiciliary care

In our original action plan we documented that there are significant challenges within the social care sector, and particularly within reablement and domiciliary care services. Although there have been improvements in the availability of services in several parts of Wales throughout 2024-25.

Recruitment and retention barriers are multifaceted and require a range of actions and cohesive partnership working to address; we remain committed to taking action alongside our partners to enhance our workforce and creating a sustainable workforce for the future.

Social Care Workforce Partnership

  - Year One Action number 1

We are funding national and targeted recruitment work and local authorities are engaged in a range of initiatives to increase capacity. Welsh Ministers introduced the Real Living Wage for social care workers from April 2022. Work to improve pay, terms and conditions more generally via the Social Care Fair Work Forum is continuing.

Year One Progress Update

Supporting our social care workforce is a priority for Welsh Government, and we recognise the incredible role they play in supporting the social care sector. Welsh Government and our Social Care Fair Work Forum are committed to raising the profile and status of the workforce through registration, improved pay, and better terms and conditions. We have provided significant funding through Social Care Wales to support recruitment, retention and support improvements within the social care sector.

In January, the Minister for Children and Social Care launched the Social Care Workforce Partnership with the overarching aim to agree a minimum set of employment expectations for the social sector, to include Fair Work principles. The Partnership has identified its top three priorities to focus on in the first year: Recognition Agreements (alongside Trade Union Access); Disciplinary and Grievance; and Health and Safety, including violence in the workplace. Each priority area is being taken forward by a partnership Task & Finish Group including representation from government, trade unions, employer representatives, and relevant experts. Implementing consistent HR policies in social care is essential for creating a supportive and efficient environment that benefits employers, employees, and service users. The Partnership will actively encourage social care employers to voluntarily adopt these models by highlighting the benefits they will offer in providing clear and consistent approaches to policies across the social care sector.

We are developing a Pay and Progression Framework for voluntary adoption across the sector; it is expected a draft Framework will be available in 2026. The Framework will provide more consistent pay, progression, and development opportunities by setting out broad bands of roles within social care, aligned with skills, learning, and pay levels.

We are in our fourth year of providing funding within the Local Government’s Revenue Support Grant (RSG) to meet the costs of the Real Living Wage (RLW)

We commissioned an independent evaluation of the implementation of the RLW and expect the first report to be published this summer. Early findings suggest the policy has had a positive impact on the sector, but also recognises the funding is not reaching all of our social care workers. The evaluation will then move onto the outcomes for the workforce in terms of wellbeing, recruitment, and retention.

A Worker Voice Task & Finish Group has been commissioned by the Forum to consider how to raise awareness amongst staff in the independent sector of the benefits of unionisation for staff and employers; how to support employers in ensuring their workers have access to trade unions; and, how to amplify worker voice within policy development and improvement work across the sector to include a diverse and inclusive range of experiences. The Group will make recommendations to the Forum for consideration and action where appropriate.

Action type: Continuous action

Community Pharmacy Wales

In our original action plan we documented that Community Pharmacy Wales represents around 700 pharmacy owners in Wales on NHS matters. Its main objective is to secure the best possible NHS service opportunities, remuneration and terms. It is the body responsible for liaising with the Welsh Government and for negotiating the contractual terms for the provision of the NHS community pharmacy services.

We will support community pharmacies with material and training to identify signs of abuse and report it to social services where appropriate.

  - Year One Action 2

Ensuring safe administration of medicine. We will continue to work with the Medication Administration in Domiciliary Care (MADC) working group, which comprises Welsh Government officials and stakeholders. The aim is to establish national practice and training with regard to domiciliary care and the safe administration of medication, reduce the number of incidents where unsafe use or storage of medicines is recorded.

Year One Progress Update

We continue to work with the Medication Administration in Domiciliary Care (MADC) working group. The MADC brings together colleagues from across Welsh Government, the health boards, local authorities, regulatory bodies, pharmacies and the National Provider forum for discussion and problem solving around medication administration within domiciliary care in Wales.

The working group aims to utilise the expertise of its members to develop national policy, guidance, and training support for medication administration within domiciliary care.

It is the intention to publish national guidance on the All Wales Medicines Strategy Group website. It has been a complex task to achieve sign off of guidance by all local authorities and a range of other stakeholders and this remains in process.  Strengthening of regional agreements is considered a positive way forward.

The group continues to explore levers to support the increased use of electronic Medication Administration Records (eMAR). This requires better digital linkages with community pharmacy suppliers/individual’s medicine records.

Action type: Year two action

Contents page link

# Section 3 Priority areas for action year one update Key enablers

## 3.1 Unpaid care

In our original action plan we documented that thousands of unpaid carers of all ages across Wales support people with complex needs to live independently and well in their own homes and reduce pressure on the Welsh health and social care system.

Many older carers live with their own health conditions and although caring for a friend or family member is a rewarding experience for many, unpaid carers can overlook their own needs.

The strategy for unpaid carers, published in March 2021, states that all unpaid carers must have the opportunity to take breaks from their caring role to enable them to maintain their own health and well-being. Practical support for unpaid carers can prevent families reaching crisis point. Financial support can also reduce stress and help unpaid carers struggling to cope with the cost-of-living crisis. Welsh Government recognises the importance of making sure unpaid carers are recognised and feel valued and we continue to invest in supporting carers to have a life alongside caring.

Year one action

Investment of £1.75m to continue the Welsh Government Carers Support Fund to provide emergency financial assistance to unpaid carers on low incomes, delivered by Carers Trust Wales in 2024/25. Continuation of Welsh Government Short Breaks Fund to provide short break opportunities, funding provided of £3.5m for 2024/25. Continuation of funded national programmes to provide carers with information, advice and wellbeing support.

Year one progress update

Carers Support Fund delivered payments to 11, 687 carers in 2024/25. Data for Short Breaks for 2024/2025 is not yet available at time of writing. However, we are confident that the target of 30,000 short breaks for 2022 –25 has been significantly exceeded. This is in addition to respite opportunities provided by local authorities as part of their statutory duties. The national programmes have been delivered as anticipated. There will be a further action for unpaid carers in section 4 for year two.

Action type: Accomplished action

## 3.2 Voice

In our original action plan we documented that a code of practice on advocacy services was issued under the Social Services and Well-being (Wales) Act 2014.

The Code set out the requirements for local authorities to ensure that access to advocacy services and support is available to enable individuals to engage and participate when local authorities are exercising statutory duties in relation to them. It recognised the importance of a variety of forms of advocacy, statutory and non-statutory, formal and informal.

The Welsh Government has funded the HOPE (Helping Others Participate and Engage) project which aims to promote access to early intervention support at community level through a range of advocacy models for older people and carers across Wales.

Year One Action

We will commission research into the provision and accessibility of advocacy services for older people in care homes, not only on entry but throughout their residency.

The Regulation and Inspection of Social Care (Wales) Act 2016 requires care homes to signpost advocacy services, and Care Inspectorate Wales statutory guidance indicates 'service providers put in place arrangements to enable individuals to access relevant advocacy services or self-advocacy groups (if they wish) and support for their communication needs to enable them to make decisions about their lives'.

A study of how this has worked in practice and affected the lives of residents would be a useful guide for future policy work.

Year One Progress Update

Welsh Government funds the HOPE Cymru project led by Age Cymru under the Sustainable Social Services Grant which continues to the end of March 2026.

HOPE delivers independent advocacy support at a community level through a range of advocacy models by recruiting and then fully training and supporting project volunteers. HOPE aims to support people at an early stage in their issues or concerns to prevent them slipping into crisis.

HOPE delivers independent advocacy for older people (50+) and carers across Wales. HOPE staff and volunteers also engage with communities who can guide us to make sure the service we provide is right for the needs of older people and carers in their areas. We don’t want to duplicate existing services but rather we want to make sure we work with and complement the existing advocacy providers and forums across Wales.

Age Cymru have also developed the Resident wellbeing toolkit to bring together helpful resources to support care home staff to engage with people living in care homes to ensure their voices are heard in relation to the care they receive.

A new action for advocacy regarding the Resident toolkit can be found in section 4.

Action type: Accomplished action

Contents page link

## 3.3 Older people’s rights

Human rights are universal and recognised rights for everyone as set out in the Human Rights Act 1998 (HRA). Age is a protected characteristic under the Equality Act 2010 which means that people cannot be treated differently because of their age.

Raising awareness of rights can also empower people to take control and recognise when their rights are being compromised. Defining human rights in simple terms can empower older people to challenge and change the way services are designed and delivered in Wales, but it is equally important to raise awareness of rights amongst professionals.

We are undertaking a series of actions to "make rights real for older people". We have delivered a national campaign to make older people and carers aware of their rights under the Social Services and Well-being (Wales) Act 2014. We also established a working group with older people and key partners including the Older People’s Commissioner to coproduce practical guidance demonstrating how health and social care professionals can embed a rights-based approach. It shows how simple changes to the way we work can uphold an individual’s human rights and have a major impact on their well-being.

Age Friendly Wales: our Strategy for an Ageing Society, published in October 2021, sets out how we will work with a range of partners to address the factors that influence how we age – from our health, social care and transport systems to the way we socialise, work and care for others.

Year One Action

We will promote further research to identify early intervention and preventative strategies to prevent the abuse of older people. This will identify approaches which can be successful in enabling older people avoid becoming at risk of, or experiencing, neglect or abuse.

Year one Update

Welsh Government fund over £1.5m per annum to the Older Persons Commissioner office. The Commissioner’s role and statutory powers are defined by the Commissioner for Older People (Wales) Act 2006 and accompanying Regulations.

The Act outlines the action that the Commissioner is able to take to ensure that the interests of older people are safeguarded and promoted when public bodies discharge their functions and the assistance the Commissioner may provide directly to older people in certain situations.

In addition, Welsh Government will continue to promote and explore further research to identify early intervention and preventative strategies to prevent the abuse of older people. This action can be found in section 4.

Action type: Continuous action

Contents page link

## 3.4 Role of LLAIS

Key to efforts to reduce the risk of abuse or neglect in any setting is to listen to the experiences of service users and empower them to speak out where they believe themselves or others to be at risk.

The drive towards closer integration of health and social services with improved public engagement is reflected in the aims of a healthier Wales. This sets out the goal of ensuring citizens are placed at the heart of a whole-system approach to health and social care services and stresses the importance of listening to all voices through continual engagement.

To realise this ambition, the Health and Social Care (Quality and Engagement) (Wales) Act 2020 replaces Community Health Councils (who currently represent the patient voice in the health service only) with a new national body, the Citizen Voice Body. Operationally known as LLAIS, the Citizen Voice Body exercises functions across health and social care.

The aims of LLAIS are to:

- strengthen the citizen voice in Wales in matters related to both health and social services, ensuring that citizens have an effective mechanism for ensuring that their views are heard

- ensure that individuals are supported with advice and assistance when making a complaint in relation to their care

- use the service user experience to drive forward improvement

Year One Action

Keeping people safe - we will publish a Code of Practice about how LLAIS can access places where health or social care services take place to get people’s views, and how that engagement happens by Summer 2023. There will also be statutory guidance to which NHS bodies and local authorities must have regard when dealing with representations made to them by LLAIS.

Year One Progress Update

This action has been completed and Code of practice for Llais on accessing premises and engaging people was published.

This code of practice is to ensure that the collective voice of individuals can inform the design and delivery of services to better fit their needs.

Ensure the rights of children, young people and adults are at the centre of this process.

Promoting and facilitating engagement between individuals and the Citizen Voice Body (CVB) through access to relevant premises to help strengthen the public’s voice and participation in shaping the design and delivery of services.

The Code sets out the expectation that bodies covered by the Code will agree to reasonable requests by the CVB for access to relevant premises.

Action type: Accomplished action

Contents page link

## 3.5 Better information sharing

Good information sharing is central to good safeguarding practice. Practitioners must share information in accordance with to the UK’s data protection legislation. One of the specific circumstances which provides for information sharing is in order to prevent abuse or serious harm to others (schedule 1 para 18 of the Data Protection Act 2018).

A key theme emerging from Adult Practice Reviews is the need for better multi-agency communication and information sharing. When information is not shared in a timely and effective way decisions about how to respond may be ill informed and this can lead to poor safeguarding practice and leave people at risk of abuse or neglect.

Year One Action

We will produce a non-statutory guide to remind practitioners working across agencies of their responsibilities to share information to safeguard adults at risk and to support them in understanding the conditions under which information may be shared.

This advice will be for all front-line practitioners and managers working with adults at risk, carers and families who have to make decisions about sharing personal information on a case-by-case basis, where there are safeguarding concerns. We will aim to publish this guidance by the third quarter of 2024.

Year One Progress Update

This action has yet to be realised. Our evolved framework now emphasizes accountability through designated action owners from Welsh Government and partner organisations who take direct responsibility for progress therefore a reshaped action can be found in section 4

Action type: Year two action

Contents page link

## 3.6 Better digital access

We are working to achieve a smarter, better-connected society and economy by making sure everybody in Wales has access to digital technologies and knows how to use them. The Digital Strategy for Wales objective of inclusivity should pay due heed to the needs of older people and offers an enhanced ability to access safeguarding support.

Through our digital communities Wales: digital confidence, health and well-being procured programme we work with organisations from all sectors that can help reach digitally excluded people.

Year One Action

Develop a communications campaign to raise awareness of digital inclusion and improve the basic digital skills of older people.

Year One Progress Update

DCW have developed and delivered a communications campaign to raise awareness of digital inclusion and improve the basic digital skills of older people by highlighting the simple steps that individuals can take to support a digitally excluded person to get online, becoming their digital companion. Their website includes case studies of those with lived experience of digital exclusion and the impact the use of technology has since had on them

DCW offer tailored advice and training to organisations working with older people fostering a sense of inclusion, empowerment, and lifelong learning. Their goal is to demonstrate how digital tools can positively impact their lives.

DCW provide free training resources to help people on their digital inclusion journey across the whole of Wales. Training: Older People and digital

Action type: Accomplished action

Contents page link

## 3.7 Learning and improving: the impact of our Single Unified Safeguarding Review (SUSR) process

In our original action plan we documented in 2018 both an academic report by Dr Amanda Robinson and a practitioner report by Liane James on Domestic Homicide Reviews (DHRs), Adult Practice Reviews (APRs), Child Practice Reviews (CPRs) and Mental Health Homicide Reviews (MHHRs) in Wales were conducted. They both highlighted how the review process is chaotic and complex, with some incidents generating multiple reviews. According to the category of the review, they may be carried out by either devolved or non-devolved agencies.

Based on the findings, the reports advised that several changes needed to be made. This included the creation of a Single Unified Safeguarding Review (SUSR) which is a cross-agency framework that encompasses all elements which would usually require multiple reviews.

    - Year One Action 1

We will provide a Single Unified Safeguarding Review (SUSR) process which is used by both devolved and non-devolved agencies to ensure recommendations are actioned and learning embedded.

Year One Progress Update

The SUSR was piloted in Wales from the beginning of 2024 and officially launched on October 1st 2024 with new statutory guidance. It combines Adult Practice, Child Practice, Mental Health Homicide, Domestic Homicide and Offensive Weapon Homicide reviews into one single rigorous process.

The SUSR eliminates the need for families to take part in multiple, often onerous and traumatising reviews and will more quickly identify learning; build a greater understanding of what happened during an incident and why and provide a clear action plan to improve services. Importantly, it will ensure learning is adopted throughout Wales.

A dedicated SUSR Co-ordination Hub supports delivery of the process, learning dissemination and monitors implementation of all SUSR recommendations. The Hub also facilitates the SUSR Support Network which provides a critical oversight function.  This includes the SUSR Ministerial Board, chaired by the Minister for Children and Social Care with a membership of key Ministers and leaders across the public sector in Wales, the Home Office, Police and Crime Commissioners and the Domestic Abuse Commissioner.  The Board oversees the safeguarding review process, addressing escalated issues and harnessing cross-sector collaboration and learning opportunities.

This action is complete. Further work will be undertaken to demonstrate how actions and learning from new SUSR reports are being embedded and how this helps protect older people at risk of abuse or neglect.  These new reports will start being published from Spring/Summer 2026.

Action type: Accomplished action

    - Year One Action 2

We will use the Welsh Safeguarding Repository (WSR) to store all safeguarding reviews in one central database and through machine learning identify trends and themes.

Year One Progress Update

We have developed the Wales Safeguarding Repository (WSR) in partnership with Cardiff University to support the SUSR process.  All completed Single Unified Safeguarding Reviews reports are held there.  Past Adult Practice Reviews, Child Practice Reviews and Mental Health Homicide reviews are held there too.

The WSR enables researchers and practitioners to extract new learning about violence, abuse, vulnerability and safeguarding with a view to improving practice on a pan-Wales basis. The SUSR Co-ordination hub and Welsh Government meet fortnightly now to take responsibility for sharing the learning that arises from the SUSR process. This will also be shared widely in bi-annual events for professionals and volunteers delivered by Welsh Government.

This will enable data to be drawn from the reviews to be used by practitioners going forward, and to produce thematic analysis of the reviews, as well as disseminating learning across Wales to ensure that lessons are identified from past incidents to help prevent similar cases in the future.

The Repository will be accessible to partners who have legitimate reasons for accessing the information to inform development of policy and practice. There is a search function that enables professionals to search for terms like ‘alcohol misuse’, ‘self-neglect’ and domestic abuse.  A ‘Recommendation Search Facility’ also allows reviewers to search and retrieve examples of recommendations previously made and ensure the same recommendations are not continually repeated. With over 170 reviews now stored in the WSR practitioners are now able to produce thematic analysis of the reviews, as well as disseminating learning across Wales to ensure that lessons are identified from past incidents to help prevent similar cases in the future.

The SUSR Co-ordination hub and Welsh Government also meet fortnightly to take responsibility for sharing the learning that arises from the SUSR process. This learning will also be shared widely by Welsh Government in bi-annual events for professionals.

This action is complete.  Further work will be undertaken to support practitioners, policy makers and researchers working to protect older people at risk of abuse or neglect to access the WSR.

Action type: Accomplished action

Contents page link

## 3.8 Better data

The National Independent Safeguarding Board annual report 2019 to 2020 recommended: The Welsh Government should ensure that the Technical Guidance of the Social Care Performance and Improvement Framework includes information about the abuse of older people by collecting data broken down by age group.

The Performance and Improvement Framework for Social Services became law in 2020. The work on further age disaggregation of the safeguarding return is a requirement of the new collections. The adult safeguarding return which has been carried over from the previous framework is now collected by much narrower age bands which allows for a more precise analysis of abuse and neglect by age.

Year One Action

Developing the new adults receiving care and support census. The Adult Census Development Group will be the primary means of developing the new census. Welsh Government and local authorities in Wales participate in this group in addition to representatives selected from academia, providers and partner agencies. This will better enable us to emerging trends and risks.

Year One Progress Update

The new Adult Receiving Care and Support Census (ARCS) has been developed individual level data on all adults who receive care and support from local authority social services.

The content and guidance for local authorities has been published, and the first collection of the data will be in 2024/25, which covers the adults who received care and support in 2023/24.

Through this collection, we’ll be able to know the categories of safeguarding (Neglect, Physical, Sexual, Financial, Emotional/Psychological) and breakdown by gender and other personal characteristics.

In addition to this, the adult safeguarding section of the Performance and Improvement Framework activity and performance data is being reviewed, with the aim to seeking to better understand the support being offered to adults who experience abuse.

This will enable better evidence of the prevalence and nature of abuse of older people in Wales.

This information will inform us of the following:

- The number of adult safeguarding referrals made to the local authority area

- The setting in which the alleged abuse/neglect occurred

- The type of abuse/neglect alleged

Combined this will provide a clear view of the demand on adult safeguarding teams and patterns/trends in referrals. It will also enable us to identify the main types of abuse/neglect that are referred and where they take place. This will assist local authorities to target general safeguarding training on specific settings/professionals, raise issues for the inspectorate if there are patterns/trends in a specific setting so they can target improvement work.

Action type: Continuous action

Contents page link

## 3.9 Training and registering our workforce – Social Care Wales

In our original action plan, we documented that Social Care Wales will:

- continue to undertake and meet its responsibilities for workforce regulation and development, delivering core and statutory functions

- continue to deliver the extension of the social care register, particularly in reference to new groups such as adult care home workers, whilst continuing to reform and improve the regulatory framework for all

- along with CIW, Social Care Wales will continue to support positive cultures in social care services

1	Year One Action 1

We will develop a National Training Framework with a 'train the trainer' programme (building on approved Regional Training Framework and NHS Training Framework) and to coordinate a national conversation to improve and enhance multi-agency Safeguarding Training. The standards will be approved by the chairs of Regional Safeguarding Boards and are subject to consultation.

Year One Progress Update

Social Care Wales (SCW) has collaborated with Regional Safeguarding Boards and constituent partners to develop and implement National Standards for Safeguarding Training in Wales. This was developed in response to ensure that all safeguarding training delivered gave the same key messages, aligned fully with the legislation, policy and guidance in place and was delivered to the right audience at the right frequency.

The Standards include groups of professionals who require safeguarding training:

- Group F (public service leaders)

- Group E (consultancy or sector leader)

- Group D (specialist)

- Group C (advanced)

- Group B (intermediary)

- Group A (basic awareness)

SCW have also been developing safeguarding training modules for online learning and face to face learning that are available on the Social Care Wales website www.socialcare.wales.

Group A covers all staff from all agencies who may come into to contact with older people who are at risk of abuse and/or neglect at some point during their work. The online training ensures that they have sufficient knowledge to identify, and report abuse to Social Services and/or Police.

Well trained staff will support the identification of abuse and neglect and report their concerns to Social Services and or Police who have specialist knowledge and will subsequently undertake investigations and take protective action if required.

Action type: Accomplished action

  - Year One Action 2

Social Care Wales will continue to deliver the extension of the social care register, particularly in reference to new groups such as adult care home workers, whilst continuing to reform and improve the regulatory framework for all.

Year One Progress Update

This action continues and will be reported upon in year two, the action remains and can be found in section 4 of this report.

Action type: Year two action

Contents page link

## 3.10 Awareness raising and communication

In our original action plan, we documented that along with partners from the Older People’s Commissioner’s Stopping Abuse Action Group, and in conjunction with the Older People’s Needs workstream of the VAWDASV Strategy, we will work to raise awareness of the types of abuse suffered by older people in Wales. This will include challenging some of the stereotypical assumptions around the nature of abuse to which older women and men are vulnerable.

Year One Action

Utilise communications channels and work with stakeholders to raise awareness of the needs of older people facing abuse and the factors which are found to obstruct those seeking assistance during 2024. This work to be built upon with the development of an awareness raising strategy.

Year One Progress Update

Welsh Government engage with, provide regular updates or reports to: the Older People’s Commissioner’s Stopping Abuse Action Group, the VAWDASV Blueprint Strategy Older People’s Workstream group and the Ministerial Advisory Forum on Ageing (MAFA).

Welsh Government utilise communications channels, engage regularly and seek opportunities to collaborate with stakeholders to raise awareness of the National Action Plan to Prevent the Abuse of Older People and to raise awareness of the types of abuse suffered by older people in Wales.

This encourages joined up working and linking the national action plan with other Welsh Government strategies to reduce abuse in Wales.

Action type: Continuous action

Contents page link

# Section 4 Year Two Actions

Introduction

As we move into year two of the action plan, our refined actions introduce clear accountability measures, designated action owners across Welsh Government, arm’s length and partner organisations. Enhanced monitoring frameworks to evaluate effectiveness.

This evolved approach will help us better understand what works, identify gaps, and continuously improve our nationwide response to the abuse of older people.

This section includes all actions that will be accomplished in year two and where applicable continuous / long term actions.

- Key to numbering:

Numbering in this section is in a continuous format in line with the objective they sit under. This is only relevant for Welsh Government officials and partners monitoring purposes.

Key objective 1. Section 4, action number = KO1/4/1.1, KO1/4/1.2 and so on. Key objective 2 = KO2/4/1.1, KO2/4/1.2 and so on.

Contents page link

# Year Two and beyond Actions

## Key Objective 1 Actions

Key Objective 1:

Older people are supported to live independently and with dignity and are able to access relevant support from safeguarding services where they are at risk of abuse or neglect

Reference: KO1/4/1.1

Action

Continue to develop and implement a routine data collection programme which makes sure we have the right data and evidence to deliver and support the objectives of this Plan

Impact

Information gathered as part of the new Adult Receiving Care and Support Census (ARCS), when combined with the Performance and Improvement Framework activity and performance data, will provide a clear view of the demand on adult safeguarding teams and patterns/trends in referrals. It will also enable us to identify the main types of abuse/neglect that are referred and where they take place.

This will assist local authorities to target general safeguarding training on specific settings/professionals, raise issues for the inspectorate if there are patterns/trends in a specific setting so they can target improvement work.

Action type: Continuous action

Action owner: Joint department action owners, Welsh Government

Reference: KO1/4/1.2

Action

Reshaped: Develop and implement a communications plan to highlight the positive outcomes, activities, and key messages of the action plan.

Impact

The plan will include a range of measurable communication activities which incorporates activities by partners and stakeholders that could be implemented to help increase understanding of the aims and outcomes of the action plan.

Action type: Continuous action

Action owner: Joint department action owners, Welsh Government

Reference: KO1/4/1.3

Action

Reshaped: Establish a dialogue with Regional Safeguarding Boards to better understand the data sources being reported to them not only from the Local Authority, e.g. Police, Violence Prevention Unit, Health. Further explore how this data can inform Welsh Government work.

Impact

Building relationships with Regional Safeguarding Boards.

Understanding of other data sources being collected by Regional Safeguarding Boards and assessing how / if this can be used within Welsh Government.

Access to this data may provide a holistic view of the demand on services in relation to adult safeguarding and identify further patterns/trends to enable us to identify the main types of abuse/neglect and where they take place.

This will assist Welsh Government to target safeguarding training and activities on specific settings/professionals

Action type Continuous action

Action owner Joint department action owners, Welsh Government

Reference: KO1/4/1.4

Action

We will develop and produce new practice guidance on self-neglect to support practice across relevant settings

Impact

The purpose of this guidance is to enable professionals working in Welsh local authorities to work more effectively with people who are self-neglecting.

This guidance will enable practitioners to better identify and act upon signs of self-neglect and prevent the harm to self and others that may arise when it is not sensitively addressed.

Action type: Year two action

Action owner: Welsh Government

Reference: KO1/4/1.5

Action

Social Care Wales and Care Inspectorate Wales will continue to undertake a programme of work focusing on leadership and management and cultures in social care services with specific reference to the rights, dignity, voice and awareness/prevention of abuse to older people.

Impact

Promote positive and inclusive organisational cultures.

This will enable service users to become better informed and better able to live independently and with dignity, reducing the risks of abuse and neglect.

Action type: Continuous action

Action owner: Social Care Wales and Care Inspectorate Wales.

Reference: KO1/4/1.6

Action

We will continue to raise awareness of the Resident Wellbeing toolkit with care homes and continue to add resources to it throughout the year.

Impact

Bring together helpful resources to enable care homes, families, friends and residents to create the ideal environment for supporting wellbeing.

Increased voice, awareness, information and support for care home residents and the people that support them.

Recognising a relationship-centred approach, where research shows that people with more social connection live longer, happier and healthier lives.

Action type Year two action

Action owner Welsh Government

Reference: KO1/4/1.7

Action

Take action to challenge ageism, raise awareness of older people’s rights and promote positive images of ageing.

Impact

The Ministerial Advisory Forum on Ageing has convened a working group to plan for a national debate on ageism. The aim of the work is to influence a positive change in attitudes towards older people and ageing in Wales. (The World Health Organisation (WHO) has identified ageism as a “major risk factor” in the abuse of older people.

WG is funding Age Cymru to deliver a communications campaign promoting positive images of ageing and older people which will be delivered in spring 2025.

Action type: Continuous action

Action owner: Welsh Government

Reference: KO1/4/1.8

Action

Support and link to the work of the Older People’s Commissioner for Wales

Impact

Welsh Government will continue to support and fund the Older People’s Commissioner.

The abuse of older people has been identified as one of the Commissioner’s priorities for her term in office and her work in this sphere, to include research, can be used to inform policy going forward.

Action type: Continuous action

Action owner: Welsh Government

Reference: KO1/4/1.9

Action

Building awareness and better joined up working.

To develop a National Training Framework with a 'train the trainer' programme (building on approved Regional Training Framework and NHS Training Framework) and to coordinate a national conversation to improve and enhance multi-agency safeguarding training around preventing and identifying abuse.

Impact

Improve and enhance multi-agency safeguarding training around preventing and identifying abuse.

Action type: Continuous action

Action owner: Social Care Wales

Reference: KO1/4/1.10

Action

New action: Support Social Care Wales with the support of Welsh Government will establish a dialogue with Regional Safeguarding Boards to ensure that the National Safeguarding Training Standards are being implemented within their constituent partner agencies

Impact

Improve and enhance multi-agency safeguarding training around preventing and identifying abuse.

Action type: Continuous action

Action owner: Social Care Wales

Reference: KO1/4/1.11

Action

New Action / reshaped action: Continue to raise awareness of materials aiming to Reduce Restrictive Practices in all settings providing care to older people.

Impact

Increased awareness in all settings providing care to older people of materials aiming to Reduce Restrictive Practices.

Action type: Year two action

Action owner: Welsh Government

Reference: KO1/4/1.12

Action

New Action / reshaped action: Continue to work on the successor plan to replace the Dementia Action Plan.

A key ethos of the successor plan will be supporting people to live independently, and ensuring they have access to the right support at the right time and have the information they need to make informed choices.

Impact

Older people are supported to live independently and with dignity and are able to access relevant support from safeguarding services where they are at risk of abuse or neglect

Action type: Continuous action

Action owner: Welsh Government

Reference: KO1/4/1.13

Action

New action: We plan to develop other practice guides relating to adults/older people such as sexual and criminal exploitation of adults, mental capacity and the management of pressure sores.

We will consider the current guidance available on each of the topics listed (and any other that are identified as part of this work) and consider our approach and how we can collaborate with partners where applicable.

Impact

The purpose of any updated guidance is to enable practitioners to have the most up to date information and guidance to consider in certain situations as they arise.

Action type Year two action

Action owner Welsh Government

Reference: KO1/4/1.14

Action

New Action: Develop ways of collecting workforce data with Social Care Wales as part of the Care Inspectorate Wales Strategic plan 2025-2030

Impact

Working together across CIW and with our partners, sharing what we know to improve outcomes for people.

Action type: Continuous action

Action owner: Care Inspectorate Wales

## Key Objective 2 - Year Two Actions

Key Objective 2:

Older people experiencing domestic abuse or sexual violence are able to access relevant support from Violence against Women, Domestic Abuse and Sexual Violence (VAWDASV) services when required.

Reference: KO2/4/1.1

Action

Reshaped: Safeguarding and VAWDASV to align on key issues that impact older people through the VAWDASV Blueprint Older People’s Needs workstream.

Impact

Safeguarding and VAWDASV policy teams will continue to work together to ensure that the cross-cutting issues that affect older people are effectively considered in policy development and practice.

Lead on the review of the information and guidance on domestic abuse: safeguarding older people in Wales guidance to ensure that practitioners have access to the best information to support them.

We will identify opportunities to improve risk assessment to ensure risk are sufficiently identified for older people at risk of abuse.

We will support a collaborative awareness raising campaign

Opportunity to highlight existing evidence and data, as well as identify gaps to support future research needs to support policy development and practice

Opportunity to strengthen working across safeguarding and VAWDASV sectors to ensure a cross-governmental and collaborative approaches to tackling safeguarding and VAWDASV related issues

Action type: Continuous action

Action owner: Joint department action owners, Welsh Government

## Key Objective 3 – Year Two Actions

Key Objective 3:

Older people are protected from becoming at risk of abuse or neglect.

Reference: KO3/4/1.1

Action

We will work with the ‘Social Care Fair Work Forum’ to support our social care workforce to improve pay, conditions and training to ensure we have the right workforce, with the rights skills to deliver high quality care to the people of Wales.

Impact

We will continue to strengthen our recruitment initiatives and commitment to funding through Social Care Wales to support recruitment, retention and support improvements within the social care sector.

Improving the pay, terms and conditions, and training opportunities for the sector will help us to recruit and retain staff and ensure we have the right skills in the right place at the right time.

Will support the recruitment challenges and aim to attract more people to the sector.

Action type: Continuous action

Action owner: Welsh Government

Reference: KO3/4/1.2

Action

Ensuring safe and consistent arrangements for administration of medicine by domiciliary care workers. We will continue to work with the Medication Administration in Domiciliary Care (MADC) working group, which comprises Welsh Government officials and stakeholders.

Impact

The aim is to establish national practice guidance and training regarding administration of medication by domiciliary care workers and the commissioning arrangements for this service.

Action type: Year two action

Action owner: Welsh Government

Reference: KO3/4/1.3

Action

Reshaped: Obtain feedback from Llais Citizen voice Body for Wales  on the implementation of the Code of practice for Llais on accessing premises and engaging people

Impact

WG will have evidence to support the implementation of the code of practice.

Views of hard-to-reach vulnerable groups will be represented in the work of Llais.

Action type: Year two action

Action owner: Welsh Government

Reference: KO3/4/1.4

Action

Reshaped: Good information sharing is central to good safeguarding practice. Practitioners must share information in accordance with to the UK’s data protection legislation.

We will explore options to produce either a non-statutory or a statutory guidance to remind practitioners working across agencies of their responsibilities to share information to safeguard adults at risk. We will first understand what guidance is currently available and consider updating or combine if appropriate.

Impact

Any new guidance will be for all front-line practitioners and managers working with adults at risk, carers and families who have to make decisions about sharing personal information on an individual-by-individual basis, where there are safeguarding concerns.

Support practitioners to understand the conditions and legal position under which information may be shared. Ensure information is shared across agencies / professionals to protect adults from abuse

Action type: Year two action

Action owner: Welsh Government

Reference: KO3/4/1.5

Action

Reshaped: We will work together to ensure signposting for financial and digital inclusion for older people is available.

Impact

People at risk or experiencing financial abuse, front-line practitioners, managers and partners will be able to access relevant information support and assistance to protect themselves against this type of abuse.

Action type: Year two action

Action owner: Welsh Government

Reference: KO3/4/1.6

Action

As we continue to implement the loneliness and isolation strategy, we will consider key issues identified by the group such as: digital exclusion, overcoming barriers to re-engaging, types of ongoing support required and sustaining community-based support. Social prescribing will play a key role in ensuring local, preventative support is available and responsive to people’s individual needs.

Impact

The strategy continues to provide focus across sectors in tackling loneliness and isolation; this includes transport services which can often be a barrier to engaging.

Partners are aware of the social prescribing framework in Wales and how to support people in increasing engagement and participation in activities, that supports their health and wellbeing.

A number of community-based support schemes are in place to support people who are over the age of 50 to maintain or re-engage with community activities and build lasting social connections. These schemes continue to be supported by the SSS 3rd Sector Grant and will continue until 2026

Integrated Impact Assessments for loneliness and isolation will be developed which will give programme and policy makers a dedicated focus to consider the impacts of loneliness and isolation when developing policy and services.

Over the next few months officials also plan to undertake a scoping exercise to create an understanding of progress made to date in terms of commitments included in the connected community's strategy, with a view to identifying any areas that may still need attention.

Action type: Continuous action

Action owner: Welsh Government

Reference: KO3/4/1.7

Action

New Action: We will provide progress updates on SUSR thematic learning work undertaken that address key issues for older people such as inter-familial domestic abuse, mental health risk-assessment and self-neglect

Given that Safeguarding Boards are so early into commissioning new SUSRs, this impact is high-level and may be refined at the end of year two.

Impact

Learning and practice resulting from SUSRs is helping to protect older people of becoming at risk of abuse or neglect

Action type: Continuous action

Action owner: Welsh Government

Reference: KO3/4/1.8

Action

New Action We will identify and support practitioners, policy makers and researchers working to protect older people at risk of abuse or neglect to access the WSR and use it to identify trends and themes and inform future practice.

Impact

Practitioners, policy makers and researchers are using the WSR to inform policy development, learning and practice.

Action type: Continuous action

Action owner: Welsh Government

Reference: KO3/4/1.9

Action

Awareness and support. We will support primary care contractor workforce to access safeguarding guidance for independent commissioned services designed by Public Health Wales.

In addition, we will ensure that health care professionals working within primary and community care are aware of relevant guidance from their regulatory and professional representative bodies to support them in identifying signs of abuse and knowing how report it to social services where appropriate.

Impact

All primary care contractor and community AHP workforce are aware of sources of advice and assistance for people accessing their services that may be experiencing or are at risk of abuse.

People at risk of or experiencing abuse will be able to access relevant information support and assistance to protect themselves against this type of abuse.

Action type: Year two action

Action owner: Welsh Government

Reference: KO3/4/1.10

Action

New action: Social Care Wales will continue to deliver the extension of the social care register, particularly in reference to new groups such as adult care home workers, whilst continuing to reform and improve the regulatory framework for all.

Impact

Registration of adult social care workers ensures that only those who are competent and qualified can deliver care and support. This

supports high standards in social care and that individuals receive safe, effective, and respectful support.

Action type: Continuous action

Action owner: Social Care Wales

Reference: KO3/4/1.11

Action

New action Care Inspectorate Wales (CIW) and Health Inspectorate Wales (HIW) will produce jointly the Deprivation of Liberty Safeguards in Wales - Annual Report 2024-25

Impact

Provides an overview of Deprivation of Liberty Safeguards in Wales, which protect vulnerable adults who lack mental capacity to consent to care arrangements.

The report highlights both progress and persistent challenges in protecting vulnerable people's rights across Welsh health boards and local authorities.

Action type: Year Two Action

Action owner: Joint action owners: Care Inspectorate Wales and Health Inspectorate Wales, Welsh Government

Reference: KO3/4/1.12

Action

New Action - Unpaid Carers Continue to fund and monitor a range of supports for unpaid carers.

Impact

Supports are designed to alleviate some of the pressures on unpaid carers and their wellbeing that could impact on the pressure within households caring for older people.

Action type: Continuous action

Action owner: Welsh Government