## Guidance
How to Use the Project Schedule Template
As part of your grant application, you're required to submit a project schedule using the provided template. This schedule helps us understand how you plan to carry out your project over time. If you're unfamiliar with Gantt charts or project timelines this guide will walk you through how to fill out the template step by step.
What is this template for?
This Project Schedule Template is a simplified Gantt chart. It lets you list out your project’s major tasks, their planned start and end dates, and see everything on a timeline. It's a great way to visualise your project’s progress from start to finish.
How much detail do you need to provide?
The level of detail in your project schedule should be proportionate to the size and complexity of your project. A larger or more complex project should include a more detailed breakdown of tasks, dependencies and contingency time.
1. Enter in Project Details
Enter organisation name, project start date [dd/mm/yyyy], and the number of weeks.
Changing the number of weeks automatically changes the project schedule to reflect your projects timeline.
2. Enter Stages of your Project
In the stage name cells which are labelled Stage 1 - 10, enter in the different stages of the project.
Example:
Planning & Preparation
Procurement
Enabling Works
👉 Tip: Use these as a guide to help map out your own timeline.
3. Enter Your Project Tasks
In the "Task Description" column, list the major activities or milestones in your project. Think of these as the big steps you’ll need to take to complete your project.
Example:
Prepare budget and risk assessment
Engage with stakeholders or community
Prepare tender documents or RFPs
Order equipment or materials
Ground investigations
👉 Tip: Break your project into 5–10 key tasks. Don’t list every small action.
4. Add Start and End Dates
For each task, fill in the Start Date and End Date columns. These should reflect when you plan to begin and finish each activity.
🗓 Use the format: dd/mm/yyyy (e.g., 01/05/2026).
5. Check the Duration
The Duration column will automatically calculate how many days each task will take based on your start and end dates. You don’t need to edit this.
6. View the Gantt Chart
As you fill in the dates, the visual timeline (the Gantt chart) to the right will automatically update. Each row shows a bar across the timeline corresponding to the task duration, so you can easily see which tasks happen when.
7. Double-Check for Overlaps
Look at the timeline to make sure:
Tasks that depend on each other are in the right order
You haven’t accidentally scheduled everything to happen at once (unless that’s your plan!)
The overall schedule makes sense given your grant timeline
8. Save and Upload
Once you're happy with your schedule:
1. Save the file as YourProjectName_Project_Schedule.xlsx
2. Upload it with your grant application as instructed
💡 Tips for Success
You can add rows if you need more tasks.
Try to be realistic with your timing—include a little buffer if you're unsure.
Keep it simple and easy to understand.

## Blank Project Schedule
Project Schedule - To be filled in by Applicant
Cells to be completed
Inputs
Organisation name: | [Enter Organisation Name] |  | Stage 1 - name: | <stage 1> | [15 empty] | Stage 6 - name: |  |  |  |  | <stage 6>
Project start date: | 2026-06-01 |  | Stage 2 - name: | <stage 2> | [15 empty] | Stage 7 - name: |  |  |  |  | <stage 7>
Number of weeks: | 32 |  | Stage 3 - name: | <stage 3> | [15 empty] | Stage 8 - name: |  |  |  |  | <stage 8>
|  |  | Stage 4 - name: | <stage 4> | [15 empty] | Stage 9 - name: |  |  |  |  | <stage 9>
|  |  | Stage 5 - name: | <stage 5> | [15 empty] | Stage 10 - name: |  |  |  |  | <stage 10>
[5 empty] | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 56 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 59 | 59 | 59 | 59 | 60 | 60 | 60 | 60 | 60
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32
Category | Task Description | Start Date | End Date | Duration | time axis 2026-06-01 to 2027-01-08
<stage 1> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 2> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 3> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 4> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 5> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 6> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 7> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 8> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 9> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0
<stage 10> | <Task 1> |  |  | 0
| <Task 2> |  |  | 0
| <Task 3> |  |  | 0
| <Task 4> |  |  | 0
| <Task 5> |  |  | 0
| <Task 6> |  |  | 0
| <Task 7> |  |  | 0
| <Task 8> |  |  | 0
| <Task 9> |  |  | 0
| <Task 10> |  |  | 0
| <Task 11> |  |  | 0
| <Task 12> |  |  | 0
| <Task 13> |  |  | 0
| <Task 14> |  |  | 0
| <Task 15> |  |  | 0

## Example Project Schedule
Cells to be completed
Inputs
Organisation name: | [Enter Organisation Name] |  | Stage 1 - name: | Mobilisation | [15 empty] | Stage 6 - name: |  |  |  |  | Readiness
Project start date: | 2026-06-01 |  | Stage 2 - name: | Planning & Design | [15 empty] | Stage 7 - name: |  |  |  |  | Implementation
Number of weeks: | 22 |  | Stage 3 - name: | Preparation | [15 empty] | Stage 8 - name: |  |  |  |  | Monitoring
|  |  | Stage 4 - name: | Delivery | [15 empty] | Stage 9 - name: |  |  |  |  | Handover
|  |  | Stage 5 - name: | Testing & Assurance | [15 empty] | Stage 10 - name: |  |  |  |  | Closure
[5 empty] | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21 | 21 | 21 | 22 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24 | 24 | 24 | 25 | 25 | 25 | 25 | 25 | 26 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | 30 | 31 | 31 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | 32 | 33 | 33 | 33 | 33 | 33 | 34 | 34 | 34 | 34 | 34 | 35 | 35 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | 36 | 37 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | 38 | 38 | 39 | 39 | 39 | 39 | 39 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 44 | 44 | 44 | 44 | 44 | 45 | 45 | 45 | 45 | 45 | 46 | 46 | 46 | 46 | 46 | 47 | 47 | 47 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 49 | 49 | 49 | 49 | 49 | 50 | 50 | 50 | 50 | 50 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 52 | 52 | 53 | 53 | 53 | 53 | 53 | 54 | 54 | 54 | 54 | 54 | 55 | 55 | 55 | 55 | 55 | 56 | 56 | 56 | 56 | 56 | 57 | 57 | 57 | 57 | 57 | 58 | 58 | 58 | 58 | 58 | 59 | 59 | 59 | 59 | 59 | 60 | 60 | 60 | 60 | 60
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22
Category | Task Description | Start Date | End Date | Duration | time axis 2026-06-01 to 2026-10-30
Mobilisation | Establish project setup and governance | 2026-06-01 | 2026-06-05 | 5
| Appoint Project Manager and core team | 2026-06-01 | 2026-06-05 | 5
| Confirm roles, responsabilities, and resourcing | 2026-06-03 | 2026-06-08 | 4
| Set up project communication channels | 2026-06-03 | 2026-06-08 | 4
| Secure office/workspace facilities | 2026-06-08 | 2026-06-12 | 5
| Establish financial management systems | 2026-06-08 | 2026-06-12 | 5
| Kick-off meeting with key stakeholders | 2026-06-12 | 2026-06-12 | 1
Planning & Design | Develop detailed project plan and milestones | 2026-06-08 | 2026-06-12 | 5
| Complete site feasibility assessments | 2026-06-08 | 2026-06-15 | 6
| Prepare budget and risk assessment | 2026-06-15 | 2026-06-22 | 6
| Finalise technical design specifications | 2026-06-15 | 2026-06-22 | 6
| Conduct energy demand analysis | 2026-06-15 | 2026-06-22 | 6
| Submit planning pre-application enquiry | 2026-06-15 | 2026-06-15 | 1
| Submit DNO grid connection application | 2026-06-15 | 2026-06-15 | 1
| Engage with stakeholders or community | 2026-06-15 | 2026-07-03 | 15
| Develop stakeholder engagement plan | 2026-06-22 | 2026-06-26 | 5
| Key risks and dependencies identified | 2026-06-22 | 2026-06-26 | 5
| Prepare procurement strategy | 2026-06-26 | 2026-07-03 | 6
Preparation | Receive planning pre-application advice | 2026-07-06 | 2026-07-17 | 10
| Receive DNO budget estimate/connection offer | 2026-07-06 | 2026-07-24 | 15
| Commission environmental impact assessments | 2026-07-06 | 2026-07-24 | 15
| Commission ground investigations | 2026-07-06 | 2026-07-20 | 11
| Commission structure surveys | 2026-07-06 | 2026-07-20 | 11
| Submit full planning application | 2026-07-20 | 2026-07-20 | 1
| Obtain necessary permits and consents | 2026-07-20 | 2026-08-07 | 15
| Finalise land/lease agreements | 2026-07-20 | 2026-08-03 | 11
| Prepare tender documents | 2026-07-24 | 2026-08-07 | 11
| Delivery partners and inputs confirmed | 2026-08-03 | 2026-08-10 | 6
| Issue procurement notices | 2026-08-07 | 2026-08-07 | 1
| Evaluate tender submissions | 2026-08-07 | 2026-08-21 | 11
Delivery | Award contracts to suppliers/contractors | 2026-08-24 | 2026-08-28 | 5
| Accept DNO connection offer | 2026-08-24 | 2026-08-28 | 5
| Order equipment or materials | 2026-08-28 | 2026-09-04 | 6
| Mobilise contractor teams on site | 2026-09-07 | 2026-09-11 | 5
| Complete civil and groundworks | 2026-09-14 | 2026-09-25 | 10
| Install energy generation equipment | 2026-09-21 | 2026-10-02 | 10
| Install energy storage systems | 2026-09-28 | 2026-10-07 | 8
| Complete electrical infrastructure works | 2026-09-28 | 2026-10-07 | 8
| Install monitoring and control systems | 2026-10-05 | 2026-10-09 | 5
| DNO completes connection works | 2026-09-28 | 2026-10-09 | 10
| Conduct progress reviews and site inspections | 2026-09-14 | 2026-10-09 | 20
Testing & Assurance | Complete equipment commissioning | 2026-10-05 | 2026-10-09 | 5
| Conduct system integration testing | 2026-10-05 | 2026-10-09 | 5
| Perform safety and compliance checks | 2026-10-09 | 2026-10-13 | 3
| Complete grid connection testing | 2026-10-09 | 2026-10-13 | 3
| Verify metering and monitoring systems | 2026-10-12 | 2026-10-14 | 3
| Obtain necessary certifications | 2026-10-12 | 2026-10-16 | 5
| Complete remedial works | 2026-10-14 | 2026-10-16 | 3
Readiness | Operational and stakeholder readiness confirmed | 2026-10-14 | 2026-10-16 | 3
| Complete operator training | 2026-10-05 | 2026-10-14 | 8
| Finalise operational procedures and manuals | 2026-10-05 | 2026-10-14 | 8
| Establish maintenance contracts | 2026-10-07 | 2026-10-14 | 6
| Confirm insurance arrangements | 2026-10-07 | 2026-10-14 | 6
| Brief local community and stakeholders | 2026-10-12 | 2026-10-16 | 5
| Complete pre-launch communications | 2026-10-14 | 2026-10-19 | 4
Implementation | Energise system and go-live | 2026-10-19 | 2026-10-19 | 1
| Monitor initial performance | 2026-10-19 | 2026-10-23 | 5
| Provide on-site support during early operation | 2026-10-19 | 2026-10-23 | 5
| Address any operational issues | 2026-10-21 | 2026-10-23 | 3
| Collect initial performance data | 2026-10-19 | 2026-10-23 | 5
Monitoring | Performance and delivery monitored | 2026-10-19 | 2026-10-23 | 5
| Track energy generation performance | 2026-10-19 | 2026-10-23 | 5
| Monitor system efficiency and reliability | 2026-10-19 | 2026-10-23 | 5
| Review financial performance against targets | 2026-10-21 | 2026-10-23 | 3
| Conduct regular stakeholder updates | 2026-10-21 | 2026-10-23 | 3
| Implement continuous improvement actions | 2026-10-23 | 2026-10-26 | 2
Handover | Transition to business-as-usual completed | 2026-10-23 | 2026-10-26 | 2
| Complete final documentation package | 2026-10-21 | 2026-10-23 | 3
| Transfer operational responsibility | 2026-10-23 | 2026-10-26 | 2
| Handover warranties and guarantees | 2026-10-23 | 2026-10-26 | 2
| Archive project records | 2026-10-26 | 2026-10-27 | 2
| Conduct lessons learned workshop | 2026-10-26 | 2026-10-27 | 2
Closure | Outcomes reviewed and project closed | 2026-10-26 | 2026-10-27 | 2
| Submit final grant claim and reports | 2026-10-26 | 2026-10-27 | 2
| Complete financial reconciliation | 2026-10-26 | 2026-10-27 | 2
| Conduct post-project evaluation | 2026-10-27 | 2026-10-27 | 1
| Celebrate and communicate success | 2026-10-27 | 2026-10-27 | 1
| Formally close project | 2026-10-27 | 2026-10-27 | 1
Formulas:
Mobilisation = NETWORKDAYS(D19,[Stage 1 - name:])