## Guidance
How to use the Risk Register Template
As part of your application, you’re asked to complete and upload a Risk Register. This helps you—and us—understand the potential challenges your project might face and how you plan to manage them.
Even if you're not used to risk registers, this simple guide will walk you through how to complete the template step by step.
What is a Risk Register?
A risk register is a document that helps you identify and manage things that could go wrong during your project. It’s not a sign you’re expecting failure—it’s a sign that you’re thinking ahead and being realistic and responsible.
Worked Example
The risks listed in the Examples Risk Register tab are for illustrative purposes only. They are not exhaustive and should not be copied directly into your application. Your risk register should reflect the specific circumstances,
risks and mitigation measures relevant to your project.
1. Risk Owner
This should link to Question 32 in the Deliverability section, which discusses the key personnel.
2. Risk Category
Before describing each risk, start by selecting a Risk Category. This helps group your risks and shows where challenges might arise in your project.
Here are the main categories to choose from:
1. Project Design / Definition / Planning Risks | [5 empty] | 6. Partners & Subcontractors – Suitability & Reliability Risks
Risks related to unclear goals, poor planning, or unrealistic timelines. | [5 empty] | Risks tied to the quality, experience, or dependability of subcontractors.
Examples: Vague objectives, underestimated delivery time, missing key milestones. | [5 empty] | Examples: Incomplete work, quality concerns, delayed handover.
2. Partner Risks | [5 empty] | 7. Costing Risks
Risks involving your delivery partners or collaborators. | [5 empty] | Risks that arise from cost misestimation or scope creep.
Examples: Partners withdrawing, delays in agreements, unclear roles. | [5 empty] | Examples: Underestimated material costs, unexpected inflation.
3. Resource Risks | [5 empty] | 8. Finance & Tax Risks
Risks related to staffing, equipment, or materials. | [5 empty] | Risks related to funding sources, cash flow, or tax obligations.
Examples: Not enough team capacity, staff turnover, supply chain delays. | [5 empty] | Examples: Delayed funding disbursement, exchange rate changes, VAT issues.
4. Client / Beneficiary Risks | [5 empty] | 9. Environmental Risks
Risks related to the people or communities you serve. | [5 empty] | Risks from environmental factors or sustainability issues.
Examples: Low engagement, difficulty recruiting participants, changing needs. | [5 empty] | Examples: Extreme weather, environmental damage, waste disposal issues.
5. Project Environment (Political / Legal / Regulatory) Risks | [5 empty] | 10. Other / Non-Identified Risks
External risks from changes in laws, politics, or compliance requirements. | [5 empty] | Risks that don’t fit into the categories above but are still important to flag.
Examples: New regulations, visa delays, legal disputes. | [5 empty] | Examples: IT failures, cyber threats, reputation risks.
3. Risk Description
Write a short, clear description of a potential risk to your project.
Examples:
Delays in supplier delivery
Key staff member leaving the team
Difficulty recruiting participants
Supply chain delays
Budget overruns
Think about risks related to time, budget, resources, delivery, stakeholders, environment, technology, and compliance.
4. Likelihood
Rate how likely it is that this risk will happen. You can use a simple scale:
Low (1) – Unlikely to occur
Medium (3) – Could occur occasionally
High (5) – Likely to occur
5. Impact
Rate how serious it would be if the risk did happen:
Low (1) – Small delays or inconvenience
Medium (3) – Noticeable impact on project delivery or quality
High (5) – Major impact; could threaten project success
6. Mitigation / Response Plan
Explain how you’ll reduce the chance of the risk happening or what you’ll do if it does.
Examples:
Identify backup suppliers
Cross-train staff to cover absences
Begin procurement early
Monitor budget monthly
This shows you’ve thought ahead and have a plan.
7. Further Action (Optional)
If the template has a space for extra comments, you can include things like:
Trigger events (what might signal this risk is about to happen)
Status updates
Related risks
8. Save and Upload
Once you're happy with your schedule:
1. Save the file as YourProjectName_Risk _Register.xlsx
2. Upload it with your grant application as instructed
Tips for Filling it Out
Focus on risks that could genuinely affect the delivery or success of your project.
Be honest: we’re not looking for “perfect” projects with zero risk—we’re looking for smart planning.
Register Template Description
Risk ID | Organisation Name | Risk Category | Risk Description | Likely causes of risk | Impact of Risk [1 to 5] | Likelihood of Risk [1 to 5] | Overall Risk [Calculated] | Control/Mitigation Measures | Mitigated Impact [1 to 5] | Mitigated Likelihood [1 to 5] | Mitigated Overall Risk [Calculated] | Further Actions Needed
[Identification number] | [Name of your organisation] | [Categorisation of risk] | [Briefly describe the risk—what could go wrong?] | [List the possible reasons this risk might happen.] | [Rate the impact if this risk occurs (1 = Low, 5 = High).] | [Rate how likely this risk is to happen (1 = Unlikely, 5 = Very Likely).] | [Automatic calculation multiplying Impact x Likelihood to get the overall risk score.] | [List the steps taken to reduce or manage the risk.] | [Rate the impact after applying control measures.] | [Rate the likelihood after applying control measures.] | [Automatic calculation multiplying Mitigated Impact x Mitigated Likelihood to get the overall risk score.] | [List any additional actions required to further reduce the risk.]
Common Terms to be Used for Risk Mitigation Strategies:
Decide not to take a risk – AVOID
Decide to accept the risk - ACCEPT
Decide to transfer the risk – SHARE*
Decide to reduce the risk - REDUCE
Note - to “share” a risk includes: transferring the risk, spreading the risk, insuring against the risk.
Risk Scoring Matrix
70%+ - event almost certain to occur in most circumstances | LIKELIHOOD | Probable | 5 | 10 | 15 | 20 | 25 |  | Level | Colour | Score Range
30-70% - event likely to occur in most circumstances |  | Likely | 4 | 8 | 12 | 16 | 20 |  | Low |  | 1 – 4
10-30% - event will possibly occur in some circumstances |  | Possible | 3 | 6 | 9 | 12 | 15 |  | Moderate |  | 5 – 12
1-10% - event unlikely but may occur at some time |  | Unlikely | 2 | 4 | 6 | 8 | 10 |  | High |  | 13 – 19
<1% - event rare and may only occur in exceptional circumstances |  | Rare | 1 | 2 | 3 | 4 | 5 |  | Very High |  | 20 – 25
|  |  | Negligible | Minor | Moderate | Major | Critical
IMPACT
|  |  | Insignificant increase to project time or cost. Barely noticeable impact on project scope or objectives. Minor errors or disruption Trust recoverable with little effort or cost Less than £50,000 | Less than 5% increase to project time or cost. Minor impact on project scope or objectives Some disruption to core activities / customers Trust recoverable at modest cost with resource allocation within budgets £50,000 to £350,000 | 5% to 20% increase to project time or cost. Major impact on project scope or objectives requiring sponsor approval. Disruption to core activities / customers Trust recovery demands cost authorisation beyond existing budgets. £350,000 to £1million | 20% to 50% increase to project time or cost. Impact on project scope or objectives unacceptable to sponsor. Significant disruption to core activities. Key targets missed. Trust recoverable at considerable cost and management attention. Financial cost: £1million to £5million | 50%+ increase to project time/cost. Strategic Aims compromised. Trust severely damaged. Financial cost >£5million

## Blank Risk Register
Project Risk Register
Cells to be completed
Risk ID | Organisation Name | Risk Owner | Risk Category | Risk Description | Likely causes of risk | Impact of Risk [1 to 5] | Likelihood of Risk [1 to 5] | Overall Risk [Calculated] | Control/Mitigation Measures | Mitigated Impact [1 to 5] | Mitigated Likelihood [1 to 5] | Mitigated Overall Risk [Calculated] | Further Actions Needed
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0

## Example Risk Register
Project Risk Register
Cells to be completed
Risk ID | Organisation Name | Risk Owner | Risk Category | Risk Description | Likely causes of risk | Impact of Risk [1 to 5] | Likelihood of Risk [1 to 5] | Overall Risk [Calculated] | Control/Mitigation Measures | Mitigated Impact [1 to 5] | Mitigated Likelihood [1 to 5] | Mitigated Overall Risk [Calculated] | Further Actions Needed
YC-R-01 | AB Community Energy CIC | Project Manager | Project Design / Definition / Planning | Planning permission for turbine installation is refused or significantly delayed | Local resident opposition, NRW concerns over ecology or landscape, inadequate pre-application engagement with Local Planning Authority | 4 | 3 | 12 | REDUCE – Appoint experienced planning consultant, conduct pre-application discussions with LPA and NRW, commission ecology surveys at earliest stage, establish community liaison group to address concerns proactively. | 3 | 2 | 6 | Prepare appeal strategy in advance, monitor application weekly once submitted. Trigger point: NRW consultation response received.
YC-R-02 | AB Community Energy CIC | Project Manager | Partner | A key delivery partner withdraws from the project or fails to fulfil their agreed role | Partner organisation facing internal financial difficulties, change in organisational priorities, unclear roles and responsibilities agreed at outset, delays in formalising partnership agreements | 4 | 2 | 8 | REDUCE – Formalise all partnership arrangements before project commencement, clearly define roles and responsibilities in the project governance structure, maintain regular partner liaison meetings, map potential alternative partners. | 3 | 1 | 3 | Review partnership agreements regularly, flag any signs of partner disengagement to the Board promptly. Trigger point: partner misses two consecutive steering group meetings.
YC-R-03 | AB Community Energy CIC | Project Manager | Resource | Project schedule slips beyond the Ynni Cymru Phase 3 grant award period due to cumulative delays | Planning determination taking longer than anticipated, grid connection timeline slippage, contractor mobilisation delays, adverse weather during the construction window | 4 | 3 | 12 | REDUCE – Develop detailed programme with critical path identified and contingency time built in, maintain regular milestone reporting, inform Ynni Cymru programme team proactively if delays arise, front-load tasks that can proceed independently such as ecology, surveys and community engagement. | 2 | 2 | 4 | Identify tasks that can be re-sequenced or accelerated to recover time, escalate to the Board immediately if a delay becomes unavoidable. Trigger point: any activity on the critical path delayed by more than 2 weeks.
YC-R-04 | AB Community Energy CIC | Community Engagement Lead | Client / Beneficiary | Loss of community support leads to formal objections and reputational damage to the project | Insufficient early engagement with local residents, perception that project benefits accrue to a small group rather than the wider community, concerns about construction noise, visual impact or increased traffic | 3 | 2 | 6 | REDUCE – Establish Community Liaison Group meeting at least quarterly throughout the project, publish regular plain-language newsletters, develop Community Benefit Fund governance framework and communicate it widely before construction commences, maintain a public complaints register. | 2 | 2 | 4 | Commission independent community survey at design stage to baseline attitudes, review engagement strategy if objections received. Trigger point: receipt of any formal objection to planning application
YC-R-05 | AB Community Energy CIC | Technical Lead | Project Environment (Political / Legal / Regulatory) | Grid connection offer from Distribution Network Operator (DNO) is delayed beyond project schedule or priced above budget | Existing capacity constraints on local distribution network, competing connection applications in the DNO queue, requirement for significant network reinforcement works identified | 4 | 4 | 16 | REDUCE – Submit grid connection application at earliest opportunity, conduct pre-application meeting with DNO to understand network constraints, obtain independent technical review of any offer received. | 3 | 2 | 6 | Review connection offer in detail upon receipt, assess alternative connection points if primary offer is unacceptable. Trigger point: DNO feasibility response received.
YC-R-06 | AB Community Energy CIC | Technical Lead | Partners & Subcontractors | The appointed EPC contractor delivers substandard work or fails to complete the installation within the agreed programme | Contractor lacks sufficient experience of community-scale renewable energy installations, inadequate site supervision, key subcontractor becomes unavailable mid-construction, contractor financial difficulties leading to insolvency | 4 | 2 | 8 | REDUCE – Carry out thorough due diligence on contractor financial standing and relevant experience during procurement, include robust performance and defects clauses in the construction contract, appoint independent technical adviser to oversee quality on site. SHARE – require contractor to provide a performance bond. | 3 | 1 | 3 | Conduct monthly site progress meetings, review contractor resourcing plan at mobilisation stage. Trigger point: contractor fails to meet first programme milestone.
YC-R-07 | AB Community Energy CIC | Finance Lead | Costing | Construction costs exceed the project budget due to unforseen circumstances, threatening financial viability | Unforeseen ground conditions identified during construction, contractor claims due to design changes, material price inflation exceeding forecast, supply chain delays increasing prelim costs | 4 | 3 | 12 | REDUCE – Procure contractor on fixed-price EPC contract, commission geotechnical survey before detailed design stage, agree robust change control process in the construction contract. SHARE – consider performance bond from contractor. | 2 | 2 | 4 | Monitor contract expenditure against budget monthly, escalate to Board if forecast outturn exceeds approved budget by more than 10%. Trigger point: first contractor payment claim received.
YC-R-08 | AB Community Energy CIC | Finance Lead | Finance & Tax | Delay in Ynni Cymru grant disbursement creates a cash flow gap and risk of contractor default | Grant claim documentation incomplete or queried by programme team, delays in Ynni Cymru internal approval process, mismatch between grant payment schedule and contractor payment milestones | 3 | 2 | 6 | REDUCE – Prepare and submit grant claims well in advance of payment deadlines, maintain thorough supporting documentation for each claim, keep a project cash flow forecast updated monthly. ACCEPT – retain a small working capital reserve to bridge short-term gaps. | 2 | 1 | 2 | Review grant claim process with Ynni Cymru at kick-off meeting. Trigger point: grant claim submitted but not approved within 20 working days.
YC-R-09 | AB Community Energy CIC | Technical Lead | Environmental | Protected species or habitats identified on or adjacent to the site during construction, causing work to be halted | Phase 1 habitat survey not carried out sufficiently in advance, emergence of protected species such as great crested newts or bats not identified at design stage, NRW issuing a stop notice following a complaint during construction | 4 | 2 | 8 | REDUCE – Commission Phase 1 habitat survey and any required Phase 2 surveys well in advance of construction, obtain all necessary licences before work commences, include ecological watching brief during groundworks, agree biodiversity net gain measures with NRW at pre-application stage. | 2 | 1 | 2 | Ensure ecologist contact details are available to site manager at all times, brief construction team on protected species protocols before mobilisation. Trigger point: any protected species sighting reported on or near the site during construction.
YC-R-10 | AB Community Energy CIC | Project Manager | Other / Non-Identified | Cyber attack or IT failure results in loss of critical project data or disruption to financial management systems | Use of unsecured personal devices to store project documents, absence of a formal data management policy, phishing attack targeting a staff member or volunteer with access to project accounts | 3 | 2 | 6 | REDUCE – Store all project documentation on a secure cloud-based platform with access controls and regular backups, implement two-factor authentication for all financial systems, provide basic cyber security awareness guidance to all staff and volunteers handling project data. | 2 | 1 | 2 | Review data management arrangements at project kick-off, ensure backup copies of all key documents are held securely. Trigger point: any suspected unauthorised access to project systems or accounts.
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0