# Business Case Templates

Business case stages should be iterative:

- The Strategic Outline Case (SOC) makes the case for change within the wider strategic context and tests alignment with national, regional and local strategies

- The Outline Business Case (OBC) assesses the best option for delivering the strategic objectives and benefits within the resource envelope available

- The Full Business Case (FBC) outlines how the project and its objectives and benefits will be delivered in terms of quality and value for money.

- The Business Justification Case (BJC) is single stage and needs to address all information required for SOC/OBC and FBC stages.

Avoid repetition:

- Do not repeat information in more than one section.

- But do, revisit the earlier business case (i.e. SOP, SOC or OBC) and confirm any key changes. If the business case remains the same, there is no need to repeat what was agreed at this previous stage.  Include cross-references to earlier documents where appropriate.

- Include any information requested through business case scrutiny addendums at the next stage of your business case.

Flag in the index where specific policy issues are addressed:

- Assessors may have ten or more business cases to read each month.  Make it as easy as possible for them to find the information they are looking for within the detailed business case.

- To assist, the Project Summary Proforma included in the front of this template must be completed at every stage and submitted with the Detailed Project Business Case as one document.

- This ensures all key programme and policy details are clearly signposted.

Keep it brief:

- Stay within the word limits.

- Be factual and concise; use bullet points where possible rather than lengthy narrative.

- Tables make financial information easier to analyse.

- A site plan is helpful for context.

- Include Welsh medium impact assessments and Active Travel Plans.

- Top five risks and mitigation actions is sufficient.

- Include photographs of current building.

Avoid annexes other than those requested by the Programme team:

- If information is important, include it in the main body of the business case

We do not need to see tender documents, At BJC and FBC stage, you only need to confirm that the final tendered costs are being presented within the business case

Project Summary Proforma

| LA / College Name |  |
| --- | --- |
| Project Title |  |
| Business Case Stage | SOC/OBC/FBC/BJC |
| Education Facility | Primary/Secondary/All-through/Special School/FE/Other – please specify. |
| Project Type | New build/Refurbishment/Extension |
| Primary purpose | Condition, suitability, increasing/decreasing capacity, Cymraeg 2050, rationalisation, improving access |
| Brief overview of project scope (max 100 words) |  |

Proposed Area:

|  | Area (m2) |
| --- | --- |
| New build |  |
| Light Refurbishment |  |
| Medium Refurbishment |  |
| Heavy Refurbishment |  |
| Total |  |

Breakdown of cost:

|  | Cost (£) | Cost per m2 (£) |
| --- | --- | --- |
| Construction cost |  |  |
| ICT |  |  |
| FFE |  |  |
| NZC |  |  |
| Abnormals |  |  |
| Irrecoverable VAT |  |  |
| Total |  |  |

Benefits

Please outline how the project supports the investment objectives of the Sustainable Communities for Learning Programme (max 100 words).

Strategic Case

School Organisation

Names of schools/campuses included as part of project:

Capacity:

|  | Existing | (FTE) | Proposed | (FTE) | Change | +/- |
| --- | --- | --- | --- | --- | --- | --- |
|  | EM | WM | EM | WM | EM | WM |
| Childcare Offer |  |  |  |  |  |  |
| Nursery |  |  |  |  |  |  |
| Primary |  |  |  |  |  |  |
| Secondary |  |  |  |  |  |  |
| Post-16 |  |  |  |  |  |  |
| Additional Learning Needs |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

Is a statutory consultation required in accordance with the School Standards and Organisation (Wales) Act 2013?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, please outline the timescales:

Planning of School/College Places

Pupil/Student Numbers for previous five years:

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Nursery |  |  |  |  |  |
| Primary |  |  |  |  |  |
| Secondary |  |  |  |  |  |
| Post-16 |  |  |  |  |  |
| Additional Learning Needs |  |  |  |  |  |
| Total |  |  |  |  |  |

Pupil/Student Projections for next five years:

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Nursery |  |  |  |  |  |
| Primary |  |  |  |  |  |
| Secondary |  |  |  |  |  |
| Post-16 |  |  |  |  |  |
| Additional Learning Needs |  |  |  |  |  |
| Total |  |  |  |  |  |

Please detail the methodology used to calculate these projections:

Please detail coordination of provision planning between education providers (both between schools or schools and colleges):

Sustainability

Confirmation that BREEAM Excellent, or higher, will be achieved?

Confirmation the scheme will be designed to achieve the Programme’s mandated Net Zero Carbon (NZC) standard. Please provide an overview of the NZC strategy (max 100 words).

Confirmation sprinklers will be installed:

| Yes |  | No |  |
| --- | --- | --- | --- |

If no, please confirm this is through prior agreement with Sustainable Communities for Learning Programme team:

Key security measures for consideration at school sites are outlined under the design guides at  www.securedbydesign.com,. Please indicate what measures you will be include for this project.

Planning / Land

Is a land acquisition required for the project? If so, please provide an overview of process and anticipated timescales (max 100 words).

Has the Town Centre First Principle been considered?

Please outline how the Town Centre First Principle has been considered.

Is planning permission required?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, have you engaged with the Local Planning Authority? Please provide a summary of considerations (will a PAC be required? Will Pre-app advice be sought?) (max 100 words).

Active Travel / Highways

Have you engaged with the Local Highway Authority and Active Travel Officer? Please provide a summary of considerations (max 100 words).

If the proposal involves changes to the location of one or more schools/ nurseries/ colleges, how does the proposed location support the sustainable transport hierarchy, which prioritises walking, then wheeling, then cycling, then public transport over private car use. (max 100 words).

How will you encourage pupils and staff to use walking, wheeling, cycling, and public transport to travel to and from school? (max 100 words).

|  | Yes / No | Please provide evidence and attach any relevant documents |
| --- | --- | --- |
| Have you undertaken any travel or traffic assessments? If so, please attach these. |  | E.g. traffic impact assessments |
| For new locations, please estimate the change in travel distances for pupils and staff and whether this was considered in determining the preferred option. |  | E.g. analysing pupil location data |
| Are your proposals already reflected on your local authority’s Active Travel Network Map? |  | (i.e. is the location connected to an existing or planned active travel route?) |
| If the location is not currently served by appropriate walking, wheeling and cycling routes, will these be in place by the time of opening? |  | E.g. Developer contribution, SRiC or AT Funding |
| What steps have you taken to minimise the need for car parking spaces on site? |  |  |
| Is there an Active Travel School Plan already in place? If so, please attach a copy. If not, when will it be prepared? And who will monitor the travel plan and review it on a regular basis? |  |  |
| Have you considered making the street outside the school a School Street? (A school street is where the area outside one or more schools is closed to traffic at the start and end of each school day) |  |  |
| Are there behaviour change or training programmes that will encourage and enable active travel already in place or planned? |  | E.g. Kerbcraft, cycle training, participation in Active Journeys, Walking promotion, cycle to work scheme, car / lift sharing? |
| Can you provide a site plan? The widths of routes on site, the location of access points and the number and location of cycle/ scooter/ pram storage? |  |  |

Flooding/Drainage

Will Sustainable Drainage Approval Body (SAB) approval be required?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, have you engaged with the SAB Authority? Please provide a summary of considerations. (max 100 words)

Does the project include an area within a flood zone as per the current and proposed technical advice note 15?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, please outline how this will be managed:

Welsh Language

How does the project support Cymraeg 2050 strategy and the authorities’ WESP or FE and Apprenticeship Welsh Medium Action Plan?

|  | How will the proposal support? |
| --- | --- |
| Local Authorities |  |
| Outcome 1 More nursery children/ three year olds receive their education through the medium of Welsh |  |
| Outcome 2 More reception class children/ five year olds receive their education through the medium of Welsh |  |
| Outcome 3 More children continue to improve their Welsh language skills when transferring from one stage of their statutory education to another |  |
| Outcome 4 More learners study for assessed qualifications in Welsh (as a subject) and subjects through the medium of Welsh |  |
| Outcome 5 More opportunities for learners to use Welsh in different contexts in school |  |
| Outcome 6 An increase in the provision of Welsh-medium education for pupils with additional learning needs (ALN) in accordance with the duties imposed by the Additional Learning Needs and Education Tribunal (Wales) Act 2018 |  |
| Outcome 7 Increase the number of teaching staff able to teach Welsh (as a subject) and teach through the medium of Welsh |  |
| Further Education |  |
| Ensuring that learners are provided with support and information to progress along the Welsh language continuum in post-16 education and training and onto post-19 where appropriate. |  |
| Create an improved infrastructure to enable learners to increase the level of learning undertaken through the medium of Welsh. |  |
| Build and extend existing staff development opportunities to enable post-16 education and training providers to increase the level of Welsh-medium provision. |  |
| Engage effectively with employers to enable effective skills planning to take place. |  |
| Learner Centred Approach; Prioritising the needs, experiences, and progression of learners |  |
| How will the proposed investment enhance the breadth and relevance of curriculum offer available to post 16 all learners across the region? |  |
| To what extent does the investment ensure alignment with statutory obligations under the Learning and Skills Measure? |  |

Has a Welsh Language Impact Assessment been undertaken?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, please provide a copy.

If no, please outline why this has not been required.

Curriculum for Wales: Enabling Learning

Please confirm outdoor learning; play based learning; inclusion and active learning have been considered. Does the environment offer independence; is it communication rich; promote physical activity; offer time for reflection; enable use of tools/equipment and evidence of rationale has been provided. (Max 100 words).

Digital Inclusion

Please confirm if you have considered public access to the to the school/college’s internet provision (e.g., guest Wi-Fi) and digital devices (e.g., laptops, tablets, PCs), in line with safety. What was the outcome?  (Max 100 words).

Community Access to Facilities

Please outline how the proposal facilitates (sports and non-sport) engagement with families, communities and multi-agencies. How do they support the needs of learners and families and benefit the wider community. Please detail how these will be managed. (max 200 words)

Sport Facilities

| Have you: | Yes/No? | Further details/evidence and attach separately, any relevant documents, as appropriate |
| --- | --- | --- |
| Consulted national and local stakeholders (e.g. Sport Wales, National Governing Bodies of Sport (NGBs), Play Wales community sports clubs etc.) on the sports facilities plans within your proposals? |  |  |
| Considered how the proposals will contribute to the Programme for Government commitments for sport and the Vision for Sport in Wales? |  |  |
| Considered how the proposed facilities fit with current local facility provision and demand e.g. have the proposals been considered in the context of the local authority or a National Governing Body of sport facility strategy? |  |  |
| Considered opening the facilities for wider community use in the evenings, weekends, and school holidays? |  |  |
| Engaged with external stakeholders to consider the needs of the local community and the potential for community use? |  | e.g. the results/outcome of any consultation exercise |
| Collaborated with your local authority sports development team/leisure trust to understand how the school facilities can be used for community sport and physical activity? |  |  |
| Considered how the community access might be maximised by ancillary facilities? |  | e.g. separate changing facilities, floodlights etc. |
| Considered/factored in measures to seek planning permission for floodlights and included the provision of the appropriate lux levels based on the sports that will use the facilities? If so, how has the potential for local opposition been mitigated? |  |  |
| Developed partnerships with community groups so that resources and expertise can be shared and used? |  |  |
| Used your School Sport Survey results to identify what physical and sporting activities your pupils would like to see on offer? |  |  |
| Understood which communities/local sports clubs your school facilities could benefit? |  |  |
| Considered/decided how the out of hours access (evenings, Weekends and school holidays) will be managed? |  | e.g. outsourcing the operational management to the sports development team, leisure trust or other local organisation |
| Considered how the use of school facilities for the community can become a sustainable model for the future? |  | e.g. will community access create a protected revenue stream for future facility upgrades? |
| Agreed a budget for the development of any proposed sports facilities, and an estimate of projected income from community access? Please provide details in the adjacent column. |  |  |
| In the case of artificial or grass pitches, have you consulted the relevant National Governing Bodies of Sport (e.g. the FAW, WRU and Hockey Wales or Sport Wales) if the pitch in question is to be used by community clubs? |  |  |
| Applied for any funding for the sports facilities from external sources such as Sport Wales, the Cymru Football Foundation, the Welsh Rugby Union, Tennis Wales or any other National Governing Body of Sport in Wales? |  |  |
| Included in your plans school sports facilities that are reliant on a successful application for external funds from any of the organisations listed above (Sport Wales, the Cymru Football Foundation etc.)? |  |  |
| Included in your proposals, details of the dimensions and markings for any pitches or playing surfaces? |  |  |
| Considered, in the case of artificial pitches, a sinking fund (an annual sum of £25k-£30k is recommended) for on-going maintenance costs/carpet replacement? |  |  |
| Explored the potential for collaborative funding for the sports facilities e.g. Sport Wales or National Governing Bodies such as the Cymru Football Foundation or the Welsh Rugby Union for team sports pitches, or Tennis Wales for overhead covers for tennis courts/MUGAs? |  |  |
| Factored into your proposals, the cost for the storage of portable sports equipment/furniture, such as goal posts, hoops, posts, nets etc. |  |  |
| Considered how to mitigate the potential environmental impact of the facilities or the impact of the natural environment around the proposed facilities? |  | e.g. the transfer of artificial grass pitch rubber crumb to the local environment or flooding from rivers, foliage from adjacent trees? |

Outdoor Play

| Have you: | Yes/No? | Further details/ evidence and attach separately any relevant documents, as appropriate |
| --- | --- | --- |
| Engaged with Local Authority Play leads to consider results of engagement from the Play Sufficiency Assessment? |  |  |
| Collaborated with Local Authority play leads to understand how the school facilities can be used to support the Play Action plan? |  |  |
| Used the Play Sufficiency assessment to identify what play activities your pupils would like to see on offer? |  |  |
| Considered how the proposal will meet the needs of children from different age groups? |  |  |
| Considered how the proposal will meet the needs of children with disabilities and/or additional learning needs? |  |  |
| Assessed the impact of the proposals for any possible negative impacts on your current outdoor play provision? |  |  |
| Considered opening the facilities for wider community use in the evenings, weekends, and school holidays? |  |  |
| Engaged with external stakeholders to consider the needs of the local community and the potential for community use? |  |  |

Economic Case

Short listed options: Please provide brief description of each shortlisted option.

|  | Option 1 | Option 2 | Option 3 | Option 4 |
| --- | --- | --- | --- | --- |

NPV quantitative assessment (£m), Appraisal period – To be completed at OBC, FBC and BJC

| CAPEX costs | £Xm | £Xm | £Xm | £Xm |
| --- | --- | --- | --- | --- |
| Total monetisable costs (NPC) | £Xm | £Xm | £Xm | £Xm |
| Total monetisable benefits (NPB) | £Xm | £Xm | £Xm | £Xm |
| Net present value (NPV) | £Xm | £Xm | £Xm | £Xm |

Broader assessment of options – To be completed at all stages

| Qualitative benefits | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) |
| --- | --- | --- | --- | --- |
| Risk assessment | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) |
| Overall ranking | Rank | Rank | Rank | Rank |

Preferred way forward? Why?

Financial Case

Size and Cost Standard

Is the scheme being designed in accordance with the Area Guidance for Schools in Wales or FE Space Norms? (Please outline which guidance has been used for the project)

Breakdown of areas:

| Schools | Proposed Area (m2) | Colleges | Proposed Area (m2) |
| --- | --- | --- | --- |
| Childcare |  | Please specify areas |  |
| Nursery |  |  |  |
| Primary |  |  |  |
| Secondary |  |  |  |
| Post 16 |  |  |  |
| ALN |  |  |  |
| Other (please specify) |  |  |  |
| Total |  | Total |  |

Please provide justification for any areas in excess of the relevant Building Bulletin or Space Norms.

Funding

Breakdown of funding

|  |  | Funding (£) | Percentage (%) |
| --- | --- | --- | --- |
| Welsh Government | Grant |  |  |
|  | General Capital Funding |  |  |
|  | Capital Receipts |  |  |
|  | S106 Contributions |  |  |
| LA/FEI | Reserves |  |  |
|  | Borrowing |  |  |
|  | Other Grant Funding |  |  |
| Total |  |  |  |

Please outline any other Welsh Government grants or other potential sources of funding allocated to support the proposal.

Are there any pending or planned applications from other potential sources of funding (e.g. Sport Wales or a National Governing Body of Sport) for sports facilities)?

| Yes |  | No |  |
| --- | --- | --- | --- |

If yes, please specify

Please confirm LA or College funding has been approved.

Commercial Case

How will the project be procured? (Max 100 words)

What are the proposed contractual relationships? (Max 100 words)

Status of project bank account? (e,g, in place, in tender requirements etc.)

Provide an overview of the approach to maximising community benefits? (Max 100 words)

Management Case

Overview of governance arrangements for project (max 100 words).

Overview of key project timeline / milestones

Detailed Project Business Case

Strategic Outline Case

Strategic Case (2,000 words)

Demonstrate how the project will meet the community’s needs.

- Strategic objectives

- Give a short description how the project supports existing policies and strategies of the organisation and other programmes and projects within the strategic portfolio.

- Wider context

- Give a short description how the project supports the Sustainable Communities for Learning Programme investment objectives, alongside existing policies and strategies of the Welsh Government including:

- The Wellbeing of Future Generations (Wales) Act 2015

- Taking Wales Forward

- Future Wales: The National Plan 2040

- Environment (Wales) Act 2016

- Cymraeg 2050: Welsh language strategy

- The Welsh in Education Strategic Plans (Wales) Regulations 2019

- Additional Learning Needs and Education Tribunal (Wales) Act 2018

- ALN Code for Wales

- Equality Act 2010

- Child Poverty Strategy

- Qualified for Life

- 30-hour childcare offer

- Welsh in Education Strategic Plans (WESP) – It is really important that your plans align with the WESP for your area. Please highlight how you will meet local needs for Welsh Medium provision/expand/move along the continuum.

- Local Development Plans

- Pupil numbers

- Llwybr Newydd – The Wales Transport Strategy

- Active Travel (Wales) Act 2013

- Environment (Air Quality and Soundspaces) (Wales) Act 2024)

- Town Centre First

- Community Focused Schools

- The School Organisation Code

- Wales: A Play Friendly Country

This list is not exhaustive and other relevant policies may be applicable.

1. EDUCATION

- Case for change

- Specify the spending objectives for the project. Theses should focus on the target outcomes and be SMART.

- Specify the main benefits associated with the achievements of the project’s spending objectives, including the benefits to all learners, including disadvantaged pupils Distinguish benefits from outcomes.

- Specify the main risks associated with the spending objectives and the proposed counter measures for avoidance, mitigation and management.

- Specify any constraints that have been places on the project.

- Specify any dependencies outside the school of the project upon which the success of the project is dependent.

- Demographics / catchment / demand

- What are the names and location of schools/colleges involved? (include the type of schools, age range and language provision)

- Where is the proposed location and why has it been chosen?

- What is the current capacity?

- What is the demand for places? (Provide evidence of future uptake if increase in demand is forecast).

- Include detail of all provision, including numbers of places (e.g. nursery, sixth form, additional learning needs centre)

- What is the impact on nearby schools/colleges (e.g. will it address sufficiency of places elsewhere?)

- Have the other schools/colleges been consulted/involved in developing the proposal?

- Childcare / early years provision

  - Do the proposals include provision for, breakfast clubs, Flying Start provision, after school care, holiday play schemes or wrap around childcare?

  - Is there sufficient outdoor and play-based learning provision?

  - What reference has there been to the Local Authority Childcare Sufficiency Assessment?

  - How will the proposals support Welsh Government’s Childcare Offer?

  - How will the project support the Cymraeg 2050 aim of expanding Welsh-medium childcare provision?

- Welsh medium education

- How will the project support the aims of Cymraeg 2050: A million Welsh speakers and the targets as set out in either the Welsh in Education Strategic Plan (WESP) or the local college’s Welsh-medium and Bilingual Strategy?

- How will the project impact on Welsh-medium education and training? Please note that assessing impact upon Welsh-medium provision is also a requirement with projects that may be deemed as English-medium.

- Does the project support co-location of provision where possible to encourage continuity and progression? For example, co-location of Welsh-medium childcare, Welsh-medium education, immersion provision.

- Active learning through effective environments

- Will the environment offer sufficient risk and challenge?

- Are emotionally safe spaces provided?

- Are sensory needs met?

- Have lighting; temperature and humidity been considered to ensure optimal comfort of staff and learners to focus on learning?

- Can authentic experiences be offered – both indoors and outdoors?

- Does the environment offer independence for learners; promote physical activity; offer time for reflection; enable use of tools/equipment?

- Is it communication rich?

- Optimise outdoor and play-based learning spaces including indoor/outdoor free flow; enabling developmentally appropriate pedagogy in all aspects for learners across the 3-16 continuum.

- Be mindful of space provided for uninterrupted play. For example, in Foundation Learning years a child should be able to leave what they are doing in their outdoor learning space to enjoy playtime/break and return to their outdoor learning. Rather than this being the same space for play-based learning and free play.

- For older learners it’s about active learning and providing engaging experiences.

- Additional learning needs provision

- Detail the needs of any learners/potential learners including bilingual learners.

- Are environments effective and inclusive to provide engaging experiences for all learners at all ages?

- What will the impact of the proposal be on these learners?

- What provision is there for children and young people experiencing difficulties/at risk of exclusion e.g. PRU provision on site/nearby.

- How will the proposal address projected demand for ALN provision and different types of need?

- How does the proposal contribute to ensuring there is sufficient additional learning provision in the area to meet the overall needs of the population of learners with ALN?

- How are you providing a more therapeutic and flexible learning environment for these learners?

- Disability

- Think about different types of disability, impairment, or long-term health condition. This also includes Deaf BSL users. Consider what barriers disabled people face. Can these barriers be reduced, removed or mitigated?

- Is the proposal consistent with authority’s accessibility strategy?

- Post 16

- What consideration has been given to collaborative working with local colleges, other schools, and 6th form centres to avoid working in competition or duplicating provision?

- How will the post-16 option proposed impact on educational outcomes including learner choice and class sizes?

- Has the impact on learner travel been considered?

- Does the proposal address the projected demand for post-16 additional learning needs provision?

- What consideration has been given to working with local authorities, other colleges, schools, housing associations etc to enable the delivery of local FE to more learners with complex ALN.

- Creating more opportunities for post-16 learners to learn and train through the medium of Welsh or bilingually is vitally important.  The Coleg Cymraeg Cenedlaethol has a specific role to work with colleges to increase capacity in the post-16 sector.  How will the proposal support learners to develop their Welsh language skills and contribute towards the aims set out in Coleg’s Further Education and Apprenticeship Welsh-medium Action Plan?

- How will welsh-medium and bilingual provision be increased and improved as a result of the proposal? In writing the proposal colleges should pay particular attention to the priorities for development identified by the Coleg Cymraeg Cenedlaethol - the designated senior manager with responsibility for Welsh language curriculum developments will be able to provide advice and guidance in this regard.

- Medr, the Commission for Tertiary Education and Research, encourages providers to consider how Sustainable Communities Capital Investment Proposals support the strategic direction set out in the Statement of Strategic Priorities under the Tertiary Education and Research (Wales) Act 2022. Whilst not all priorities will apply to every proposal, Medr is particularly interested in how investments contribute to:

- Widening access and participation

- Promoting lifelong learning

- Ensuring provision meets the needs of learners, employers, and communities

  - Consider how the proposed investment may support these aims—by addressing learner demand, aligning with regional and national skills needs, expanding qualification pathways, and ensuring facilities are adaptable and inclusive.

- Learner Centred Approach; Prioritising the needs, experiences, and progression of learners

Consider the following:

- How will the proposed investment enhance the breadth and relevance of curriculum offer available to post 16 all learners across the region?

- To what extent does the investment ensure alignment with statutory obligations under the Learning and Skills Measure?

- Period dignity

For toilet and changing room provision and refurbishment, please include in the business case how period dignity has been considered in your proposal. Consider the following:

- Can people access toilets where they can change, dispose or clean sanitary products ?

- Can people access private sinks (ideally within a private cubicle) in order to wash and prepare reusable period products?

- Have you considered the needs of transgender, non-binary and intersex young people when considering period dignity?  This may include ensuring sanitary bins and period products are available across all facilities.

- Equality Impact Assessment and Children’s Rights Impact Assessment

- Confirm that these assessments have been/will be completed.

- Youth Engagement

- Has there been consultation with learners and parents/carers in developing the proposal?

- Proposals must consider wider government priorities so that new buildings or refurbishments provide appropriate or flexible spaces to deliver Welsh Government education strategies including curriculum reform.

- Will the environment offer sufficient risk and challenge; are emotionally safe spaces provided; are sensory needs met; have lighting; temperature and humidity been considered; can authentic experiences be offered - again use of the outdoor space?

- Does the environment offer independence; promote physical activity; offer time for reflection; enable use of tools/equipment?

- Is it communication rich?

- Where the proposal relates to a school delivering pre-16 provision, does the proposed project enable effective realisation of Curriculum for Wales? How will it support learners to realise the four purposes? For example, does it consider open-plan areas, individual or quiet learning areas, discussion zones, innovative spaces to learn and play or outdoor learning facilities?

- School/College performance condition category and targets following project

  - Give details of current school performance along with proposed targets post project

  - What are the transitional arrangements for learners (e.g. how will learner outcomes be maintained during project; how will learners be supported through any potential disruption).

2. Built environment

- Planning: Site location

  - Is the site an existing school site/ allocated within a Local Development Plan/ a new site not allocated within a Local Development Plan? The proposal will need to demonstrate what alternatives have been looked at to ensure it is the most sustainable location. For example, demonstrating how the sequential test, as required by policy 6 of Future Wales, has been applied, avoiding areas of flood risk etc.

  - Does the proposed site enable walking, wheeling and cycling?

  - It is important that this analysis is undertaken at the very early stages of the project, ideally in the five year strategic plan/ strategic outline programme. With regards to sites not allocated within the Local Development Plan it is important at this early stage that the team speak to the local authority planners. It is at this early stage that it would be good to use the DCFW design review process to maximise the potential benefits more details of which are here Design Review Service - Design Commission for Wales (dcfw.org).

- Details of scheme: How does the proposal meet the relevant:

  - Strategic place making outcomes (page 19 PPW);

  - Policy 2 of Future Wales – Shaping Urban Growth and Regeneration – Strategic Placemaking.

  - How does the proposal align with the Regional Transport Plan and meet the relevant policies such as Llwybr Newydd: the Wales Transport Strategy 2021?

  - How does the proposal meet the relevant planning policy in Future Wales and the Local Development Plan

Examples of relevant policies:

- links to existing infrastructure and how these can be strengthened,

- provision of active travel and green infrastructure,

- opportunities for play,

- Opportunities for community sport provision

- net biodiversity benefit,

- provision of electric charging points,

- decarbonisation,

- how the proposal will prioritise active travel over the car.

- Active Travel

- Has there been engagement and clear collaboration with the Local Authority’s Active Travel officers, Road Safety officers, and Transport teams in the development of the proposals?

- Have direct, safe, and high-quality active travel routes to and from the site been identified? If gaps exist, have these been communicated to the Local Authority’s Active Travel team for prioritisation within the wider active travel network map planning process?

- How will the school promote sustainable travel modes?

- Will there be adequate facilities for cycle/scooter storage?

- How is the project reducing reliance on private car use?

- Does it include a strategic reduction in car parking provision, particularly for short journeys that could be made actively?

- Are there safe and well-managed drop-off/pick-up zones for school or college buses that avoid congestion and enable safe walking, wheeling, and cycling on site?

- Does the design incorporate opportunities for play, social interaction, and outdoor learning along active travel corridors and within the site, contributing to placemaking and wellbeing?

- Is there provision for secure cycle, scooter, and pram parking (where appropriate), as well as changing facilities and other infrastructure that supports walking, wheeling, and cycling as a default choice?

- Has a site-specific Active Travel School Plan (ATSP) been developed as part of the wider transport planning process to embed active travel into the school’s ethos and operations?

- Where appropriate, how will the school or college site function as a community hub, encouraging walking, wheeling, and cycling beyond the school day and supporting wider modal shift in the local area?

- Learner Travel

- What is the expected catchment area, and how will pupils and staff travel to the site?

- Has the local authority assessed the travel needs of learners in their area in accordance with their statutory duty under the Learner Travel Measure 2008?

- Has the local authority/Further Education Institution assessed the potential travel needs of learners who will attend the school or college?

- What will be the impact on the number of learners eligible for free transport under the age, distance, aptitude criteria? Have the ongoing cost implications/resource availability of this been considered?

- What is the impact on journey times between home and school/college?

- Has the local authority risk assessed the walked routes to school/college?

- What will the impact on learner travel be? Will the project reduce or increase the opportunities for learners to walk or cycle to school/college?

- What are the legislative, cost, time, or practical implications of Covid restrictions, and will this alter travel plans?

- Is the site accessible by existing public transport services? Will additional bus or rail services be required?

- Has a traffic impact assessment been completed? What is the projected increase in traffic volumes during peak school hours? What measures will be implemented to mitigate congestion and improve road safety?

- How many parking spaces will be provided for staff and visitors? Will there be EV charging facilities?

- Are upgrades to local roads, junctions, or pedestrian crossings required?

- Town Centre First

- The Welsh Government is keen to promote the use of town centre locations for new developments where this is appropriate. Is the proposed project located in a town centre? If not, please explain why a town centre location would not be appropriate/possible.

- A map or reference to the precise location should be included.

- Play Wales

- Which national/local stakeholders (e.g. Play Wales, community organisations) have you discussed proposals with?

- How will the proposals maximise play opportunities during and beyond the school day?

- What are the proposed plans for community use of outdoor play spaces?

- How will play facilities contribute to wellbeing, inclusion, and tackling poverty in the local community?

- How will schools provide time, space, and freedom for play, recognising its role in fostering inclusion, mental health, and positive educational outcomes?

- Have schools considered Play Wales’ guidance on opening school grounds for play outside teaching hours, and how will this be implemented to support community wellbeing?

- Sport Wales

- Which national and local stakeholders (e.g. Sport Wales, National Governing Bodies of Sport, community sports clubs) have you discussed your proposals with?

- How do the proposals contribute to Programme for Government commitments for sport and the Vision for Sport in Wales?

- How will the proposed facilities fit with current local facility provision and demand (e.g. local authority or National Governing Body facility strategies)?

- What are the proposed plans for community use? What is needed to maximise usage (e.g. hall/MUGA/pitch markings, floodlights, separate changing facilities)?

- What are the staffing arrangements/operating model for community use in the evening, at weekends, and during school holidays?

- In the case of artificial or grass pitches, have you consulted the relevant National Governing Bodies of Sport (e.g. FAW, WRU, Hockey Wales, Sport Wales) if the pitch is to be used by community clubs?

- In the case of artificial pitches, has a sinking fund (an annual sum of £25k–£30k is recommended) been factored in for ongoing maintenance costs/carpet replacement?

- Have you explored collaborative funding opportunities for the sports facilities (e.g. Sport Wales, Cymru Football Foundation, WRU, Tennis Wales)?

- Have you applied for any funding for the sports facilities from external sources such as Sport Wales, Cymru Football Foundation, WRU, Tennis Wales, or other National Governing Bodies of Sport in Wales?

- Are your plans for the school sports facilities reliant on a successful application for external funds from any of the organisations listed above?

- Do the proposals for an artificial grass pitch/pitches include mitigations for potential negative environmental impact (e.g. transfer of rubber crumb to the local environment)?

- Does the budget include costs for the storage of portable sports equipment/furniture (goal posts, hoops, nets, etc.)?

- Do the proposals include measures to seek planning permission for floodlights and provide appropriate lux levels based on the sports that will use the facilities? If so, how has the potential for local opposition been mitigated?

- Do the proposals for the location of outdoor pitches consider the potential impact of the natural environment (e.g. flooding from rivers, foliage from adjacent trees)?

- How will the proposed facilities fit with current/local facilities?

- Have the proposals reflected the contents of Facilities for Future Generations: a blueprint for sport and active recreation in Wales and used its framework where appropriate?

- Have schools considered Sport Wales’ advice and toolkit on community use of school sports facilities (e.g. Opening Schools Facilities Toolkit)?

- Community Focused Schools

- What are the proposed plans for community use, including access to services and programmes which support community resilience and contribute to tackling poverty?

- What other facilities will be available for community use (e.g. room hire, adult/community learning spaces)?

- Has the school/college considered allowing public access to the school/college’s internet provision (e.g., guest Wi-Fi) and digital devices (e.g., laptops, tablets, PCs), in line with safety? This will ensure support for people in Wales who are below the ‘minimum digital living standard’ and/or face barriers to accessing services.

- How will the school/college ensure community engagement is embedded in the design and operation of facilities?

- How will approaches be developed in partnership with and tailored to the specific needs of children, young people, families, and communities, in line with the Community Focused Schools model?

- Play Sufficiency Duties

- How does the proposal align with the outcomes or actions of your Play Sufficiency Assessment (PSA)?

- Have you consulted with the local authority play team?

- How are the needs of children with disabilities and or Additional Learning needs being considered in the proposal?

- Are play opportunities tailored to meet the needs of children across different age groups?

- Have you assessed the project for any negative impacts on existing play provision?

- Have you considered opening the facilities for wider community use in the evenings, weekends, and school holidays?

- Have you engaged with external stakeholders to consider the needs of the local community and the potential for community use?

- Environment (Wales) Act 2016

- Section 6 of the Environment (Wales) Act 2016 requires public authorities to maintain and enhance biodiversity and the resilience of ecosystems in the exercise of its functions. The provision of bio-diverse green infrastructure by public authorities helps them to comply with their statutory duties, as well as deliver their well-being objectives where they are also a public body subject to the Well-being of Future Generations Act 2015.

- The Welsh Government has an ambition of a carbon neutral public sector by 2030. How energy efficient are the designs? Have you looked at onsite or nearby development of renewable energy generation, including low carbon heating.

- Recognition of the role that renewables play in effective long term cost, environment and wellbeing solutions.

- Have you considered Electric vehicle charging infrastructure and the source of power, for instance solar car ports.

- Do you have water and recycling and waste management plans e.g. passive ventilation, use of sustainable urban drainage and the options for tree planting and green spaces.

- Water quality initiatives in the form of sustainable drainage systems at ground level, such as ponds and swales, and at building level in the form of green roofs and walls

- Creation of ecologically resilient habitats on the new site should be included within the business case.

- Plans on creating areas of biodiversity, any provision that would contribute to improving air quality and decarbonisation. Actions and works to improve the existing natural features that add to a school’s sense of place e.g. hedgerows, trees, earth banks and historic features or landscape character.

- Planting of individual or small groups of trees for parkland, hedgerows, orchards and wildflowers to increase connectivity between habitats to directly benefit wild pollinators and increase resilience of our biodiversity. All these provide opportunities for food growing initiatives, outdoor learning and screen from sources of air pollution such as roads

- Installation of bird boxes in appropriate locations

- How links to any neighbouring natural environment features, that could range from green space to a national park, have been enhanced

- Fencing and other measures to improve biosecurity and animal health and welfare

- Development of interpretation materials and visitor information (e.g. habitats and species, ecosystem services and historic environmental features)

- Provision of bike/scooter storage and wider action plans for Active Travel

- Ensuring no net loss of playing fields and green spaces. If so, what will be done to mitigate the effects of this? Has engagement taken place with the local authority’s green space team?

- How will future SuDS and green spaces be maintained? Have attempts been made to apply the Building with Nature Standards?

- Please refer to https://www.buildingwithnature.org.uk/how-it-works for more information.

- What construction materials are being used?  Where do they come from? can you incorporate reused or recycled components? Has Welsh timber been considered?

- Renewable energy generation.

- Net Zero Carbon

- For new build projects, please include in the business case:

- assurance that net zero carbon in operation and the relevant embodied carbon target will be achieved.

- how the energy usage will be monitored and reported on for the 5 years, and as a pilot what will be provided in the form of a lessons learnt report at the end of the project.

- NPV calculations will need to show cost per tonne of CO2 saved.

- Completion of the net zero carbon valuation spreadsheet.

For refurbishment projects, please include in the business case:

- evidence of the current operational carbon used and that saved, and to achieve net zero both must be equal or the saving being more to show negative carbon.

- NPV calculations will need to show cost per tonne of CO2 saved.

- Completion of the net zero carbon valuation spreadsheet.

- Biodiversity and Resilience of Ecosystems duty

In line with the Wellbeing of Future Generations Act and the Environment (Wales) Act 2016, the SCfL Programme encourages projects to contribute to environmental sustainability and ecosystem resilience. This includes integrating green infrastructure and biodiversity into the design and delivery of learning environments.

Projects may wish to explore opportunities such as:

- Increasing Biodiversity Net Gain

- Improving Green Space ratios

- Planting trees and supporting rewilding initiatives

- Incorporating biophilic design elements, such as living roofs and walls

These considerations help public authorities meet their duties under Section 6 of the Environment Wales Act, which requires them to maintain and enhance biodiversity and promote ecosystem resilience. In doing so, Local Authorities should take account of factors such as:

- diversity between and within ecosystems

- the connections between and within ecosystems

- the scale of ecosystems

- the condition of ecosystems (including their structure and functioning)

- the adaptability of ecosystems.

- Secure by design

- Secured by Design (SBD) is the official police security initiative that is owned by the UK Police Service. It has the specific aim to reduce crime and help all people to live and work more safely. It provides recognised standards that have been shown to reduce crime and the fear of crime.

- Terrorist attacks within the UK have become a distinct possibility in recent years, posing a real and serious threat. Measures to mitigate against crime and the occurrence and effects of it, should be designed in from the outset of a new school development proposal. This can also reduce the vulnerability from a terrorist attack.

- Designing Out Crime Officers (DOCO’s) and Counter Terrorism Security Advisors should be consulted at an early stage in the design process, to ensure new school developments contain appropriate design solutions, which mitigate the potential level of risk of crime and terrorism, whilst ensuring the quality of the new school estate.

- It is desirable that all new school developments in Wales, especially those funded by Welsh Government, followed the principles of the Secured by Design Gold Award.

- The Secured by Design Schools document can be found on the Secured by Design website www.securedbydesign.com under Design Guides.

Economic Case (2,000 words)

Demonstrate that the project provides good value for money

Outline the purpose of this specific economic case and discuss the rationale for intervention with link to economic principles such as positive externalities and market failures. Ensure that a strong case for change has been presented.

- SMART Investment objectives

These should align with your wider programme objectives but can be amended slightly for specific projects. We would expect to see not more than 5 or 6 SMART objectives or they are likely to lack focus, these objectives usually (but not always) fall into categories such as:

- Capacity/coverage (e.g., providing sufficient school places or increasing availability of specific services)

- Quality/outcome (e.g., improving user experience or ensuring minimum service standards are met)

- Efficiency/economy (e.g., reducing operating costs or improving productivity)

- Resilience/sustainability (e.g., ensuring long term viability and reducing environmental impacts)

- Equity/fairness (e.g., improving access for disadvantages groups/reducing levels of inequality)

N.B It is important to note that objectives should not simply describe an option, they should be identified at the outset and define what success looks like from the investment as opposed to pre-judge how it will be achieved. This ensures the appraisal can consistently benchmark options on their ability to address a problem and be judged against the same criteria.

- Critical success factors

These should differ from your objectives and be more specific to the appraisal decision. They should define attributes that any successful proposal must have to achieve delivery of its objectives. The Green book states that most cases only need five standard CSF’s, however it recognises that an additional one or two additional factors may be required and that the total number of CSFs should not exceed seven. The key critical success factors reference in the Green Book include:

- Strategic fit and meeting business need

  - Potential value for money

  - Supplier capacity and capability

  - Potential affordability

  - Potential achievability

- Generate the long list of options

A wide range of options should be generated to show that all possibilities have been considered.  Long list appraisal creation should be conducted by utilising the knowledge of all relevant experts on the project (usually through a workshop) The options framework below can be used to help generate the long list:

- Scope – What could be done and where? This sets clear boundaries on what costs and benefits can be included in the appraisal

- Service solution – How could it be done? e.g. new build. This allows you to clearly communicate what differs across your options

- Service delivery – Who could deliver the provision?

- Implementation – When could it be done? Does it need to be phased?

- Funding – How could it be funded? e.g. Capital or through the Mutual Investment Model.

- Narrowing down to the short list

These options should be examined as a group exercise and that you record the time, date and attendees involved in this process.

To narrow down the long list, the following process should be undertaken:

- The options should be assessed directly against both the investment objectives and critical success factors, indicating which are met, partially met or not met

- Provide a brief summary of the main advantages and disadvantages

- Decide whether the option should be carried forward or discounted.

Following this analysis, a short list of options is identified that will be taken forward for more detailed analysis in the OBC.  Describe the short list. This should include a minimum of 3-5 options, including:

- A quantified Business as Usual (this is used as the benchmark counterfactual)

- A realistic do minimum based on the core requirements for the project

- The recommended preferred way forward

- One or more possible options based on a more and/or less ambitious combinations of the preferred way forward.

- Qualitative benefits template

At SOC stage, the qualitative benefits table is used to compare how well each of the shortlisted option delivers against the programme’s strategic objectives, where benefits cannot yet be fully quantified. It provides a structured, narrative-based assessment that helps decision makers understand the relative strengths, weaknesses and differentiating features of each option before moving into more detailed economic appraisal

N.B The qualitative benefits table must be included in the main body of the Economic Case so that the key comparative insights directly inform the narrative and support the reader’s understanding of why the preferred option represents the strongest overall strategic fit.

- Quantitative benefits template

This provides a summary of the main quantitative benefits, including improvements in condition and suitability, numbers of places and reduction in backlog maintenance after completion of works. This should be filled in as much as possible at this stage for all short-listed options.

It is also a place to record the indicative economic costs for the shortlisted options.  Remember to also make allowances for optimism bias, particularly in the absence of more detailed risk appraisal.

Commercial Case (250 words)

Demonstrate that the project is commercially viable

- Procurement approach / Framework

- Social Value (SV) and Community Benefits (CB) approach – confirmation that a plan for community benefit / social value objectives will be developed.

- Project Bank Accounts (PBA) – confirmation that PBA policy will be complied with and is included in tender documentation, or that a PBA is already in place.

- Projects relying on a Section 106a agreement to deliver the facilities on behalf of the local authoritywe would expect the delivery partner to have a PBA in the s106a agreement.

Financial Case (250 words)

Demonstrate that the project is affordable

- Financial forecast including indicative cash flows

- Funding requirements

- Source(s) of matching funding

- Assessment of the project costs against Welsh Government cost per m2 benchmark and FF&E and IT costs per pupil are set out in Annex 6.

- Highlight any known abnormal costs

- Estimated NZC costs or irrecoverable VAT where applicable.

Management Case (250 words)

Demonstrate that the project will be delivered effectively

- Project management methodology i.e. MSP/Prince2

- Key risks and mitigations

- Key milestones / project programme

- Social Value and Community Benefits reporting

Outline Business Case

Strategic Case (500 words)

Demonstrate how the project will meet the community’s needs

- Changes since SOC was approved

- Date SOC was approved

- Detail any addendum responses from the SOC stage to avoid repeated queries.

Economic Case (3,000 words)

Demonstrate that the project provides good value for money

- Investment objectives and critical success factors

- Short list appraisal – costs and benefits

- Risk assessment

- Preferred option

The Economic Case should be comprehensive at OBC stage and will not be accepted unless it contains all the necessary content. The requirements of this section at this stage are to:

- Summarise the findings from the SOC and update with any changes;

- Calculate net present values (NPVs) for all short-listed options;

- Provide an assessment of the benefits for all short-listed options; preferably the case will attempt to quantify benefits but where this isn’t possible an in depth qualitative analysis should be conducted.

- Provide an assessment of the risks (including optimism bias) for all short-listed options;

- Conduct sensitivity analysis to test the robustness of the preferred option.

Summarise and update findings from SOC

- Firstly, this section should include confirmation that the Investment Objectives and Critical Success Factors identified in the SOC have been revisited and have not changed.

- It should briefly restate the long list of options and provide a summary of how this was narrowed down to a short list.

- If this has changed since SOC stage, the process needs to be restated in full with clear explanations for decisions on whether options should be taken forward. The new short list should then be taken forward for detailed analysis.

Calculate net present values (NPV)

- NPV should be calculated in order to assess which option offers the best value for money over the expected life of the building. This is generally 30 years for a refurbishment and 60 years for a new build. The economic analysis focusses on value for money and should:

- use constant (base year) prices

- include opportunity costs

- include all quantifiable costs, benefits and risks to both the organisation and wider society

- include environmental costs; make allowances for optimism bias

- exclude all Exchequer ‘transfer’ payments – for example, VAT

- exclude general inflation

- exclude sunk costs

- exclude depreciation and capital charges.

A summary of what should be included is:

Costs

- Costs of the build

- Costs of ongoing maintenance and running the building (this could also be a cost saving)

- Any other financial costs from operating e.g. transport

- The value of existing assets to reflect their opportunity cost

- Any transactions to buy land /assets

Benefits

- The sale of existing assets

- The expected residual value of the site(s) recorded as a benefit

- Any revenue received recorded as a benefit.

- Time savings from increased productivity / efficiency Transport savings

- Economies of scale achieved from consolidating sites

- Education outcome based benefits such as improved attendance or reduced exclusions or ALN placement costs

Please see Options Appraisal Template – worked example (Annex 4) and Options Appraisal Template – blank (Annex 5). For revenue funded projects this would have been completed at SOC.

The results from the options appraisal should be the primary criteria to decide which option offers the best value for money, however a broader assessment of the options should be conducted to provide a robust, rounded narrative. This should include:

An assessment of the benefits:

- Quantitative benefits (NPV + quantitative benefits table) - Your NPV analysis and updated quantitative benefits table should be complete and together provide the core quantified assessment of each shortlisted option. These should capture the improvements in condition and suitability, number of places, reduction in backlog maintenance and other measurable benefits expected to arise from completion of works.

- Qualitative benefits (qualitative benefits table) – To complement the quantitative assessment, an updated qualitative benefits table should also be provided. This should have been complete at SOC, but at OBC we expect greater detail and clearer differentiation between shortlisted options, focusing on any significant additional benefits that cannot be monetised but are important in the context of the project, especially where these help explain why an option with negative NPV may still represent overall value.

- This assessment should complement the findings from the NPV rather than be considered the primary criteria.

N.B. The qualitative benefits table must be included in the main body of the Economic Case, so that the narrative clearly reflects both quantitative and qualitative evidence when explaining the preferred option.

An assessment of risks

- This should assess different types of risks associated with each short-listed option. It should consider the likelihood of risks occurring and their potential impact. Weighting and scoring can be used and recorded in like in the table below:

| Type of risk and Weight | Option 1 |  |  | Option 2 |  |  | Option 3 |  |  | Option 4 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact (I), Likelihood (L) and risk score (S) | I | L | S | I | L | S | I | l | S | I | L | S |
| Risk 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |
| Rank |  |  |  |  |  |  |  |  |  |  |  |  |

This assessment is not an isolated process and should be linked with a risk register and inform the calculation of optimism bias. Details of how risks will be monitored and been mitigated should be noted as part of a risk register. A judgement on risks and how well they can be mitigated should inform the optimism bias calculation. A template for calculating optimism bias is included within the NPV template spreadsheet.

Based on the results of the analysis, the preferred option should then be identified as the best value for money.

Sensitivity analysis

It is important that the robustness of the preferred option is tested through sensitivity analysis. This ensures that even if there are a rise in costs, a shortfall in benefits or both, that the preferred option still represents the best value for money. This can either be done using switching values or scenarios.

Summary

A summary of the analysis must be provided to show that the preferred option remains robust. A conclusion should be reached and a summary statement providing a clear narrative of the reasoning for the preferred option should be provided alongside a summary table shown below.

|  | Option 1 | Option 2 | Option 3 | Option 4 |
| --- | --- | --- | --- | --- |

| NPV quantitative assessment (£m), Appraisal period |  |  |  |  |
| --- | --- | --- | --- | --- |

| CAPEX costs | £Xm | £Xm | £Xm | £Xm |
| --- | --- | --- | --- | --- |
| Total monetisable costs (NPC) | £Xm | £Xm | £Xm | £Xm |
| Total monetisable benefits (NPB) | £Xm | £Xm | £Xm | £Xm |
| Net present value (NPV) | £Xm | £Xm | £Xm | £Xm |

| Broader assessment of options |  |  |  |  |
| --- | --- | --- | --- | --- |

| Qualitative benefits | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) |
| --- | --- | --- | --- | --- |
| Risk assessment | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) |
| Overall ranking | Rank | Rank | Rank | Rank |

Commercial Case (1,000 words)

Demonstrate that the project is commercially viable

- Procurement approach / Framework

- Market testing

- Procurement plan and milestones

- Evaluation and award criteria

- Community benefits plan - confirmation that a plan for community benefits / social value objectives will be developed.

- Project Bank Account (PBA) – confirmation that PBA policy will be complied with or details of the compelling reason(s) why a PBA is not considered appropriate

- Projects relying on a Section 106a agreement

- We would expect the delivery partner to have a PBA in the s106 agreement. Where this is not possible, we would expect to see sound reasons why a PBA could not be applied and evidence that prompt and fair payment terms would be in place.

Financial Case (500 words)

Demonstrate that the project is affordable

- Financial forecast

- Funding requirements

- Source(s) of matching funding

- Risk assessment

- Cabinet or Board commitment, including date of approval

- Size and cost benchmark appraisal

- Project Cost Template (PCT) which should include a detailed breakdown of abnormal costs and estimates for NZC and irrecoverable VAT where applicable.

Management Case (500 words)

Demonstrate that the project will be delivered effectively. Detail the approach for the following:

- Project resources

- Contract management

- Benefits realisation arrangements

- Community Benefits and Social Value reporting arrangements

- Risks and mitigation

- Project assurance

- Key milestones / project programme and contingency arrangements

Full Business Case

Strategic Case (500 words)

Demonstrate how the project will meet the community’s needs

- Changes since SOC and OBC were approved

- Date SOC and OBC were approved

- Detail of any addendum responses from the SOC or OBC to avoid repeated queries.

Economic Case (500 words)

Demonstrate that the project provides good value for money

- Changes since SOC and OBC were approved

- Confirmation of HM Treasury Green Book compliance

As this section has been covered in detail at OBC stage, there is no need to restate the case in detail, although where changes have occurred, consider whether or not these changes would materially impact upon the ranking of the options achieved at OBC, and record your conclusions. This is of particular importance when there is a significant increase in costs.

This section should restate the investment objectives and critical success factors, highlight any changes since OBC, and confirm that all economic appraisals have been carried out in accordance with HM Treasury’s Green Book as well as updating NPV calculations to account for mature costs and benefits, optimism bias levels and risk assessments.

An updated Project Benefits (both quantitative and qualitative) and summary table is required at FBC, identifying any changes since OBC.

Commercial Case (1000 words)

Demonstrate that the project is commercially viable

- Confirmation of procurement route taken

- Negotiated deal and contract arrangements

- Risk transfer agreements

- Community benefits schedule – setting out the Community Benefits / Social Value objectives of the project including the preferred reporting mechanism for the outcomes against the objectives – either the Community Benefits Measurement Tool or National TOMs for Wales

- Confirmation of Project Bank Account arrangements

  - Which bank will be used to service the PBA?

  - What type of account will be used, Joint or Sole account or

  - Details of the compelling reason(s) why a PBA is not considered appropriate

- Projects relying on a Section 106a agreement to deliver the facilities on behalf of the local authority, we would expect the delivery partner to have a PBA in the s106 agreement.

Financial Case (1000 words)

Demonstrate that the project is affordable

- Financial forecast

- Final tendered project costs

- Finalised sources of matching funding broken down by source (capital resources, borrowing etc.)

- Size and cost benchmark appraisal

- Project Information Proforma (PIP)

- Project Cost Template (PCT) which should include a detailed breakdown of abnormal costs and estimates for NZC and irrecoverable VAT where applicable.

- Final cabinet or Board approval

- Details of any revenue savings

- Details of any other WG funding streams (e.g. Childcare Capital Grant)

Management Case (1000 words)

Demonstrate that the project will be delivered effectively. Finalise arrangements and plans for the following:

- Project delivery

- Statutory procedures

- Risk register (top 5)

- Benefits realisation

- Social Value and Community Benefits reporting arrangements

- Project assurance

- Change and contract management

- Post project evaluation

- Updated project milestones / programme and contingency arrangements

Business Justification Case

Please ensure that all SOC/OBC/FBC information is included within your BJC.

Strategic Case (1,500 words)

Demonstrate how the project will meet the community’s needs

- Strategic Rationale

- Give a short description how the project supports the Organisation’s policies and strategies and alignment within the wider programme of investment.

- Identify how the project aligns with the Sustainable Communities for Learning Programme investment objectives, alongside existing policies and strategies of the Welsh Government.

- Case for change

- Specify the main benefits associated with the achievement of the project’s spending objectives, including the benefits to all learners, including disadvantaged pupils. Distinguish benefits from outcomes.

- Specify the main risks associated with the spending objectives and the proposed counter measures for avoidance, mitigation and management.

- Specify any constraints that have been places on the project.

- Specify any dependencies outside the school of the project upon which the success of the project is dependent.

- Demographics / catchment / demand

- What are the names and location of schools/colleges involved? (include the type of schools, age range and language provision)

- Confirm the existing and proposed capacity of the school or college following investment.

- Can the number of ALN places be identified separately?

- Provide evidence of current and future demand for school places.

- What is the impact on nearby schools/colleges (e.g. will it address sufficiency of places elsewhere?)

- How will the project support the aims of Cymraeg 2050: A million Welsh speakers and the targets as set out in either the Welsh in Education Strategic Plan (WESP) or the FEI’s Welsh-medium and Bilingual Strategy?

- Additional learning needs provision

- Detail the needs of any learners/potential learners including bilingual learners.

- What will the impact of the proposal be on these learners and on the sufficiency of ALN provision in the area?

- How will the proposal affect the ability of the LA/school/college to meet the needs of learners in ALN?

- Post 16

- What consideration has been given to collaborative working with local colleges; other schools and 6th form centres to avoid working in competition or duplicating provision?

- What consideration has been given to collaborative working with local authorities to ensure more learners wih ALN can access FE provision that meets their needs?

- Active Travel

- Has the local authority assessed the travel needs of learners in their area in accordance with their statutory duty under Learner Travel Measure 2008?

- Has the local authority risk assessed the walked routes to school/college?

- What will the impact on learner travel be? Will the project reduce or increase the opportunities for learners to walk or cycle to school/college?

- Will there be adequate facilities for cycle/scooter storage?

- Has there been clear collaboration with the Local Authority’s Active Travel officers, Road Safety officers, and Transport teams in the development of the proposals?

- Have direct, safe, and high-quality active travel routes to and from the site been identified? If gaps exist, have these been communicated to the Local Authority’s Active Travel team for prioritisation within the wider active travel network map planning process?

- How is the project reducing reliance on private car use? Does it include a strategic reduction in car parking provision, particularly for short journeys that could be made actively?

- Are there safe and well-managed drop-off/pick-up zones for school or college buses that avoid congestion and enable safe walking, wheeling, and cycling on site?

- Does the design incorporate opportunities for play, social interaction, and outdoor learning along active travel corridors and within the site, contributing to placemaking and wellbeing?

- Is there provision for a secure cycle, scooter, and pram parking (where appropriate), as well as changing facilities and other infrastructure that supports walking, wheeling, and cycling as a default choice?

- Has a site-specific Active Travel School Plan (ATSP) been developed as part of the wider transport planning process to embed active travel into the school’s ethos and operations?

- Where appropriate, how will the school or college site function as a community hub, encouraging walking, wheeling, and cycling beyond the school day and supporting wider model shift in the local area?

- Town Centre First

- The Welsh Government is keen to promote the use of town centre locations for new developments where this is appropriate. Is the proposed project located in a town centre? If not, please explain why a town centre location would not be appropriate/possible.

- A map or reference to the precise location should be included.

- Play Wales

- How will the proposed facilities fit with local play sufficiency duties and provision?

- What are the proposed plans for community use of outdoor play spaces? What is needed to maximise usage (e.g. markings, floodlights, storage for play equipment)?

- What are the staffing arrangements/operating model for community use of play facilities outside of school hours?

- Sport Wales

- How will the proposed facilities fit with current local facility provision and demand (e.g. have the proposals been considered in the context of the local authority or a National Governing Body of sport facility strategy)?

- What are the proposed plans for community use of sports facilities? What is needed to maximise usage (e.g. additional hall/MUGA/pitch markings, floodlights, separate changing facilities, storage for sports equipment)?

- What are the staffing arrangements/operating model for community use of sports facilities in the evenings, weekends, and holidays?

- Community Focused Schools

- How do the proposals align with the Welsh Government’s Community Focused Schools policy?

- How will the proposed facilities fit with current/local facilities?

- What are the proposed plans for community use, including access to services and programmes which support community resilience and contribute to tackling poverty?

- What other facilities will be available for community use (e.g. room hire, adult/community learning spaces)?

- What consideration has been given to the school/college internet or ICT provision being opened up for public access (e.g. Community Wi-Fi, digital inclusion)?

- Condition and Suitability

- Detail the current condition of the facilities and how the project will remove or reduce Category D and C condition buildings or improve facilities to Category A or B condition.

- Sustainability and Net Zero Carbon

- For new build projects, please include assurance that net zero carbon in operation and the relevant embodied carbon targets will be achieved.

- For refurbishment projects, please include evidence of the current operational carbon used and that saved, and to achieve net zero both must be equal or the saving being more to show negative carbon.

- How will the project enhance biodiversity?

- Economic Case (1,500 words)

Demonstrate that the project provides good value for money

Economic Case (2,000 words)

Demonstrate that the project provides good value for money

- Investment objectives and critical success factors

- Short list appraisal – costs and benefits

- Risk assessment

- Preferred option

The Economic Case should be comprehensive at OBC stage and will not be accepted unless it contains all the necessary content. The requirements of this section at this stage are to:

- Summarise the findings from the SOC and update with any changes;

- Calculate net present values (NPVs) for all short-listed options;

- Provide an assessment of the benefits for all short-listed options; preferably the case will attempt to quantify benefits but where this isn’t possible an in depth qualitative analysis should be conducted.

- Provide an assessment of the risks (including optimism bias) for all short-listed options;

- Conduct sensitivity analysis to test the robustness of the preferred option.

Summarise and update findings from SOC

- Firstly, this section should include confirmation that the Investment Objectives and Critical Success Factors identified in the SOC have been revisited and have not changed.

- It should briefly restate the long list of options and provide a summary of how this was narrowed down to a short list.

- If this has changed since SOC stage, the process needs to be restated in full with clear explanations for decisions on whether options should be taken forward. The new short list should then be taken forward for detailed analysis.

Calculate net present values (NPV)

- NPV should be calculated in order to assess which option offers the best value for money over the expected life of the building. This is generally 30 years for a refurbishment and 60 years for a new build. The economic analysis focusses on value for money and should:

- use constant (base year) prices

- include opportunity costs

- include all quantifiable costs, benefits and risks to both the organisation and wider society

- include environmental costs; make allowances for optimism bias

- exclude all Exchequer ‘transfer’ payments – for example, VAT

- exclude general inflation

- exclude sunk costs

- exclude depreciation and capital charges.

A summary of what should be included is:

Costs

- Costs of the build

- Costs of ongoing maintenance and running the building (this could also be a cost saving)

- Any other financial costs from operating e.g. transport

- The value of existing assets to reflect their opportunity cost

- Any transactions to buy land /assets

Benefits

- The sale of existing assets

- The expected residual value of the site(s) recorded as a benefit

- Any revenue received recorded as a benefit.

- Time savings from increased productivity / efficiency Transport savings

- Economies of scale achieved from consolidating sites

- Education outcome based benefits such as improved attendance or reduced exclusions or ALN placement costs

Please see Options Appraisal Template – worked example (Annex 4) and Options Appraisal Template – blank (Annex 5). For revenue funded projects this would have been completed at SOC.

The results from the options appraisal should be the primary criteria to decide which option offers the best value for money, however a broader assessment of the options should be conducted to provide a robust, rounded narrative. This should include:

An assessment of the benefits:

- Quantitative benefits (NPV + quantitative benefits table) - Your NPV analysis and updated quantitative benefits table should be complete and together provide the core quantified assessment of each shortlisted option. These should capture the improvements in condition and suitability, number of places, reduction in backlog maintenance and other measurable benefits expected to arise from completion of works.

- Qualitative benefits (qualitative benefits table) – To complement the quantitative assessment, an updated qualitative benefits table should also be provided. This should have been complete at SOC, but at OBC we expect greater detail and clearer differentiation between shortlisted options, focusing on any significant additional benefits that cannot be monetised but are important in the context of the project, especially where these help explain why an option with negative NPV may still represent overall value.

- This assessment should complement the findings from the NPV rather than be considered the primary criteria.

N.B. The qualitative benefits table must be included in the main body of the Economic Case, so that the narrative clearly reflects both quantitative and qualitative evidence when explaining the preferred option.

An assessment of risks

- This should assess different types of risks associated with each short-listed option. It should consider the likelihood of risks occurring and their potential impact. Weighting and scoring can be used and recorded in like in the table below:

| Type of risk and Weight | Option 1 |  |  | Option 2 |  |  | Option 3 |  |  | Option 4 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Impact (I), Likelihood (L) and risk score (S) | I | L | S | I | L | S | I | l | S | I | L | S |
| Risk 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |
| Rank |  |  |  |  |  |  |  |  |  |  |  |  |

This assessment is not an isolated process and should be linked with a risk register and inform the calculation of optimism bias. Details of how risks will be monitored and been mitigated should be noted as part of a risk register. A judgement on risks and how well they can be mitigated should inform the optimism bias calculation. A template for calculating optimism bias is included within the NPV template spreadsheet.

Based on the results of the analysis, the preferred option should then be identified as the best value for money.

Sensitivity analysis

It is important that the robustness of the preferred option is tested through sensitivity analysis. This ensures that even if there are a rise in costs, a shortfall in benefits or both, that the preferred option still represents the best value for money. This can either be done using switching values or scenarios.

Summary

A summary of the analysis must be provided to show that the preferred option remains robust. A conclusion should be reached and a summary statement providing a clear narrative of the reasoning for the preferred option should be provided alongside a summary table shown below.

|  | Option 1 | Option 2 | Option 3 | Option 4 |
| --- | --- | --- | --- | --- |

| NPV quantitative assessment (£m), Appraisal period |  |  |  |  |
| --- | --- | --- | --- | --- |

| CAPEX costs | £Xm | £Xm | £Xm | £Xm |
| --- | --- | --- | --- | --- |
| Total monetisable costs (NPC) | £Xm | £Xm | £Xm | £Xm |
| Total monetisable benefits (NPB) | £Xm | £Xm | £Xm | £Xm |
| Net present value (NPV) | £Xm | £Xm | £Xm | £Xm |

Broader assessment of options

| Qualitative benefits | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) | Brief description or rank (linked to qualitative benefits table) |
| --- | --- | --- | --- | --- |
| Risk assessment | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) | Brief description or rank (linked to risk appraisal) |
| Overall ranking | Rank | Rank | Rank | Rank |

Unless prior agreement is made with the programme team, please undertake an and submit a full NPV analysis.

Commercial Case (500 words)

Demonstrate that the project is commercially viable

- Confirmation of procurement route taken

- Negotiated deal and contract arrangements

- Risk transfer agreements

- Community benefits schedule – setting out the Community Benefits / Social Value objectives of the project including the preferred reporting mechanism for the outcomes against the objectives – either the Community Benefits Measurement Tool or National TOMs for Wales

- Confirmation of Project Bank Account arrangements

  - Which bank will be used to service the PBA?

  - What type of account will be used, Joint or Sole account or

  - Details of the compelling reason(s) why a PBA is not considered appropriate

- Projects relying on a Section 106a agreement to deliver the facilities on behalf of the local authority, we would expect the delivery partner to have a PBA in the s106 agreement.

Financial Case (500 words)

Demonstrate that the project is affordable

- Financial forecast

- Final tendered project costs

- Finalised sources of matching funding broken down by source (capital resources, borrowing etc.)

- Size and cost benchmark appraisal

- Project Information Proforma (PIP)

- Project Cost Template (PCT) which should include a detailed breakdown of abnormal costs and estimates for NZC and irrecoverable VAT where applicable.

- Final cabinet or Board approval

- Details of any revenue savings

- Details of any other WG funding streams (e.g. Childcare Capital Grant)

Management Case (500 words)

Demonstrate that the project will be delivered effectively. Finalise arrangements and plans for the following:

- Project delivery

- Statutory procedures

- Risk register (top 5)

- Benefits realisation

- Social Value and Community Benefits reporting arrangements

- Project assurance

- Change and contract management

- Post project evaluation

- Updated project milestones / programme and contingency arrangements

Templates

Please ensure the following templates are completed and submitted at the relevant business case stage:

| Template | SOC | OBC | FBC | BJC |
| --- | --- | --- | --- | --- |
| Programme Business Case Template |  |  |  |  |
| Project Benefits Template |  |  |  |  |
| Options Appraisal |  |  |  | * |
| Project Cost template |  |  |  |  |
| Project Information Proforma | ** |  |  |  |

*Unless agreed otherwise with the Programme team

**Finance section only

Conditions of Funding

There are specific grant conditions that local authorities and further education institutions need to be aware of when submitting business cases:

- Community Benefits

- Project Bank Accounts

- British Research Establishment Environmental Assessment Method (BREEAM) and Energy Performance Certification (EPC)

- Surface water drainage

- Foul drainage

- Recycled content

- Fire sprinklers

- Acoustics (BB93)

- Accessibility and Equality

- Active Travel

- Carbon Reduction

- Biodiversity and Resilience of Ecosystems duty

For more information please refer to the business case guidance or speak with a member of the Sustainable Communities for Learning team.