Gwerthusiad Peilot Ail Gartrefi a Fforddiadwyedd Cyfnod 2
Second Homes and Affordability Pilot Evaluation Phase 2

---
Trosolwg o’r Gwerthusiad Evaluation Overview
Amserlen yr asesiad: Awst 2023 i Ragfyr 2026
Tri Cham:
Cam 1: Cwmpasu, mapio data, ymchwil archwiliadol (adroddiad wedi'i gyhoeddi Chwefror 2025)
Cam 2: Gwerthuso prosesau (Adroddiad wedi'i gyhoeddi 17 Rhagfyr 2025)
Cam 3: Gwerthuso effaith ac economaidd (gwaith maes ar y gweill ar hyn o bryd, adroddiad terfynol i'w gyflwyno ddechrau 2027)
Evaluation timeline: August  2023 to December 2026
Three Phases:
Phase 1: Scoping, data mapping, exploratory research (report published Feb 2025)
Phase 2: Process evaluation (Report published 17 Dec 2025)
Phase 3: Impact and economic evaluation (fieldwork currently underway, final report due early 2027)

---
Dull Gwerthuso Proses Process Evaluation Method
Gwerthusiad proses: "beth y gellir ei ddysgu o sut mae polisi, peilot neu raglen wedi'i gyflwyno?“
Gwaith maes
 Cyfwelwyd â phartneriaid y Peilot (Ebrill – Gorffennaf 2025)
Cyngor Gwynedd, Tai Teg, Adra, Parc Eryri, Cwmpas, a Llywodraeth Cymru
Cyfwelwyd â 32 o randdeiliaid yng nghymuned leol Dwyfor (Mehefin – Awst 2025)
13 o berchnogion ail gartrefi neu dai tymor byr
3 o berchnogion busnesau neu fentrau cymdeithasol
3 o bobl sy'n ymwneud â thai dan arweiniad y gymuned
Y gweddill oedd trigolion lleol ac aelodau o grwpiau cymunedol
A process evaluation: "what can be learnt from how a policy, pilot or programme has been delivered?"
Fieldwork
Interviewed Pilot partners (April – July 2025)
Cyngor Gwynedd, Tai Teg, Adra, Parc Eryri, Cwmpas, and the Welsh Government
Interviewed 32 stakeholders in the Dwyfor local community (June – August 2025)
13 second home or short-term let owners
3 business or social enterprise owners
3 people involved in community-led housing
The rest were local residents and members of community groups

---
Canfyddiadau Allweddol: Llwyddiannau'r Peilot
Key Findings: Pilot Successes
Set-up phase of Pilot:
Having the opportunity to make a difference in Dwyfor
Increased resource and capacity for tackling housing issues
Building relationships between the Welsh Government and Pilot partners
Refining ways of working collaboratively
Reaching intended beneficiaries:
Overall agreement by stakeholders  that interventions are reaching their intended beneficiaries, but easier to measure for some interventions (e.g. Homebuy) than others
Council tax premiums are seen to have the greatest reach and Article 4 is seen as having similar potential
Cyfnod sefydlu'r Peilot:
Cael y cyfle i wneud gwahaniaeth yn Nwyfor
Cynyddu adnoddau a chapasiti i fynd i'r afael â phroblemau tai
Adeiladu perthnasoedd rhwng Llywodraeth Cymru a phartneriaid y Peilot
Mireilio ffyrdd o weithio ar y cyd
Cyrraedd y buddiolwyr bwriadedig:
Cytundeb cyffredinol gan randdeiliaid bod ymyriadau'n cyrraedd eu buddiolwyr bwriadedig, ond yn haws i'w mesur ar gyfer rhai ymyriadau (e.e. Prynu Cartref) nag eraill
Gwelir bod gan bremiymau treth y cyngor y cyrhaeddiad mwyaf ac ystyrir bod gan Erthygl 4 botensial tebyg

---
Canfyddiadau Allweddol: Llwyddiannau'r Peilot
Key Findings: Pilot Successes
Working with different stakeholders:
Generally good relationships and strong collaboration between stakeholders
The Homebuy scheme and Article 4 were cited as particularly good examples of collaboration
Gweithio gyda gwahanol randdeiliaid:
Perthnasoedd da yn gyffredinol a chydweithio cryf rhwng rhanddeiliaid
Cafodd y cynllun Prynu Cartref ac Erthygl 4 eu dyfynnu fel enghreifftiau arbennig o dda o gydweithio.

---
Canfyddiadau Allweddol: Heriau'r Peilot
Key Findings: Pilot Challenges
Set-up phase of Pilot:
A lack of experimentation at the beginning, with frustration at the level of ‘red tape’
Difficulties communicating purpose of the Pilot
Managing different stakeholders’ expectations
Risks and obstacles:
Unique to each intervention, for example:
Legal risks for Article 4
Level of resource required for community-led housing initiatives
A previous data protection issue for Homebuy
Working with different stakeholders:
Some challenges include misalignment of responsibilities and knock-on effects of each other’s implementation of schemes
Cyfnod sefydlu'r Peilot:
Diffyg arbrofi ar y dechrau, gyda rhwystredigaeth ar lefel y 'biwrocratiaeth'
Anawsterau wrth gyfleu pwrpas y Peilot
Rheoli disgwyliadau gwahanol randdeiliaid
Risgiau a rhwystrau:
Unigryw i bob ymyrraeth, er enghraifft:
Risgiau cyfreithiol ar gyfer Erthygl 4
Lefel yr adnoddau sydd eu hangen ar gyfer mentrau tai dan arweiniad y gymuned
Mater diogelu data blaenorol ar gyfer Homebuy
Gweithio gyda gwahanol randdeiliaid:
Mae rhai heriau'n cynnwys camlinio cyfrifoldebau ac effeithiau canlyniadol gweithredu cynlluniau ei gilydd

---
Canfyddiadau Allweddol: Meysydd i'w Gwella
Key Findings: Areas for Improvement
Partneriaid y Peilot:
Cael rolau a chyfrifoldebau wedi'u diffinio'n gliriach ar gyfer partneriaid y Peilot, gan gynnwys llinellau cyfathrebu cliriach
Caniatáu mwy o arbrofi ar ymyriadau yn y Peilot, gan gynnwys canllawiau cliriach ynghylch pa fathau o gynigion y gellir a na ellir eu derbyn
Aelodau'r gymuned leol:
Mae diddordeb mewn gweld mwy o dryloywder ynghylch sut mae refeniw a gynhyrchir trwy bremiymau treth y cyngor yn cael ei wario
Targedu ymyriadau'n well o amgylch cynaliadwyedd y Gymraeg
Gwella cyfathrebu trwy gynnal sesiynau wyneb yn wyneb y gallai aelodau'r gymuned leol fynychu
Yn gyffredinol, mwy o ymgysylltiad gan bobl leol wrth wneud penderfyniadau
Mwy o dai i'w hadeiladu, yn enwedig ar ôl ymgynghori'n ystyrlon â chymunedau.
Pilot partners:
Having more clearly defined roles and responsibilities for Pilot partners, including clearer lines of communication
Allowing for more experimentation of interventions in the Pilot, including clearer guidelines around what sorts of proposals can and cannot be accepted
Local community members:
There is interest in seeing greater transparency around how revenue generated through council tax premiums is spent
Better targeting of interventions around Welsh language sustainability
Improving communication by running in-person sessions that local community members could attend
Generally, more engagement of local people when making decisions
More housing to be built, especially after meaningful consultation with communities

---
Effeithiau sy'n Dod i'r Amlwg Emerging Impacts
Noder bod y canfyddiadau hyn yn seiliedig ar adroddiadau cyfyngedig ac ni ddylid eu dehongli fel tystiolaeth gadarn o effaith. Maent yn darparu mewnwelediadau dangosol yn hytrach na chasgliadau pendant.
Peilot cyffredinol:
Canfyddiadau o gyflawni'r nod cyffredinol o wella tegwch a darparu cyfle cyfartal i bobl leol
Llywio polisi cenedlaethol
Meithrin perthnasoedd cryf rhwng partneriaid y Peilot a Llywodraeth
Cymru Prynu Cartref – Cymru:
Adroddiadau cyfyngedig bod buddiolwyr wedi prynu cartrefi na fyddent fel arall yn gallu eu prynu
Tai dan arweiniad y gymuned:
Mae arwyddion bod tai newydd yn dod i ddefnydd
Ymddengys bod rhai grwpiau cymunedol wedi datblygu mwy o hyder.
Please note that these findings are based on limited reports and should not be interpreted as robust impact evidence. They provide indicative insights rather than definitive conclusions.
Pilot overall:
Perceptions of achieving overall aim of improving fairness and providing equal opportunity for local people
Informing national policy
Fostering strong relationships between Pilot partners and the Welsh Government
Homebuy – Wales:
Limited reports that beneficiaries have purchased homes they otherwise wouldn’t be able to
Community-led housing:
There are indications that new houses are coming into use
Some community groups appear to have developed greater confidence

---
Effeithiau sy'n Dod i'r Amlwg Emerging Impacts
Noder bod y canfyddiadau hyn yn seiliedig ar adroddiadau cyfyngedig ac ni ddylid eu dehongli fel tystiolaeth gadarn o effaith. Maent yn darparu mewnwelediadau dangosol yn hytrach na chasgliadau pendant.
Premiymau treth y cyngor
Yn ôl y sôn, mae mwy o ail gartrefi yn mynd ar werth yn Nwyfor, ond mae rhai wedi nodi eu bod yn cael trafferth gwerthu
Mae rhai adroddiadau bod perchnogion tai ail wedi dechrau rhentu eu heiddo am gyfnod byr i dalu am bremiymau treth y cyngor
Adroddodd rhai perchnogion busnesau sy'n dibynnu ar fasnach o ail gartrefi y gallai'r premiymau fod wedi effeithio'n negyddol ar eu busnes
Erthygl 4:
Teimlai rhai aelodau o'r gymuned leol ei bod hi'n anoddach gwerthu eiddo oherwydd Erthygl 4.
Please note that these findings are based on limited reports and should not be interpreted as robust impact evidence. They provide indicative insights rather than definitive conclusions.
Council tax premiums
Reportedly more second homes going up for sale in Dwyfor, but some reported they are struggling to sell
Some reports of second homeowners have started short-term letting of their properties to cover council tax premiums
Some business owners who rely on trade from second homes reported that the premiums may have negatively affected their business
Article 4:
A few members of the local community felt it is more difficult to sell properties because of Article 4

---
Camau Nesaf y Gwerthusiad Evaluation Next Steps
Mae'r gwerthusiad effaith ar y gweill ar hyn o bryd. Bydd hwn yn cael ei gyhoeddi ddechrau 2027.
Gwerthusiad lefel peilot: Ymchwil i asesu effeithiau cyffredinol y rhaglen; cymharu ardal y Peilot ag ardaloedd cymharol
Ardaloedd eraill yng Nghymru, Cernyw a chymhariaeth lefel genedlaethol
Gwerthusiad lefel polisi penodol (Plymio manwl): Asesu cyfraniad a gwerth polisïau unigol a ddewiswyd
Prynu Cartref, Prynu Cartref adeiladu pwrpasol, tai dan arweiniad y gymuned, Erthygl 4, premiymau treth y cyngor, trethi annomestig.
The impact evaluation is currently underway. This will be published in early 2027.
Pilot level evaluation: Research to assess overall programme effects; comparison of Pilot area with comparator areas
Other areas in Wales, Cornwall and national level comparison
Specific policy-level evaluation (Deep dive): Assess the contribution and value of selected individual policies
Homebuy, purpose build Homebuy, community led housing, Article 4, Council tax premiums, non-domestic rates.
[Speaker Notes: Approach: Review of policy landscape and current data  Prioritise policies & measures to focus on 1.1. Example policies to be prioritised: Council Tax Premium; Article 4 Direction; Homebuy – Wales; Community-Led Housing Stakeholder engagement: Approx. 25 interviews with WG and policy-specific representatives. Development of Impact Evaluation Framework and Cost-Benefit Analysis Framework (Spring)  Reassess policy context, refine methodology, and update with latest data (Summer) Number of chargeable second homes, chargeable empty properties and short-term lets over years % of chargeable second homes of housing stock % of chargeable empty properties of housing stock % of short-term lets of housing stock Housing stock additions – new dwellings: Statswales: https://statswales.gov.wales/Catalogue/Housing/New-House-Building/newdwellingsstarted-by-area-dwellingtype House prices Rents Affordability (both to rent and to buy) The stats Wales data is based on CT1 predictions and may not be as reliable as snapshot data (of the sort Cyngor Gwynedd share with us). Stats colleagues working on domestic rates data have access to this data by local authority and may be able to provide for the purposes of the evaluation? Is it worth us asking or do you prefer to go with CT1?]