Education Investment Panel – 26 February 2026

Item 7.3.2 – RCT - Ysgol Gyfun Gymraeg Cwm Rhondda - FBC

- Key Statistics

| Project Title | Ysgol Gyfun Gymraeg Cwm Rhondda |  |  |  |
| --- | --- | --- | --- | --- |
| Project Type | Secondary new build |  |  |  |
| Local Authority | RCT |  |  |  |
| Cost/WG Share (%) | Element | Total Cost | WG Contribution | WG % |
|  | Project Cost (Excl. NZC) | 73,730,980 | 47,925,137 | 65 |
|  | NZC Cost | 3,769,020 | 3,769,020 | 100 |
|  | Overall Project Cost | 77,500,000 | 51,694,157 | 66.7 |
| Business Case Stage | FBC |  |  |  |
| Business Case History | SOC Approval Date | June 2025 |  |  |
|  | SOC Cost | £77,500,000 |  |  |
|  | OBC Approval Date | December 2025 |  |  |
|  | OBC Cost | £77,500,000 |  |  |
|  | Recent links attached: |  |  |  |
| Primary Purpose | Condition, suitability, Cymraeg 2050, rationalisation and improving access |  |  |  |

- Summary

This proposal aims to build a new Welsh medium secondary school for Ysgol Gyfun Cwm Rhondda (YGCR), with new teaching facilities for 750 pupils (ages 11-16) and 150 sixth form pupils (total capacity: 900 pupils). Investment will improve the school building offer for Welsh medium education and create a continuum of learning to support Cymraeg 2050 targets. SOC was approved in June 2025. It is proposed that a new school will be built on the existing school site (proposed start on site is Sept 2026), and it will open during the 2030 academic year. Investment will provide a modern, flexible learning environments for all pupils which will include: - a hall/dining area, sports hall, and specialist teaching and learning areas to cater for the needs of all pupils i.e. science labs, food technology classrooms and ICT suites. - Dedicated facilities within the school boundary that the local community will be able to safely use, both during and after the school day. - Enhanced outdoor spaces to support the full range of curriculum activities. - Improved traffic management systems including on-site pupil bus drop off, and onsite staff and visitor parking. Kier, with scrutiny from Aecom have benchmarked the construction costs and an opportunity schedule has been developed since submission of the OBC. Kier and Aecom, are confident further opportunities can be identified as the project progresses through the RIBA stages. The project cost with this business case has been completed using a Stage 2 Plus Cost Plan. This is predominantly based on the RIBA Stage 2 design, including elements of the Stage 3 design which have been developed to date. The latest benchmarked cost data has been used to inform this cost plan. This ensures the costs included are robust and a reflection of the current market rates. The preliminary costs and design fees are based on tendered sums submitted by Kier.

Key Benefits - Delivering a significant improved educational provision, having a noteworthy positive impact upon the educational performance of the pupils and staff morale. - Building to net zero carbon in operation with a BREEAM rating of ‘excellent’. Be fully compliant with the Equality Act 2010. - Providing dedicated facilities will be designed within the site so that the local community will be able to safely use the facilities, both during and after the school day. - Deliver external areas that would allow pupils and staff to experience a greater breadth of teaching and learning experiences, in line with the New Curriculum for Wales. - Provide sustainable and attractive Welsh Medium education opportunities to support Welsh Government’s Cymraeg 205: A Million Welsh Speakers and RCT’s Welsh in Education Strategic Plan (WESP).

Delivery Timescales Action Timeline RCTCBC Cabinet Approval to Proceed 19th March 2025 SOC Submission 1st May 2025 OBC Submission 23rd October 2025 PAC Period Commences 15th December 2025 FBC Submission 8th January 2026 Planning Submission February 2026 SAB Submission May 2026 Construction Commencement Summer 2026 New Build Complete 2029 Demolition and Externals Complete 2030

- Discussion Points

| Category | Details |  |
| --- | --- | --- |
| Local provision | Ysgol Gyfun Cwm Rhondda is in the village of Cymmer, southwest of Porth, Rhondda Cynon Taf. The existing school site is made up of seven buildings varying in construction methods, across several level changes. Block 1: Sports block Block 2: Teaching block split over 4 levels (CLASP 1960/70) Block 3: New 3 storey teaching block Block 4: Single storey specialist teaching block (CLASP 1960/70) Block 5: Victorian teaching block Block 6: teaching block with main hall and sixth form There are currently 625 pupils on roll, 559 aged 11-16 and 66 sixth form pupils aged 17-19 (PLASC 2025). To note there are 5 WM primary schools in the YG Cwm Rhondda cluster. Pupil projections within the school are set to rise over the next 4 years (647 2028/29), however feeder school projections show a gradual decrease over the same time hence the reduction in capacity in the new school. |  |
| Short-listed options | - Option One – Business as Usual: Maintain current Welsh medium secondary school provision at YG Cwm Rhondda. Provision at YGCR to remain as is, with future repairs and redecorations dealt with on a priority basis. RCTCBC continue to project manage future repairs and redecorations of the school. Ongoing. Funded entirely using RCTCBC funds. - Option Two – Do Minimum Demolish the Victorian building at YG Cwm Rhondda and rebuild in the same footprint. Demolish the Victorian building at YG Cwm Rhondda and rebuild in the same footprint. RCTCBC to design and manage the design and reconstruction of the Victorian teaching block. Deliver the new school by September 2032. Funded entirely using RCTCBC funds. - Option Three – Most Ambitious (A): Preferred way forward Redevelop YG Cwm Rhondda in a phased approach with 21st Century facilities. Build a new Welsh medium secondary school with 21st Century facilities. RCTCBC to commission and project manage consultant team to redevelop the school on the existing site, to design and build new facilities. Deliver the new school during 2030 academic year. This project is funded through a combination of RCTCBC funds and external funding via the WG’s Sustainable Communities for Learning Programme. |  |
| Capacity | Existing (FTE); Proposed (FTE); Change +/-. EM; WM; EM; WM; EM; WM. Childcare Offer. Nursery. Primary. Secondary; 870; 750; -120. Post-16; 153; 150; -3. Additional Learning Needs. Total; 1023; 900; -123. |
| Cymraeg 2050 / WESP | This project supports Cymraeg 2050 targets and RCT’s Outcome 1 of its WESP. An impact assessment has been undertaken. |  |
| Condition and suitability | Recent condition survey grade: C with backlog maintenance of c£4.097m. ‘The overall mechanical and electrical services are functioning but are near the end of their expected life span. Some buildings need significant investment.’ Number of buildings known to contain asbestos. |  |
| Sustainability | Net Zero Carbon in operation and BREEAM Excellent will be achieved, in accordance with current requirements of planning and building control legislation. It will be fully accessible and compliant with the Equality Act 2010. This project will include a review of safe routes to school and, if required, an investment in improvements to walkways, road crossings and traffic calming measures to ensure the required safety standards are met. Traffic/Highways will form part of the Client Engagement Meetings (CEM) process, which will be used in this project from initial contractor appointment to build the project brief and keep all stakeholders involved in the project. An initial presentation has been made to key internal stakeholders include highways, on 7 August 2025; providing an opportunity to ask questions and share observations of the plan. This project will include a review of safe routes to school and, if required, an investment in improvements to walkways, road crossings and traffic calming measures to ensure the required safety standards are met. Where possible, we will look to increase opportunities for pupils, staff and the community to walk/cycle/scooter to school. The promotion and implementation of active travel will also feature within the design of the new school. The new school will allow for public enabled Wi-Fi which will facilitate the delivery of adult learning and other community activities. |  |
| Town Centre First | The school is in walking distance to Porth town centre. |  |
| Community Facilities | There will be areas designed within the new school for the local community to safely access and benefit from use of the new facilities, both during and after the school day. This will enhance the already well-used community facilities and allow for the further expansion of wider community engagement. The project will include a community room with ICT equipment whereby there could be an offer of ICT support, Welsh learners’ sessions etc. Also, the existing offer of internal, and external sports facilities for community use will be strengthened – this includes a much-improved sports hall and an all-weather sports pitch. |  |
| Size compared with standard benchmark | - Proposed area (m2) New build: c8,888 Light refurbishment (to facilitate a single-phased build) c1,200 | 8888 + 1,200 10,088 |
|  | - Benchmark area (m2) New Build Light refurbishment | 8726 |
|  | - Variance (m2) | 1,362 |
|  | Justification for additional areas: The size of the hall and the inclusion of a multi-gym is showing above the recommended guidelines for a school of this size. This reflects the community use aspect. Various stakeholders already use the school and as part of the proposal there is an opportunity to provide a setting for Rhondda Netball group to compete at a ‘Club’ level and support their links with Rhondda Schools Rugby and Welsh Rugby Union. |  |
| Cost compared with standard benchmark figure | (a)Total cost of project: | 77,500,000 REDACTED |
|  | (b) Standard benchmark cost for construction (or nearest available benchmark): New build Refurbishment | 37,955,548 36,268,348 1,687,200 |
|  | Variance With abnormals included Without abnormals | REDACTED |
|  | Overall cost per square metre Significantly higher than other projects when abnormals included. REDACTED | REDACTED |
|  | Further explanation (abnormals; adjustment to allow for more or fewer pupil places compared to nearest benchmark figure): The school site is challenging with significant level changes. It is proposed that the new school be built on the existing school site of Ysgol Gyfun Cwm Rhondda, which was selected as no other suitable sites were available. Historic maps and information indicate the school site was previously used for industrial purposes including a quarry and tramway sidings, therefore, detailed site-specific investigation works with the appropriate enabling and demolition works along with clearance of the existing buildings and site are required. Robust site surveys and investigations have been undertaken that have aided the design of the new school. The topography and the nature of the site are extremely challenging, with circa 25m level difference from the highest to the lowest part of the school site. A significant proportion of the project costs are considered ‘abnormal’ as listed above. REDACTED | REDACTED |
| Comparison with other projects | Cost comparison to similar projects - comparison information in the absence of an updated benchmark [REDACTED] |  |
| Risks | A limited part of the site is located with the Flood Zone 2 & 3 (Surface Water and Small Watercourses). This is located near to the existing cluster of teaching blocks southeast of the site. Management of this will be considered during the design stage. To note: the site is not located in a flood zone for rivers and seas. SAB approval is required. A SuDS application will be submitted February 2026 for Sustainable Drainage Approving Body (SAB) approval prior to the commencement of works. A Pre-Application Consultation (PAC) will be undertaken for this project and a PAC report will be submitted. An initial presentation was made to key internal stakeholders including a Planning Officer on 7th August 2025. This presentation also provided the opportunity for questions to be asked and observations to be shared. The PAC period is currently live, running from 15th December 2025 until 23rd January 2026. |  |
| Links with other grants | NA |  |

- Assessment Summary

| Case | Assessor/Division | Queries raised | Date Addendum Issued | Date Addendum Response Agreed | Approved |
| --- | --- | --- | --- | --- | --- |
| Strategic Case | # REDACTED | No |  |  | Yes |
|  | # REDACTED | No |  |  | Yes |
|  | # REDACTED | No |  |  | Yes |
|  | # REDACTED | No | 28/01/26 | 3/2/26 | Yes (see note) |
|  | # REDACTED | No |  |  | Yes |
|  | REDACTED | No |  |  | Yes |
|  | # REDACTED | Yes |  |  | Yes |
|  | # REDACTED | No |  |  | Yes |
|  | REDACTED | Yes |  |  | Yes |
|  | # REDACTED | Yes/No | 28/01/26 | 12/02/26 | Yes (with caveat) |
|  | # REDACTED | Yes | 28/01/26 | 12/02/26 | Yes |
|  | # REDACTED | NCR |  |  | NA |
|  | # REDACTED | Yes | 28/01/26 | 03/02/26 | Yes |
|  | # REDACTED | No |  |  | Yes |
|  | # REDACTED | NCR |  |  | NA |
|  | # REDACTED | No |  |  | Yes |
|  | # REDACTED | NA |  |  | NA |
| Economic Case | # REDACTED | No |  |  | Yes |
| Commercial Case | REDACTED | No |  |  | Yes |
| Financial Case | # REDACTED | No |  |  | Yes |
| Management Case | # REDACTED | No |  |  | Yes |

* Approved - Assessor content within own area of expertise

** NA - Not applicable

*** NCR - No comments received from policy colleague

- FEI Financial health check rating

NA

- Recommendation / Sign Off

| Business Case Scrutiny Group meeting date | 22/01/26 |
| --- | --- |
| Business Case Scrutiny Group – date of sign off | 12/02/26 |
| Recommendation to Education Investment Panel | Approve so that a grant award letter can be issued. Subject to further justification for retaining a sixth form capacity of 150 places despite numbers on roll falling from 125 in 2021 to 65 in 2024–25. While recent Cymraeg 2050 investments have supported modest improvements, the benefits of the newly awarded Medr funding have not yet been realised and, as the Medr funding is for one year only, it cannot be relied upon to justify such a significant expansion at this stage. Additional clarity is required on realistic future demand, long term sustainability, and alignment with wider Welsh medium tertiary planning across RCT. |